## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-B) | SM/07370 | Retrofitting | Creation of 'FHTC (Funtional House Hold Tap Connection)' of left out Mouza, in connection with Jal Jeevan Mission of Indas W/S Scheme (PWSS) Block- Indas under Bishnupur Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000671/2022-2023 | 514/BQA | 13/03/2023 | 11/06/2023 | S B ASSOCIATES | 90.97 | 78.61 | 86.41 | 50
2 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-B) | SM/07370 | Retrofitting | FHTC Maintenance of Indas Water Supply Scheme under Bishnupur Sub Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000298/2022-2023 | 316/VSD | 29/11/2022 | 14/12/2022 | GOUTAM GHOSH | 0.96 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-B) | SM/07370 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000019/2021-2022 | 477/BQA | 04/03/2022 | 04/03/2022 | Resource Division | 7.94 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme (Part-B) | SM/07370 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000010/2022-2023 | 2036/BQA | 29/09/2022 | 29/09/2022 | Resource Division | 8.74 | 0 | 0 | 0
Total | [13 empty] | 108.61 | 78.61 | 72.38