## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Madandihi (101) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 3) |  | Junior Engineer | ORD/000073/2020-2021 | 133/KSD | 12/02/2021 | 27/02/2021 | BISWAJIT LAI | 4.19 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kamardanga (99) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 8) |  | Junior Engineer | ORD/000093/2020-2021 | 138/KSD | 12/02/2021 | 27/02/2021 | UTTAM KUMAR SINHAMAHAPATRA | 3.44 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malcharar (100) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 4) |  | Junior Engineer | ORD/000085/2020-2021 | 134/KSD | 12/02/2021 | 27/02/2021 | BIKASH MANDAL | 3.83 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kamardanga (99) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 9) |  | Junior Engineer | ORD/000099/2020-2021 | 139/KSD | 12/02/2021 | 27/02/2021 | UTTAM KUMAR SINHAMAHAPATRA | 3.4 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | "Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Baragram (86) mouza under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 01 No. Total Household - 196 Nos. " |  | Junior Engineer | ORD/000033/2021-2022 | 1780/BQA | 09/07/2021 | 08/08/2021 | DAUD ALI KHAN | 12.24 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | "Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Purnapani (89) and Pirargari (95) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 02 Nos. Total Household - 197 Nos. " |  | Junior Engineer | ORD/000035/2021-2022 | 1782/BQA | 09/07/2021 | 08/08/2021 | DAUD ALI KHAN | 12.28 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | "Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhabanipathar (90) mouza under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 01 No. Total Household - 114 Nos. " |  | Junior Engineer | ORD/000036/2021-2022 | 1783/BQA | 09/07/2021 | 08/08/2021 | SUNIL KUMAR MANDAL | 7.37 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Shukni Basa (181), Majgerya (182), Birbhandh (183), Dudhenala (184), Khunta Banda (185) & Kharujhor (186) mouzas under Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 6 Nos. Total Household - 527 Nos. |  | Junior Engineer | ORD/000032/2021-2022 | 1779/BQA | 09/07/2021 | 08/08/2021 | EARTH MOVING (INDIA) | 36.83 | 24.63 | 66.88 | 0
9 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Zone-J (Rudra) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-J (Rudra) :- Baddi (26), Gholkuri (27), Kata Kumari (28), Deulbhira (29), Laekdihi (30), Ladda (33), Lipidiri (34), Ramdungri (35), Dhanara (36), Nischintapur (37), Rudra (38), Burisol (39), Keshra (40), Rajsol (41), Bag Sanda (51), Mahespur (52), Deuli (53), Chirkun Kanali (54), Bagdubi (56), Palash Bani (57), Sukhla (58), Maukanali (59), Budh Khila (60), Atasol (61), Tamakhun (62), Dhabani (63), Naranpur (64), Susunigeria (77), Bikramdihi (81) & Dhagra (82) Total Mouza:- 30 Nos. Total Household - 4013 Nos. |  | Junior Engineer | ORD/000068/2021-2022 | 2290/BQA | 06/09/2021 | 21/10/2021 | GOPAL CHANDRA CHOUDHURY | 251.08 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-I (Hatikheda) :- Nilgiri (12), Balarampur (13), Sareng Garh (14), Dudha Jharna (15), Paresnath (16), Kamarkuli (17), Barda (18), Ambikanagar (19), Hatikheda (20), Mukundaur (21), Chiada (22), Punnapani (23), Puddi (24), Jharia (25), Ladhan Bani (31), Dulalpur (32), Rajsol (41), Thutasol (42), Lalmoni Kocha (43), Chhatar Doba (44), Damodarpur (45), Dhananjaypur (46), Jaynagar (47), Barkola (48), Chaitandihi (49), Kheria Kocha (50), Jorakend (55), Dhagra (82) & Bansol (83) Total Mouza:- 29 Nos. Total Household - 3152 Nos. |  | Junior Engineer | ORD/000067/2021-2022 | 2289/BQA | 06/09/2021 | 21/10/2021 | M/S TARUN KUMAR PATRA | 191.43 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | "Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Nutandihi (93) mouza under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 01 No. ,Total Household - 171 Nos. " |  | Junior Engineer | ORD/000038/2021-2022 | 1785/BQA | 09/07/2021 | 08/08/2021 | UTTAM KUMAR SINHAMAHAPATRA | 10.68 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Malcharar (100) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 6) |  | Junior Engineer | ORD/000283/2021-2022 | .649/KSD | 17/09/2021 | 02/10/2021 | TAPAN KUMAR MANDAL | 4.36 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Singlahar (168), Paryasa (169), Purnapani Chhota Tung (170) & Purnapani Bara Tung (171) mouzas under Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 4 Nos. Total Household - 589 Nos. |  | Junior Engineer | ORD/000031/2021-2022 | 1778/BQA | 09/07/2021 | 08/08/2021 | EARTH MOVING (INDIA) | 40.2 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dhadkidihi (92) and Puada (94) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 02 Nos. Total Household - 222 Nos. |  | Junior Engineer | ORD/000037/2021-2022 | 1784/BQA | 09/07/2021 | 08/08/2021 | BEAUTY CHATTERJEE | 13.71 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sukni Basa (91), Chholagara (96) & Dhadanga (97) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000156/2021-2022 | 2828/BQA | 16/11/2021 | 16/12/2021 | TAPAS GHOSH | 12.37 | 0 | 0 | 0
16 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Baragram (86) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 3) |  | Junior Engineer | ORD/000274/2021-2022 | 646/KSD | 17/09/2021 | 02/10/2021 | SAMIRUDDIN KHAN | 4.26 | 0 | 0 | 0
17 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Bhabanipathar (90) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 08) |  | Junior Engineer | ORD/000280/2021-2022 | 719/KSD | 12/11/2021 | 27/11/2021 | TAPAN KUMAR MANDAL | 1.57 | 0 | 0 | 0
18 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Jamda (98) & Kamardanga (99) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 4) |  | Junior Engineer | ORD/000240/2021-2022 | 674/KSD | 29/09/2021 | 14/10/2021 | EDER ALI KHAN | 4.23 | 0 | 0 | 0
19 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Baragram (86) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 4) |  | Junior Engineer | ORD/000275/2021-2022 | 647/KSD | 17/09/2021 | 02/10/2021 | DAUD ALI KHAN | 3.52 | 0 | 0 | 0
20 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Household survey in different mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) & Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 14) |  | Junior Engineer | ORD/000220/2021-2022 | 622/KSD | 09/08/2021 | 09/11/2021 | TAPAS DEY | 4.56 | 0 | 0 | 0
21 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Purnapani (89) & Pirargari (95) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 8) |  | Junior Engineer | ORD/000276/2021-2022 | 651/KSD | 17/09/2021 | 02/10/2021 | DAUD ALI KHAN | 1.35 | 0 | 0 | 0
22 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Belitore w/s scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - barjora G.P chandar, Name of OHR - Murakata Total House Hold - 45 sl no - 08. |  |  | VCH/001293/2021-2022 | FHTC/02 | 02/08/2021 | 02/08/2021 | JAGADISH BANERJEE | 4.4 | 0 | 0 | 0
23 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Rerofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 5 nos ( Hatasora, Jirrakelai, Sirpura, Tulsa (Part), Sihika.) Total House Hold - 552 |  |  | VCH/001733/2021-2022 | FHTC/23 | 23/11/2021 | 23/11/2021 | SOUMITRA BHATTACHARYA | 37.11 | 0 | 0 | 0
24 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra UPVC pipeline to Cover Pratappur , Balarampur, Telegarah, Chapatara & Sendra Mouzas for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Cherabasta ( Zone-K) under Bankura - I, II, & Barjora Block W/S Scheme ( BRGF ph -I project) under Bankura Sadar Sub-Division of Bankura Division |  |  | VCH/001404/2021-2022 | FHTC/15 | 15/09/2021 | 15/09/2021 | GOPAL CHANDRA CHOUDHURY | 4.59 | 0 | 0 | 0
25 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra new UPVC pipeline to cover Kadmaghati mouza for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Arjunpur ( Zone-N) under Bankura - I , II & Barjora Block W/S Scheme ( BRGF Ph-I project) under Bankura Sadar Sub Division of Bankura Division PHE Dte. |  |  | VCH/001407/2021-2022 | FHTC/15 | 15/09/2021 | 15/09/2021 | GOPAL CHANDRA CHOUDHURY | 4.19 | 0 | 0 | 0
26 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Household survey of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA under Bankura - I,II & Saltora Block under Salota - Chhatna block (BRGF ph - I project) under Bankura sadar sub-division of Bankura division PHE Dte. block - Saltora, no. of mouza - 03 nos total house hold - 7930 (M.b. No. 3507) |  |  | VCH/001575/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | TAPAS DEY | 1.75 | 0 | 0 | 0
27 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra HDPE pipeline to cover Nachna (107) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 09) |  |  | VCH/001031/2021-2022 |  | 16/09/2021 | 16/09/2021 | SUBHADIP KOLEY | 2.42 | 0 | 0 | 0
28 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra UPVC pipeline to cover Purnapani Chhota Tung (170) & Purnapani Bara Tung (171) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I)at Block-Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- A) |  |  | VCH/001315/2021-2022 |  | 28/09/2021 | 28/09/2021 | UNITED TRADERS | 4.94 | 0 | 0 | 0
29 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra UPVC pipe line to cover Nutandihi Mouza for Construction and commissioning of FHTC (Functional House Hold Tap Connection) Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme |  |  | VCH/001500/2021-2022 |  | 08/10/2021 | 08/10/2021 | UTTAM KUMAR SINHAMAHAPATRA | 4.85 | 0 | 0 | 0
30 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Extra UPVC line of retrofitting works for creating of FHTC ( Functional Household Top Connection ) with jal jivan mission (JJM) and Jal Swapna of DADHIMUKHA Zone-D under Bankura I,II & Barjora Block W/S Scheme ( BRGF Ph-I Project) under Bankura Sadar Sub Division of Bankura Division . PHE Dte. ( Sl.No-18), |  |  | VCH/001570/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | DAUD ALI KHAN | 3.98 | 0 | 0 | 0
31 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Household survey in Jagannathpur (110), Nimdiha (112), Pirra Bakra (113), Mukundapur (114), Khakra Kanali (115) & Nagri (116) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 15), |  |  | VCH/001586/2021-2022 | FHTC/08 | 08/10/2021 | 08/10/2021 | TAPAS DEY | 0.24 | 0 | 0 | 0
32 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 02 (Joytunga, Kostia ), Total House Hold -423 ( Sl .No.- 17), |  |  | VCH/001567/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | UNIVERSAL CONSTRUCTION | 37.69 | 0 | 0 | 0
33 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Household survey in Rajadali (156), Sibarampur (157), Loadihi (158), Kumorebahal (159), Satsol (160), Sarga (161), Jhanti Pahari (162), Sunri Gara (163), Nadupara (177), Susne (178), Kadam Beria (179), Dhabani (180), Jalhari (181) & Harangara (185) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 3) |  |  | VCH/001584/2021-2022 | FHTC/08 | 08/10/2021 | 08/10/2021 | TAPAS DEY | 0.04 | 0 | 0 | 0
34 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Jamda (98) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 15) |  |  | VCH/001325/2021-2022 |  | 28/09/2021 | 28/09/2021 | ASOKE KUMAR SAHU | 1.61 | 0 | 0 | 0
35 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 04 nos. i.e. (Mirzapur-14, Haripur-15, Nandipara- 18 & Krishnabati- 67 ), Total House Hold - 120, |  |  | VCH/001569/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | GOUTAM GHOSH | 5.68 | 0 | 0 | 0
36 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhaban zone - A W/S Scheme under Saltora - Chhatna ( BRGF PH - I j project ) Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna Name of OHR - Dhaban Total House Hold - 144 |  |  | VCH/001573/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | TAPAS KUMBHAKAR | 9.23 | 0 | 0 | 0
37 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Extra UPVC pipe line Laying of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . Name of Mouza :- (Ramchandra pur (Part - B ), |  |  | VCH/001587/2021-2022 | FHTC/08 | 08/10/2021 | 08/10/2021 | M/S SUPRIYA CHATTERJEE | 2.76 | 0 | 0 | 0
38 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Saltora - Chhatna water supply (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. block - Chhatna ,Name of OHR - Dhaban . Total House Hold -67 nos M.B. No. 5098 |  |  | VCH/001576/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | SOUMITRA KUMAR DAS | 4.21 | 0 | 0 | 0
39 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra UPVC pipeline to Cover Ailtha, Bagneja, Uparbandh, Akurbad, Banki, Mouzas for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Cherabasta ( Zone-K) under Bankura - I, II, & Barjora Block W/S Scheme ( BRGF ph -I project) under Bankura Sadar Sub-Division of Bankura Division PHE Dte. |  |  | VCH/001408/2021-2022 | FHTC/15 | 15/09/2021 | 15/09/2021 | SUBHADIP KOLEY | 4.69 | 0 | 0 | 0
40 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Tilna (Zone - E) under Saltora - Chhatna water supply (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. block - Chhatna ,Name of OHR - Tilna . Total House Hold - 384 nos |  |  | VCH/001581/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | GOUTAM BHOWMIK | 12.64 | 0 | 0 | 0
41 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying of M.S pipeline for crossing bridge to cover Kadmaghati mouza for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Arjunpur ( Zone-N) under Bankura I II and Barjora Block ( BRGF ph -I) under Bankura Sadar Sub Division of Bankura Division PHE Dte. |  |  | VCH/001406/2021-2022 | FHTC/15 | 15/09/2021 | 15/09/2021 | GOPAL CHANDRA CHOUDHURY | 1.98 | 0 | 0 | 0
42 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra UPVC pipeline to cover Jarisa (89) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-II of Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte., |  |  | VCH/001568/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | BHATTACHARIYA CONSTRUCTION | 2.19 | 0 | 0 | 0
43 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Arkama (124) & Hazamdihi (233) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone- H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 22), |  |  | VCH/001571/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | UNITED TRADERS | 4.12 | 0 | 0 | 0
44 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra UPVC pipeline to cover parasibad & Laxmijanardanpur mouzas for construction and commissioning of FHTC in connection with jal jeevan mission (JJM) and Jal Swapna of Sonadaha ( Zone-Q) under Bankura I, II & Barjora Block W/S scheme ( BRGF Ph-I) under Bankura Sadar Sub-Division of Bankura Division PHE Dte. |  |  | VCH/001574/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | NAYAN BARDHAN | 2.75 | 0 | 0 | 0
45 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra UPVC pipeline to Cover Gaira, Arjunpur , Bahadurpur , Radhanagar, Moukura Mouzas for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Arjunpur ( Zone-N) under Bankura - I, II, & Barjora Block W/S Scheme ( BRGF ph -I project) under Bankura Sadar Sub-Division of Bankura Division PHE Dte. |  |  | VCH/001409/2021-2022 | FHTC/15 | 15/09/2021 | 15/09/2021 | SUBHADIP KOLEY | 3.8 | 0 | 0 | 0
46 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Survey work for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) & KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block- Bankura- II, Name of OHR- 1) Tilabedia, 2) Khyerkanali, No. of Mouza :- 25 nos (Mouladanga, Mithila, Jagannathbati, raghunathpur, Manoharpur, Mohanpur, Kesekol, Domanbandhi, Kumuria, Tilabedia, Kamladanga, Bambanpur, Nabada, Sibarampur, Churamonipur, Khyerkanali, Patradanga, Brindabanpur, Purba ratanpur, Belboni, Agya Nandapur, Kalaphar, Kaljuri, Muraboni & Rasiknagarpur), Total House Hold = 3931 nos., |  |  | VCH/001582/2021-2022 | FHTC/08 | 08/10/2021 | 08/10/2021 | TAPAS DEY | 1.24 | 0 | 0 | 0
47 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra HDPE pipeline to cover Buriam (112) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 11) |  |  | VCH/001030/2021-2022 |  | 16/09/2021 | 16/09/2021 | SUBHADIP KOLEY | 2.47 | 0 | 0 | 0
48 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra UPVC pipeline to cover Purnapani Chhota Tung (170) & Purnapani Bara Tung (171) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I)at Block-Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- B) |  |  | VCH/001316/2021-2022 |  | 28/09/2021 | 28/09/2021 | UNITED TRADERS | 4.95 | 0 | 0 | 0
49 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Household Survey of retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Jagadalla, Anchuri, Chaturdihi, Andharthol & Kustora. No.of Mouza :- 114 Total House Hold - 15724., |  |  | VCH/001583/2021-2022 | FHTC/08 | 08/10/2021 | 08/10/2021 | TAPAS DEY | 2.02 | 0 | 0 | 0
50 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Household survey in Golakpur (50), Bhutardihi (51), Manora (52), Bijardihi (57), Chaka Doba (58), Sitarampur (59), Bhuchu Dungri (61), Madhupur (62), Bhuakana (63), Belkanlia (67) & Bauridihi (68) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 1) |  |  | VCH/001585/2021-2022 | FHTC/08 | 08/10/2021 | 08/10/2021 | TAPAS DEY | 0.23 | 0 | 0 | 0
51 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra HDPE pipeline to cover Nachna (107) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 10) |  |  | VCH/001029/2021-2022 |  | 16/09/2021 | 16/09/2021 | PRADYUMNA KOLEY | 3.1 | 0 | 0 | 0
52 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Joykrisnapur (Zone - I) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of Mouza - PHULBERIA, |  |  | VCH/001292/2021-2022 | FHTC/02 | 02/08/2021 | 02/08/2021 | GANGADHAR MONDAL | 3.15 | 0 | 0 | 0
53 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra UPVC pipeline to Cover Cherabasta , Aina Gobindapur, Mukundapur Mouzas for construction and commissioning of FHTC in connection with jal jeevan mission and jal swapna of Cherabasta ( Zone-K) under Bankura - I, II, & Barjora Block W/S Scheme ( BRGF ph -I project) under Bankura Sadar Sub-Division of Bankura Division PHE Dte. |  |  | VCH/001405/2021-2022 | FHTC/15 | 15/09/2021 | 15/09/2021 | GOPAL CHANDRA CHOUDHURY | 4.78 | 0 | 0 | 0
54 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Telebedia (Zone - M) under bankura - l & ll & barjora block water supply (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. M.B. No. 5115 |  |  | VCH/001580/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | PARAMESWAR CHOWDHURY | 4.6 | 0 | 0 | 0
55 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra UPVC (6Kg/Sq. Cm. Water Pressure, class III) pipeline to cover Damodarpur (122), Simla (123), Rangibari (125) & Gopi Sagar (235) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone- H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 21), |  |  | VCH/001572/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | UNITED TRADERS | 4.87 | 0 | 0 | 0
56 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna , Name of OHR:- Dhaban , Total House Hold - 67 |  |  | VCH/001577/2021-2022 | FHTC/11 | 11/10/2021 | 11/10/2021 | SRIKANTA MONDAL | 3.06 | 0 | 0 | 0
57 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? in Surulia (87) & Nutandihi (93) mouzas by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 06) |  | Junior Engineer | ORD/000527/2021-2022 | 30/KSD | 16/02/2022 | 26/02/2022 | UTTAM KUMAR SINHAMAHAPATRA | 1.91 | 0 | 0 | 0
58 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying HDPE pipeline from Atchala to Jaynagar Primary School to increase pressure to cover Jaynagar (47) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-I (Hatikheda) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 03) |  | Junior Engineer | ORD/000104/2022-2023 | 207/KSD | 03/06/2022 | 23/06/2022 | M/S. AMAL KUMAR SARKAR | 3.78 | 0 | 0 | 0
59 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying HDPE pipeline to increase pressure in Madankata (176) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-L (Dhankura) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 04) |  | Junior Engineer | ORD/000106/2022-2023 | 208/KSD | 03/06/2022 | 23/06/2022 | M/S. AMAL KUMAR SARKAR | 4.62 | 0 | 0 | 0
60 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying HDPE pipeline to increase pressure in Thutasole (42) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-I (Hatikheda) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 05) |  | Junior Engineer | ORD/000123/2022-2023 | 325/KSD | 01/08/2022 | 16/08/2022 | SUBHENDU BANERJEE | 2.34 | 0 | 0 | 0
61 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Malbera (109) mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 13) |  | Junior Engineer | ORD/000693/2021-2022 | 37/KSD | 16/02/2022 | 03/03/2022 | PARTHA PRATIM CHHATAIT | 3.82 | 0 | 0 | 0
62 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Tungcharar (108) mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 15) |  | Junior Engineer | ORD/000694/2021-2022 | 39/KSD | 16/02/2022 | 03/03/2022 | PARTHA PRATIM CHHATAIT | 3.73 | 0 | 0 | 0
63 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Jamda (98) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 20) |  | Junior Engineer | ORD/000615/2021-2022 | 43/KSD | 16/02/2022 | 03/03/2022 | ASOKE KUMAR SAHU | 3.26 | 0 | 0 | 0
64 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Tungcharar (108) mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 16) |  | Junior Engineer | ORD/000695/2021-2022 | 40/KSD | 16/02/2022 | 03/03/2022 | PARTHA PRATIM CHHATAIT | 3.03 | 0 | 0 | 0
65 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Extension of distribution main by UPVC pipe (6Kg/Sq. Cm. Water Pressure, class III) along with installation of Street Stand Post etc. to cover Dudhenala & Ghatpal village under Zone-M (Purnapani) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 9) |  | Junior Engineer | ORD/000569/2021-2022 | 545/KSD | 29/06/2021 | 09/07/2021 | UNITED TRADERS | 3.53 | 0 | 0 | 0
66 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Majgerya (182) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part -B) (Sl. No. 13) |  | Junior Engineer | ORD/000326/2021-2022 | 724/KSD | 12/11/2021 | 27/11/2021 | UNITED TRADERS | 4.01 | 0 | 0 | 0
67 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Dhadkidihi (92) & Puada (94) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 5) |  | Junior Engineer | ORD/000339/2021-2022 | 648/KSD | 17/09/2021 | 02/10/2021 | BEAUTY CHATTERJEE | 4.5 | 0 | 0 | 0
68 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Baragram (86) Mouzas by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 08) |  | Junior Engineer | ORD/000384/2021-2022 | 816/KSD | 15/12/2021 | 30/12/2021 | SAMIRUDDIN KHAN | 2.6 | 0 | 0 | 0
69 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Dhadanga (97) & Haludkanali (102) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 15) |  | Junior Engineer | ORD/000334/2021-2022 | 658/KSD | 17/09/2021 | 02/10/2021 | SUBHENDU BANERJEE | 3.36 | 0 | 0 | 0
70 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Paryasa (169) & Purnapani Chhota Tung (170) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 11) |  | Junior Engineer | ORD/000324/2021-2022 | 722/KSD | 12/11/2021 | 27/11/2021 | UNITED TRADERS | 2.87 | 0 | 0 | 0
71 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Birbhandh (183) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 14) |  | Junior Engineer | ORD/000327/2021-2022 | 725/KSD | 12/11/2021 | 27/11/2021 | UNITED TRADERS | 3.56 | 0 | 0 | 0
72 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Singlahar (168) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 09) |  | Junior Engineer | ORD/000322/2021-2022 | 720/KSD | 12/11/2021 | 27/11/2021 | UNITED TRADERS | 4.97 | 0 | 0 | 0
73 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Majgerya (182) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 12) |  | Junior Engineer | ORD/000325/2021-2022 | 723/KSD | 12/11/2021 | 27/11/2021 | UNITED TRADERS | 4.9 | 0 | 0 | 0
74 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Dhadanga (97) & Haludkanali (102) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O ( Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 16) |  | Junior Engineer | ORD/000335/2021-2022 | 659/KSD | 17/09/2021 | 02/10/2021 | SUBHENDU BANERJEE | 3.48 | 0 | 0 | 0
75 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Restoration of PMGSY Concrete road at village Rudra damaged during FHTC (Functional House Hold Tap Connection) work of Zone-J (Rudra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 23) |  | Junior Engineer | ORD/000500/2021-2022 | 46/KSD | 16/02/2022 | 03/03/2022 | GOPAL CHANDRA CHOWDHURY | 3.67 | 0 | 0 | 0
76 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying HDPE pipeline to increase pressure in Surulia (87) & Jalneja (88) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000060/2022-2023 | 1684/BQA | 27/07/2022 | 26/08/2022 | SOURAV SINHA MAHAPATRA | 5.68 | 0 | 0 | 0
77 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Singlahar (168) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-M (Purnapani) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 10) |  | Junior Engineer | ORD/000323/2021-2022 | 721/KSD | 12/11/2021 | 27/11/2021 | UNITED TRADERS | 3.78 | 0 | 0 | 0
78 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 04 (Kurulia ,Majdangra , Gadardihi Balarampur, & Gobindapur(PART-B) ), Total House Hold - 155 |  |  | VCH/002516/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | AJIT KUMAR PAUL | 1.41 | 0 | 0 | 0
79 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chandpara (357) and Bamandiha (358) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 2 Nos. Total Household:- 369 Nos.' |  |  | VCH/002456/2021-2022 | FHTC/19 | 19/02/2022 | 19/02/2022 | ASHOKE KUMAR DEY | 12.3 | 0 | 0 | 0
80 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 01 nos Beldanga (Part). Total House Hold - 130' |  |  | VCH/002529/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | SHYAMAL KUMAR DAS | 0.5 | 0 | 0 | 0
81 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | laying extra HDPE pipe, line to cover sirsara mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA o f cherabasta (Zone - K) under Bankura - I & II & Barjora - Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. |  |  | VCH/003112/2021-2022 | FHTC/30 | 30/03/2022 | 30/03/2022 | GOPAL CHANDRA CHOWDHURY | 4.92 | 0 | 0 | 0
82 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 05 (Nabagram, Ailtha, Munipur, Bagneja & Upar bandh) Total House Hold - 605' |  |  | VCH/003115/2021-2022 |  | 30/03/2022 | 30/03/2022 | GOPAL CHANDRA CHOWDHURY | 6.47 | 0 | 0 | 0
83 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345) and Janapara (356) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 2 Nos. Total Household:- 359 Nos.' |  |  | VCH/002465/2021-2022 | FHTC/19 | 19/02/2022 | 19/02/2022 | BIJOY KOLEY | 13.71 | 0 | 0 | 0
84 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying of HDPE pipe line from Tajpur Rampur more to Tajpur High School of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- B) |  |  | VCH/002490/2021-2022 | FHTC/02 | 02/02/2022 | 02/02/2022 | GOPAL CHANDRA CHOWDHURY | 4.82 | 0 | 0 | 0
85 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Haroka (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haraka, No.of Mouza :- 2, ( Adhury, Gogra (part ) , Total House Hold - 439 |  |  | VCH/002503/2021-2022 | FHTC/02 | 02/02/2022 | 02/02/2022 | UNIVERSAL CONSTRUCTION | 22.73 | 0 | 0 | 0
86 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | laying extra HDPE pipe line to cover Doba (40 ) & Kheria Kocha (50) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - l (Hatikheda) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division |  |  | VCH/003037/2021-2022 | FHTC/27 | 27/03/2022 | 27/03/2022 | M/S TARUN KUMAR PATRA | 4.44 | 0 | 0 | 0
87 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 02 ( Upardihi & Kulmura.) Total House Hold - 441' |  |  | VCH/002533/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | GOPAL CHANDRA CHOWDHURY | 6.56 | 0 | 0 | 0
88 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhedua (264), Sikrabad (272), Gopalpur (273), Jiakanali (274), Pitadungri (275) Kuchiarmahar (276) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/003102/2021-2022 | FHTC/30 | 30/03/2022 | 30/03/2022 | SWAPAN KUMAR UPADHYAY | 47.33 | 0 | 0 | 0
89 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra UPVC pipe line to Dhadanga & Haludkanali mouza Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Madandihi Zone O of Khatra Hirbandh Ranibandh w/s scheme (Part -B) |  |  | VCH/003024/2021-2022 | FHTC/28 | 28/03/2022 | 28/03/2022 | SUBHENDU BANERJEE | 0.42 | 0 | 0 | 0
90 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | laying extra HDPE pipe line to cover Ambikanagar ( 19) & Jaynagar (47) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - l (Hatikheda) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, part - B |  |  | VCH/003029/2021-2022 | FHTC/27 | 27/03/2022 | 27/03/2022 | M/S TARUN KUMAR PATRA | 4.78 | 0 | 0 | 0
91 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Prayer for release fund for laboratory personal's for the month of Sep 2021 to Oct 2021 "MMKS/221/ Nov 2021 dt - 16.11.2021" |  |  | VCH/002644/2021-2022 | FHTC/10 | 10/02/2022 | 10/02/2022 | MALLABHUM MAHILA KALYAN SAMITY | 0.66 | 0 | 0 | 0
92 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of FHTC ( Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and Jal Swapna of Kanchanpur ( Zone - C) under bankura I,II & Barjora Block W/S scheme (BRGF Ph I Project ) undre Bankura Sadar Sub Division of Bankura Division , PHE Dte. , Block- Barjora , Name of the OHR- KAnchanpur (Zone-C) No of Mouzas : Khandari. |  |  | VCH/002457/2021-2022 | FHTC/19 | 19/02/2022 | 19/02/2022 | SUBHADIP KOLEY | 4.78 | 0 | 0 | 0
93 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying HDPE pipeline with in pachirdang mouzas for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Anchuri (Zone - T) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/000220/2022-2023 | FHTC/08 | 08/04/2022 | 08/04/2022 | M/S BANERJEE & BANERJEE | 6.57 | 0 | 0 | 0
94 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra HDPE pipeline to cover Baharamuri ( 91) mouza for construction and commissioing FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of (Zone - Q) (Jambedia) Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh & Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/000374/2022-2023 | FHTC/02 | 02/05/2022 | 02/05/2022 | GOPAL CHANDRA CHOWDHURY | 2.91 | 0 | 0 | 0
95 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra UPVC pipeline to cover Kadamkanali (146) mouza and Bhangahar village under Kubasol (139) mouza for construction and commissioing FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of (Zone - B) (Tilaboni) Khatra - Hirbandh - Ranibandh water supply scheme (BRGF ph - I project) at block - Hirbandh & Khatra dist - Bankura under Bankura Khatra Sub - Division of Bankura Division, PHE Dte. ( Sl .No.- 13) |  |  | VCH/000376/2022-2023 | FHTC/02 | 02/05/2022 | 02/05/2022 | SANJOY PATRA | 3.19 | 0 | 0 | 0
96 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616. |  |  | VCH/002311/2021-2022 | FHTC/20 | 20/01/2022 | 20/01/2022 | UNICON INDIA | 152 | 0 | 0 | 0
97 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying of extra HDPE pipe line to cover Tajpur Rampur mouza for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (PART- A) |  |  | VCH/002498/2021-2022 | FHTC/02 | 02/02/2022 | 02/02/2022 | GOPAL CHANDRA CHOWDHURY | 4.78 | 0 | 0 | 0
98 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying distribution system of UPVC pipe line with allied works from Near Bharakhullya air valve to BharakhullyaVillage (Purba Para) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. [ under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] |  |  | VCH/002522/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | ZAKIR HOSSAIN MONDAL | 3.6 | 0 | 0 | 0
99 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying distribution system of UPVC pipe line with allied works at BharakhullyaVillage (Paschim Para) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. [ under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] |  |  | VCH/002523/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | ZAKIR HOSSAIN MONDAL | 2.99 | 0 | 0 | 0
100 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying of HDPE pipe line from S.P.N school to Barjora Maliara Main Road , Barjojora School Danga Prymary School to Dena Bank , Suman Tewary house to Barjora Maliara Main Road & Baltu Babar Ashram of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) [under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] |  |  | VCH/002525/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | ZAKIR HOSSAIN MONDAL | 4.96 | 0 | 0 | 0
101 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Parkul (217), Mashara (218), Goaladanga (219), Chandanpur (261), Beniabaid (262) & Kankradara (263) mouzas by retrofitting Zone-IIA (Baragari) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/002446/2021-2022 | FHTC/19 | 19/02/2022 | 19/02/2022 | EARTH MOVING (INDIA) | 38.69 | 0 | 0 | 0
102 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 03, Bhangaria, Magra , Sonadaha(part), Total House Hold -138' |  |  | VCH/002526/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | TAPAN KUMAR UPADHYAY | 1.64 | 0 | 0 | 0
103 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Providing service for operation of 10 nos laboratory under Bankura Disctrict under Bankura Division, PHE Dte. for the period 01.11.2020 to 31.10.2021 |  |  | VCH/002642/2021-2022 | FHTC/10 | 10/02/2022 | 10/02/2022 | CLIFFORD FACILITY SERVICES PVT. LTD. | 6.16 | 0 | 0 | 0
104 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying of HDPE pipe line near Pakhanna village (damaged due to widening of road) of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- B) |  |  | VCH/002489/2021-2022 | FHTC/02 | 02/02/2022 | 02/02/2022 | GOPAL CHANDRA CHOWDHURY | 4.78 | 0 | 0 | 0
105 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 01 (Kanchanpur (PART) Total House Hold - 507' |  |  | VCH/002495/2021-2022 | FHTC/02 | 02/02/2022 | 02/02/2022 | GOPAL CHANDRA CHOWDHURY | 1.66 | 0 | 0 | 0
106 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 01 (Purandapur.) Total House Hold - 502' |  |  | VCH/002499/2021-2022 | FHTC/02 | 02/02/2022 | 02/02/2022 | GOPAL CHANDRA CHOWDHURY | 6.93 | 0 | 0 | 0
107 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra UPVC pipe 15 mm NB PVC to cover Dhatala, Banskkathia , Binoddihi mouza for const. and commissioning of FHTC connection with JJM and Jal Jeevan Mission of Shyampur ( Zone E ) under Saltota Chhatna W/S Scheme ( BRGF Ph -I) under Bankura Sadar Sub Division Of Bankura Division PHE Dte. |  |  | VCH/002556/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | SAIKAT CHOWDHURY | 4.94 | 0 | 0 | 0
108 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | 'Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Deuli (369) mouza by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 1 No. Total Household:- 322 Nos.' |  |  | VCH/002480/2021-2022 | FHTC/19 | 19/02/2022 | 19/02/2022 | MESSRS FREEDOM CONSTRUCTION | 10.69 | 0 | 0 | 0
109 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Prayer for release fund for laboratory personal's for the Durga puja Festival 2021 "MMKS/219/ Sep 2021 dt - 02.09.2021" |  |  | VCH/002645/2021-2022 | FHTC/10 | 10/02/2022 | 10/02/2022 | MALLABHUM MAHILA KALYAN SAMITY | 0.14 | 0 | 0 | 0
110 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Installation of 4 nos. stand alone community purification plant with provision of tube well solar power operated pumping machinery and treatment unit for removal of fluoride affected habitation of different dev. Block under Bankura district within Bankura Division , PHE Dte. |  |  | VCH/003128/2021-2022 | FHTC/31 | 31/03/2022 | 31/03/2022 | MONDAL PRECISION PRIVATE LIMITED | 21.73 | 0 | 0 | 0
111 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chakadoba (73), Lalraydihi (144), Bagjobra (145), Kadamkarali (146), Bhojda (147), Palashbani (148) & Indpur (149) mouzas by retrofitting Zone-B (Tilabani) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh & Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/000377/2022-2023 | FHTC/02 | 02/05/2022 | 02/05/2022 | SANJOY PATRA | 4.24 | 0 | 0 | 0
112 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying HDPE pipeline from dhagra post office to chaitandihi more to increase pressure to cover Dhagra (82) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of zone - I ( Hatikheda ) of Khatra - Hirbandh - Ranibandh W/S Scheme (BRGF ph - I project) under Jal Jeevan Mission (JJM) and JAL SWAPNA under Khatra Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/000583/2022-2023 |  | 22/07/2022 | 22/07/2022 | BEAUTY CHATTERJEE | 4.87 | 0 | 0 | 0
113 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying HDPE pipeline from Naba Chiyada village to Mukundapur Primary School and Dulalpur Primary School to increase pressure in Mukundapur (21) and Dulalpur (32) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-I (Hatikheda) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/000557/2022-2023 |  | 18/07/2022 | 18/07/2022 | GON ASSOCIATES | 5.44 | 0 | 0 | 0
114 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Rudra (38), Mahespur (52), Chirkun Kanali (54) & Budh Khila (60) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-J (Rudra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 20) |  |  | VCH/000752/2022-2023 | FHTC/03 | 03/08/2022 | 03/08/2022 | GOPAL CHANDRA CHOWDHURY | 2.51 | 0 | 0 | 0
115 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Supply of stationary article for office of Bankura Division, PHE Dte. for the month sep |  |  | BILL/00044/2022-2023 |  | 05/12/2022 | 05/12/2022 | BANKURA WHOLESALE COSUMERS' CO-OPERATIVE SOCITY LTD. | 0.4 | 0 | 0 | 0
116 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01(Purunia ), Total House Hold - 105 ( Sl .No.- 12 ) |  |  | VCH/002517/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | JAGADISH BANERJEE | 2.08 | 0 | 0 | 0
117 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | laying distribution system of UPVC pipe line with allied works from Oltotr to Madhavpur Village & Bahadur pur Village under under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002521/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | ZAKIR HOSSAIN MONDAL | 4.83 | 0 | 0 | 0
118 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Gadardihi (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - Gadardihi (Zone - E) . No.of Mouza :- 01 Lalbazar (PART-A) Total House Hold -141 |  |  | VCH/002581/2021-2022 | FHTC/24 | 24/02/2022 | 24/02/2022 | SUBHANKAR BANERJEE | 0.97 | 0 | 0 | 0
119 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Murakata Ghosh Para, Total House Hold -75 |  |  | VCH/002547/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | SOMA BANERJEE | 0.3 | 0 | 0 | 0
120 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora-Block ,Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 03 nos, ( Dhatala, Binodihi ,Bashkatia) Total House Hold - 394. |  |  | VCH/002549/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | SAIKAT CHOWDHURY | 5.51 | 0 | 0 | 0
121 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creacion of FHTC (Funtcional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- 01 no, (Parasia), Total House Hold -155 |  |  | VCH/002568/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | TAPAN KUMAR UPADHYAY | 2.96 | 0 | 0 | 0
122 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | laying extra HDPE pipe line to cover Dulalpur (32 ) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - l (Hatikheda) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division |  |  | VCH/003040/2021-2022 | FHTC/27 | 27/03/2022 | 27/03/2022 | M/S TARUN KUMAR PATRA | 3.91 | 0 | 0 | 0
123 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 Laxmi janardanpur (Part), Total House Hold- 70 (Sl No of Work- 08) |  |  | VCH/002460/2021-2022 | FHTC/19 | 19/02/2022 | 19/02/2022 | ZAKIR HOSSAIN MONDAL | 0.52 | 0 | 0 | 0
124 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | extra UPVC pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph- I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR- KOTALPUKUR (Zone - B), No. of Mouza :- 10 nos, (Basuda, Rajprasadpur (Part), Saldanga, Managram, Dewangrya, Numuigarya, Behargarya, Arjuni, Naykona & Radhanagar) |  |  | VCH/002637/2021-2022 | FHTC/01 | 01/02/2022 | 01/02/2022 | AMIYA KUMAR BIT | 4.36 | 0 | 0 | 0
125 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra UPVC pipe line to cover gara mouza for const. and commissioning of FHTC with Jal Jeevan mission (JJM) JAl Swapna of Jarehira ( Zone-B) under Saltora Chhatna Block W/S scheme (BRGF Ph-I ) under bankura Sadar Sub-Division of Bankura Division PHE Dte. |  |  | VCH/002476/2021-2022 | FHTC/19 | 19/02/2022 | 19/02/2022 | SK. ALAMAGIR ALAM | 3.14 | 0 | 0 | 0
126 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | 'Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Belapal (368) mouza by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 1 No. Total Household:- 310 Nos.' |  |  | VCH/002482/2021-2022 | FHTC/19 | 19/02/2022 | 19/02/2022 | MESSRS FREEDOM CONSTRUCTION | 9.63 | 0 | 0 | 0
127 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jibanpur (92) mouzas by retrofitting Zone-Q (Jambedia) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh & Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. part - A |  |  | VCH/000375/2022-2023 | FHTC/02 | 02/05/2022 | 02/05/2022 | GOPAL CHANDRA CHOWDHURY | 2.78 | 0 | 0 | 0
128 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting |  |  |  | BILL/00045/2022-2023 |  | 06/12/2022 | 06/12/2022 | PRADIP KR. BANERJEE | 0.07 | 0 | 0 | 0
129 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora-Block ,Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 01, (Patdoha) Total House Hold - 489 |  |  | VCH/002315/2021-2022 | FHTC/20 | 20/01/2022 | 20/01/2022 | SUBHANKAR BANERJEE | 27.3 | 0 | 0 | 0
130 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 02 Laxminarayanpur & Gangadar pur ), Total House Hold - 99 ( Sl .No.- 13) |  |  | VCH/002559/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | SUBHANKAR BANERJEE | 1.41 | 0 | 0 | 0
131 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Providing service for operation of 10 nos laboratory under Bankura Disctrict under Bankura Division, PHE Dte. for the period 01.11.2020 to 31.10.2021 |  |  | VCH/002643/2021-2022 | FHTC/10 | 10/02/2022 | 10/02/2022 | CLIFFORD FACILITY SERVICES PVT. LTD. | 7.37 | 0 | 0 | 0
132 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Jamda (98) & Kamardanga (99) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 4) |  |  | VCH/002527/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | EDER ALI KHAN | 4.23 | 0 | 0 | 0
133 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Debidia (86) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 16) |  |  | VCH/002511/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | GOURANGA CHATTERJEE | 0.25 | 0 | 0 | 0
134 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Debidia (86) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-D) (Sl. No.- 19) |  |  | VCH/002515/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | AJIT KUMAR PAUL | 2.09 | 0 | 0 | 0
135 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Majura (372) mouza by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 1 No. Total Household:- 547 Nos.' |  |  | VCH/002443/2021-2022 | FHTC/19 | 19/02/2022 | 19/02/2022 | TAPAN KUMAR MANDAL | 16.66 | 0 | 0 | 0
136 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | laying extra UPVC pipe, line to cover Mobarakpur , Agra, Sirasara mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA o f Cherabasta (Zone - K) under Bankura - I & II & Barjora - Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. |  |  | VCH/003113/2021-2022 | FHTC/30 | 30/03/2022 | 30/03/2022 | GOPAL CHANDRA CHOWDHURY | 4.51 | 0 | 0 | 0
137 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of EKTESWAR (Zone - I) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, No.of Mouza :- 02 (Ekteswar (PART ) & Sankardihi. Total House Hold - 452 nos. |  |  | VCH/002483/2021-2022 | FHTC/19 | 19/02/2022 | 19/02/2022 | GOUTAM BHOWMIK | 20.52 | 0 | 0 | 0
138 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying Extra UPVC Pipe Line to Cover Kulpat bankati, Gourandihi, Kesia, Ladadihi, Ramdihi, Choto kalajharia, Radharamanpur, Baro kalajuria mouzas for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone- R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002635/2021-2022 | FHTC/01 | 01/02/2022 | 01/02/2022 | PRANABANANDA TEWARI | 2.91 | 0 | 0 | 0
139 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kesia (241), Bhalaidiha (242), Kapaskhera (243) & Katar (245) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/002647/2021-2022 | FHTC/10 | 10/02/2022 | 10/02/2022 | GOUTAM BHATTACHRYYA | 13.52 | 0 | 0 | 0
140 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANDHARTHOL (Zone - V) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Andharsole, No.of Mouza :- 01 (Andharthol (PART) Total House Hold - 499 |  |  | VCH/003099/2021-2022 | FHTC/30 | 30/03/2022 | 30/03/2022 | MUNMUN UPADHYAY | 35.35 | 0 | 0 | 0
141 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra UPVC pipeline & 15 mm pipe to cover parasia mouza for const. and commissioning of FHTC connection with JJM and Jal Swapna of Jorehere ( Zone- B ) under saltora chhatna W/S Scheme ( BRGF Ph - I ) under Bankura Sadar Sub Divisiob of Bankura Division PHE Dte. |  |  | VCH/002566/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | TAPAN KUMAR UPADHYAY | 4.62 | 0 | 0 | 0
142 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | laying extra HDPE pipe line to cover Dhagra (82 ) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - l (Hatikheda) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division |  |  | VCH/003032/2021-2022 | FHTC/27 | 27/03/2022 | 27/03/2022 | M/S TARUN KUMAR PATRA | 3.95 | 0 | 0 | 0
143 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILABAID (Zone - F) of Saltora Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Tilabaid, No.of Mouza :- 1 nos, Barkona Total House Hold - 620. |  |  | VCH/002478/2021-2022 | FHTC/19 | 19/02/2022 | 19/02/2022 | SOUMITRA BHATTACHARYA | 22.02 | 0 | 0 | 0
144 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | aying extra HDPE pipe line to cover Hatikheda (20 ) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - l (Hatikheda) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division |  |  | VCH/003038/2021-2022 | FHTC/27 | 27/03/2022 | 27/03/2022 | M/S TARUN KUMAR PATRA | 2.54 | 0 | 0 | 0
145 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chatarkanali, No.of Mouza :- 06, Patna Joykrishnapur, Kunjaban, Bhedua Purusottampur, Puramauna, Sankarpur & Narrah (PART), Total House Hold - 528.' |  |  | VCH/000226/2022-2023 | FHTC/11 | 11/04/2022 | 11/04/2022 | SWAPAN KUMAR CHANDRA | 9.23 | 0 | 0 | 0
146 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra HDPE pipeline to cover Tamakhun (62) mouza Construction and commissioning of FHTC (Functional House Hold Tap Connection) in work of Zone-J (Rudra), by improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme.under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 28 |  |  | VCH/000568/2022-2023 |  | 18/07/2022 | 18/07/2022 | GOPAL CHANDRA CHOWDHURY | 4.44 | 0 | 0 | 0
147 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra HDPE pipeline to cover Rudra (38) Mahespur (52) chirkun Kanali (54) & Budh Khila (60) mouza Construction and commissioning of FHTC (Functional House Hold Tap Connection) in work of Zone-J (Rudra), by improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme.under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 20 |  |  | VCH/000569/2022-2023 |  | 18/07/2022 | 18/07/2022 | GOPAL CHANDRA CHOWDHURY | 2.51 | 0 | 0 | 0
148 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos mousas (Garerban, Ekteswar (Part, 30%), of pipe water supply scheme for Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Ekteswar, No.of Mouza :- 02 no., (Garerban, Ekteswar (Part, 30%), Total House Hold - 480 nos. |  |  | VCH/002561/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | MAKALI CONSTRUCTION | 21.47 | 0 | 0 | 0
149 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-I (Hatikheda) :- Nilgiri (12), Balarampur (13), Sareng Garh (14), Dudha Jharna (15), Paresnath (16), Kamarkuli (17), Barda (18), Ambikanagar (19), Hatikheda (20), Mukundaur (21), Chiada (22), Punnapani (23), Puddi (24), Jharia (25), Ladhan Bani (31), Dulalpur (32), Rajsol (41), Thutasol (42), Lalmoni Kocha (43), Chhatar Doba (44), Damodarpur (45), Dhananjaypur (46), Jaynagar (47), Barkola (48), Chaitandihi (49), Kheria Kocha (50), Jorakend (55), Dhagra (82) & Bansol (83) Total Mouza:- 29 Nos. Total Household - 3152 Nos. |  |  | VCH/003031/2021-2022 | FHTC/27 | 27/03/2022 | 27/03/2022 | M/S TARUN KUMAR PATRA | 11.61 | 0 | 0 | 0
150 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | laying extra HDPE pipe line to cover Rajsol (41 ) & Bansol (83) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - l (Hatikheda) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division |  |  | VCH/003035/2021-2022 | FHTC/27 | 27/03/2022 | 27/03/2022 | M/S TARUN KUMAR PATRA | 4.07 | 0 | 0 | 0
151 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying of extra HDPE pipe line to cover Tajpur Rampur mouza for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (PART- A) |  |  | VCH/002497/2021-2022 | FHTC/02 | 02/02/2022 | 02/02/2022 | GOPAL CHANDRA CHOWDHURY | 3.52 | 0 | 0 | 0
152 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Debidia (86) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 06) |  |  | VCH/002513/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | GOURANGA CHATTERJEE | 3.38 | 0 | 0 | 0
153 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | laying of HDPE pipe line from Ramkrishna Mission Ashram to Barjora Pry. School of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II)[ under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] |  |  | VCH/002580/2021-2022 | FHTC/24 | 24/02/2022 | 24/02/2022 | NAYAN BARDHAN | 4.81 | 0 | 0 | 0
154 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 02 no, ( Namabad , Gopinathdihi) Total House Hold-141 |  |  | VCH/003124/2021-2022 | FHTC/17 | 17/03/2022 | 17/03/2022 | ASHIS PAL | 2.88 | 0 | 0 | 0
155 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- Murakata ,Main road to durga mondir (Part), Total House Hold -35. |  |  | VCH/002500/2021-2022 | FHTC/02 | 02/02/2022 | 02/02/2022 | ASHIS PAL | 4.74 | 0 | 0 | 0
156 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying HDPE pipeline with in pachirdang mouzas for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Anchuri (Zone - T) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/003118/2021-2022 |  | 30/03/2022 | 30/03/2022 | M/S BANERJEE & BANERJEE | 6.57 | 0 | 0 | 0
157 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :-0 2 , Sangrampur (Part-C),Baharkhulia(part-A), Total House Hold - 124 ( Sl .No.- 10) |  |  | VCH/002558/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | SUBHANKAR BANERJEE | 1.4 | 0 | 0 | 0
158 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 13 nos. Mouzas, (( Basudevpur (Uttar) , Mandarboni, Radhanagar, Payermohan, Shushunia, Sarali, Bishanpur, Harirampur, Birsinghapur, Sonargram, Madanhati, Hatasuria, Sahebdihi) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase- I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- III) Block -Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE-III). No.of Mouza :- 13 nos (Basudevpur (Uttar), Mandarboni, Radhanagar, Payermohan, Shushunia, Sarali, Bishanpur, Harirampur, Birsinghapur, Sonargram, Madanhati, Hatasuria, Sahebdihi), Total House Hold - 2821 nos. |  |  | VCH/003101/2021-2022 | FHTC/28 | 28/03/2022 | 28/03/2022 | M/S TARUN KUMAR PATRA | 151.09 | 0 | 0 | 0
159 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte.Block - Bishnupur, Name of OHR - Narikala, No. of Mouza :- 02 nos. i.e. Layak Bandh - 13 & Chua Masina - 17, Total House Hold - 2202 |  |  | VCH/003123/2021-2022 | FHTC/24 | 24/03/2022 | 24/03/2022 | UNICON INDIA | 44.72 | 0 | 0 | 0
160 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Majuria, No. of Mouza :- 1 no. i.e. Majuria-135 , Total House Hold - 943 |  |  | VCH/002485/2021-2022 | FHTC/19 | 19/02/2022 | 19/02/2022 | GOPAL CHANDRA CHOWDHURY | 57.01 | 0 | 0 | 0
161 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - DADHIMUKHA (Zone - D), Name of Mouza :- Gopbandh, Kantabandh, Elia Narayanpur, & Rautora), Total House Hold - 51 nos. |  |  | VCH/000228/2022-2023 | FHTC/11 | 11/04/2022 | 11/04/2022 | DAUD ALI KHAN | 4.42 | 0 | 0 | 0
162 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Restoration of PMGSY concrete road at village Rudra damaged during of FHTC (Functional House Hold Tap Connection) in work of Zone-J (Rudra), by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. sl no - 23 |  |  | VCH/000558/2022-2023 |  | 18/07/2022 | 18/07/2022 | GOPAL CHANDRA CHOWDHURY | 3.67 | 0 | 0 | 0
163 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No.of Mouza :- 04 (Gourangadihi, Ledadihi, Ramdihi & Gouripur .), Total House Hold - 434 |  |  | VCH/002519/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | PARTHA PRATIM CHHATAIT | 0.09 | 0 | 0 | 0
164 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Gobarda (152) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-A (Bhuakana) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 08) |  |  | VCH/002459/2021-2022 | FHTC/19 | 19/02/2022 | 19/02/2022 | PRADYUMNA KOLEY | 2.34 | 0 | 0 | 0
165 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 04 (Matranga, Pratappur, Balarampur & Teleghra) Total House Hold - 576' |  |  | VCH/003116/2021-2022 |  | 30/03/2022 | 30/03/2022 | GOPAL CHANDRA CHOWDHURY | 12.5 | 0 | 0 | 0
166 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JOREHERA (Zone - B) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, No of Mouza:- 01 no, (Gara), Total House Hold -132 |  |  | VCH/002466/2021-2022 | FHTC/19 | 19/02/2022 | 19/02/2022 | SK. ALAMAGIR ALAM | 7.32 | 0 | 0 | 0
167 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 03 (Kantabandh ,Radharamanpur , Birsing pur ), Total House Hold -166 |  |  | VCH/002530/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | DAUD ALI KHAN | 0.82 | 0 | 0 | 0
168 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - JOYKRISHNAPUR (Zone- I), Name of mouza- Joykrishna pur Sarenga (PART- B), |  |  | VCH/002634/2021-2022 | FHTC/01 | 01/02/2022 | 01/02/2022 | M/S SUPRIYA CHATTERJEE | 3.73 | 0 | 0 | 0
169 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Assessment of performance of the scheme including actual delivery of drinking water supply scheme qulity of water being supplied and assess peoples perception of the supply of water including the level of peoples satisfaction of the piped water supply scheme for Bankura district convering 14 blocks in 1st phase founded under backward region grant fund (BRGF) under Bankura Division, PHE Dte. |  |  | VCH/003127/2021-2022 | FHTC/31 | 31/03/2022 | 31/03/2022 | SUPPORT FOR IMPROVEMENT OF GOVERNANCE & MONITORING ADVANCEMENT FOUNDATION | 9.9 | 0 | 0 | 0
170 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- Murakata Roy Para, Total House Hold -75 |  |  | VCH/002501/2021-2022 | FHTC/02 | 02/02/2022 | 02/02/2022 | ASHIS PAL | 0.22 | 0 | 0 | 0
171 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | aying extra HDPE pipe line to cover Ambikanagar ( 19) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - l (Hatikheda) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, part - A |  |  | VCH/003033/2021-2022 | FHTC/27 | 27/03/2022 | 27/03/2022 | M/S TARUN KUMAR PATRA | 4.88 | 0 | 0 | 0
172 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of FHTC , Jal jeevan mission and Jal Swapna of Kotalpur ( Zone-B ) under bankura I , II & Barjora Block W/S scheme ( BRGF Ph - I ) under Bankura Sadar Sub-Division , PHE Dte. Block Barjora , Name of OHR Kotulpur ( Zone-B ) . No.Of Mouzas: 05 ( Purakunda , Sitalpur, suratpur , Chandi & Balarampur ) Total H.Hold : 958 |  |  | VCH/002534/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | GOPAL CHANDRA CHOWDHURY | 1.78 | 0 | 0 | 0
173 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra UPVC pipe lineto cover Bhedua (264) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Gargarya Zone- IIA (Baragari) of Khatra - Hirbandh-Ranibandh water supply scheme (BRGF Ph-I) at Block- Khatra Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. part - A Sl no - 01 |  |  | VCH/002967/2021-2022 |  | 25/03/2022 | 25/03/2022 | TARINI CHARAN UPADHYAY | 4.36 | 0 | 0 | 0
174 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying distribution system of UPVC pipe line with allied works from Near Beliatore police Station air valve to Oltora Village under under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002638/2021-2022 | FHTC/01 | 01/02/2022 | 01/02/2022 | ZAKIR HOSSAIN MONDAL | 4.88 | 0 | 0 | 0
175 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Supply, Delivery and Stacking of C.I.D.F. Sluice Valve for ¿FHTC (Functional House Hold Tap Connection)¿ work of Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 02) |  |  | VCH/002640/2021-2022 | FHTC/01 | 01/02/2022 | 01/02/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.89 | 0 | 0 | 0
176 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B)) . No.of Mouza :10 (Basuda, Rajprasadpur(Part), Saldanga, Managram, Dewangrya, Numuigarya, Behargarya, Arjuni, Naykona & Radhanagar ), Total House Hold -473 |  |  | VCH/002463/2021-2022 | FHTC/19 | 19/02/2022 | 19/02/2022 | AMIYA KUMAR BIT | 6.65 | 0 | 0 | 0
177 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 02 (Akurbad & Banki, ) Total House Hold - 633' |  |  | VCH/003114/2021-2022 |  | 30/03/2022 | 30/03/2022 | GOPAL CHANDRA CHOWDHURY | 8.22 | 0 | 0 | 0
178 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra HDPE pipeline to cover Tamakhun (62) mouza Construction and commissioning of FHTC (Functional House Hold Tap Connection) in work of Zone-J (Rudra), by improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme.under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 28 |  |  | VCH/000744/2022-2023 | FHTC/03 | 03/08/2022 | 03/08/2022 | GOPAL CHANDRA CHOWDHURY | 4.44 | 0 | 0 | 0
179 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | laying extra UPVC pipe line to cover KELEBOLA mouza for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002636/2021-2022 | FHTC/01 | 01/02/2022 | 01/02/2022 | PRANABANANDA TEWARI | 2.84 | 0 | 0 | 0
180 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Debidia (86) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No.- 18) |  |  | VCH/002512/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | GOURANGA CHATTERJEE | 0.22 | 0 | 0 | 0
181 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Debidia (86) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 17) |  |  | VCH/002514/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | AJIT KUMAR PAUL | 0.22 | 0 | 0 | 0
182 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GADARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - GADARDIHI (Zone - E) . No.of Mouza :- 01 , (Gadardihi (PART-D) , Total House Hold - 154 |  |  | VCH/002518/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | TAPAS PAL | 1.38 | 0 | 0 | 0
183 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying Extra UPVC Pipe Line to Cover gouripur,bonkati,ladadihi mouzas for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone- R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002520/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | BISWARUP BOSE | 4.61 | 0 | 0 | 0
184 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Lobason Bauri Para, Total House Hold -76 |  |  | VCH/002544/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | TAPAS PAL | 0.33 | 0 | 0 | 0
185 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TALANJURI (Zone - F) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - TALANJURI (Zone - F) . No.of Mouza :- 01 (Talanjuri (PART-D) Total House Hold -117 |  |  | VCH/002582/2021-2022 | FHTC/24 | 24/02/2022 | 24/02/2022 | JAGADISH BANERJEE | 2.6 | 0 | 0 | 0
186 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Prayer for release fund for laboratory personal's for the month of Sep 2021 to Oct 2021 SBUS/03/2021-22 dt - 02.07.2021 |  |  | VCH/002646/2021-2022 | FHTC/10 | 10/02/2022 | 10/02/2022 | SONAMUKHI BIKALPA UNNAYAN SAMITY | 0.66 | 0 | 0 | 0
187 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Haroka (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Haraka, No.of Mouza :- 3, (Madhabpur , Netkamal, Karkata) , Total House Hold - 435 |  |  | VCH/002502/2021-2022 | FHTC/02 | 02/02/2022 | 02/02/2022 | UNIVERSAL CONSTRUCTION | 24.92 | 0 | 0 | 0
188 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01 , Phulberia(PART-A) , Total House Hold - 150 |  |  | VCH/002504/2021-2022 | FHTC/02 | 02/02/2022 | 02/02/2022 | GANGADHAR MONDAL | 0.62 | 0 | 0 | 0
189 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 1 ( Palsana ) , Total House Hold - 140 |  |  | VCH/002505/2021-2022 | FHTC/02 | 02/02/2022 | 02/02/2022 | GANGADHAR MONDAL | 0.78 | 0 | 0 | 0
190 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Puada (94) mouza by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/003044/2021-2022 | FHTC/27 | 27/03/2022 | 27/03/2022 | BEAUTY CHATTERJEE | 1.31 | 0 | 0 | 0
191 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 01 nos (Bonkati (Part ). Total House Hold - 132' |  |  | VCH/002531/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | PRANABANANDA TEWARI | 1.25 | 0 | 0 | 0
192 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (Zone - N) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Arjunpur. No.of Mouza :- 02 Radhanagar(part) & Maukara,) Total House Hold - 280' |  |  | VCH/002532/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | GOPAL CHANDRA CHOWDHURY | 3.84 | 0 | 0 | 0
193 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Additional UPVC Pipe Line for increasing pressure in existing distribution pipe line of Belboni mouza for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHIRKANALI (Zone - J) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002578/2021-2022 | FHTC/24 | 24/02/2022 | 24/02/2022 | M/S TARUN KUMAR PATRA | 2.08 | 0 | 0 | 0
194 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 02 (Joytunga, Kostia ), Total House Hold -423 ( Sl .No.- 17) |  |  | VCH/002639/2021-2022 | FHTC/01 | 01/02/2022 | 01/02/2022 | UNIVERSAL CONSTRUCTION | 6.26 | 0 | 0 | 0
195 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | laying extra HDPE pipe line to cover Ambikanagar ( 19) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Zone - l (Hatikheda) Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, part - B |  |  | VCH/003042/2021-2022 | FHTC/27 | 27/03/2022 | 27/03/2022 | M/S TARUN KUMAR PATRA | 4.93 | 0 | 0 | 0
196 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying of HDPE pipe line from Tajpur Rampur more to Tajpur High School of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A) |  |  | VCH/002492/2021-2022 | FHTC/02 | 02/02/2022 | 02/02/2022 | GOPAL CHANDRA CHOWDHURY | 4.84 | 0 | 0 | 0
197 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No.of Mouza :- 03 (Kulpat, Kesia,& Bhedua(Part), Total House Hold - 435' |  |  | VCH/000373/2022-2023 | FHTC/02 | 02/05/2022 | 02/05/2022 | PARTHA PRATIM CHHATAIT | 4.76 | 0 | 0 | 0
198 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Preparation of detailed project report for Augmentation of Saltora piped water supply scheme block - Saltora district under Bankura Division, PHE Dte. under Jal Swapna project zone - l |  |  | VCH/003126/2021-2022 | FHTC/31 | 31/03/2022 | 31/03/2022 | LEMNISCATE | 3.18 | 0 | 0 | 0
199 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra HDPE pipeline to cover Junbedai mouza for construction and commissioing FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Harialgora (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/000378/2022-2023 | FHTC/02 | 02/05/2022 | 02/05/2022 | M/S SUPRIYA CHATTERJEE | 3.85 | 0 | 0 | 0
200 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bena (236), Chaka (237), Kurulpahari (238) AND Baurisol (240) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/000372/2022-2023 | FHTC/02 | 02/05/2022 | 02/05/2022 | EARTH MOVING (INDIA) | 11.14 | 0 | 0 | 0
201 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra HDPE pipe lineto cover Dhanara (36 ) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- J (Rudra ) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Ranibandh under Khatra Sub - Division of Bankura Division, PHE Dte. part - A sl no - 04 |  |  | VCH/003122/2021-2022 | FHTC/29 | 29/03/2022 | 29/03/2022 | GOPAL CHANDRA CHOWDHURY | 4.62 | 0 | 0 | 0
202 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Bankati, No.of Mouza :- 02 nos, (Duyaranda, Kelebela), Total House Hold - 422.' |  |  | VCH/002560/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | SOUMITRA BOSE | 3.76 | 0 | 0 | 0
203 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra UPVC pipe line to Jantadumur mouza Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Dhankura Zone L of Khatra Hirbandh Ranibandh w/s scheme (Part -B) |  |  | VCH/003023/2021-2022 | FHTC/28 | 28/03/2022 | 28/03/2022 | SUBHENDU BANERJEE | 4.5 | 0 | 0 | 0
204 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | 'Construction and commissioning of FHTC (Functional House Hold Tap Connection)¿ in Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 1 No. Total Household:- 182 Nos.' |  |  | VCH/002524/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | GON ASSOCIATES | 9.63 | 0 | 0 | 0
205 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 nos Choto chaka, Total House Hold- 66 (Sl No of Work- 02) |  |  | VCH/002528/2021-2022 | FHTC/22 | 22/02/2022 | 22/02/2022 | KASTURI ROY | 0.19 | 0 | 0 | 0
206 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of TILNA (Zone - E) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Under Jal Dhara - 2020 Fund. Block - Chhatna, Name of OHR - Tilna, No.of Mouza :- 02 nos, (Moyragora, Jaynagar) Total House Hold - 146 |  |  | VCH/003119/2021-2022 |  | 30/03/2022 | 30/03/2022 | M/S BANERJEE & BANERJEE | 3.99 | 0 | 0 | 0
207 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 1no ,Sidhaberia (Part), Total House Hold- 145 nos. |  |  | VCH/003120/2021-2022 |  | 30/03/2022 | 30/03/2022 | TAPAS KUMBHAKAR | 9.46 | 0 | 0 | 0
208 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Extra UPVC pipe line from Soragara Village to Enayetpur village of retrofitting work for creation of FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of GODARDIHI (Zone - E) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block- Barjora, Name of OHR:- GODARDIHI (Zone - E), Name of Mouza:- Enayetpur. |  |  | VCH/002583/2021-2022 | FHTC/24 | 24/02/2022 | 24/02/2022 | SUBHANKAR BANERJEE | 4.32 | 0 | 0 | 0
209 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 02 (Bara Bendya & Khemua), Total House Hold -396 (SL.No-18) |  |  | VCH/003117/2021-2022 |  | 30/03/2022 | 30/03/2022 | UNIVERSAL CONSTRUCTION | 40.32 | 0 | 0 | 0
210 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Gagra (26), Chhota Goaldangra (45), Baragoaldangra (46), Parashia (47), Barpakhan (48), Baramurarpur (49), Jamirapara (50) & Khalaimura (51) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/002449/2021-2022 | FHTC/19 | 19/02/2022 | 19/02/2022 | ASOKE BHATTACHARYYA | 37.72 | 0 | 0 | 0
211 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra UPVC pipeline to cover Bhabanipathar (90) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 08 |  |  | VCH/002641/2021-2022 | FHTC/01 | 01/02/2022 | 01/02/2022 | TAPAN KUMAR MANDAL | 1.57 | 0 | 0 | 0
212 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Route survey Preparation of detailed project report for Agumentation of Jhantipahari piped water supply scheme zone - ll under Bankura sadar sub - Division of Bankura Division, PHE Dte. under Jal Swapna project sl no - 03 W/O NO - 903/BSD dt. 24.09.2021 |  |  | VCH/000225/2022-2023 | FHTC/08 | 08/04/2022 | 08/04/2022 | LEMNISCATE | 3.04 | 0 | 0 | 0
213 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying extra UPVC pipe line to cover Bhedua Purosatyampur, Narrah mouzas for construction & commissioning of FHTC in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/000227/2022-2023 | FHTC/11 | 11/04/2022 | 11/04/2022 | SELCO | 3.61 | 0 | 0 | 0
214 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying HDPE pipeline from Dhagra post office to Chaitandihi more to increase pressure to Dhagra (82) mouza for Construction and commissioning of FHTC (Functional House Hold Tap Connection) retrofitting Zone-I (Hatikheda) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/000760/2022-2023 | FHTC/01 | 01/08/2022 | 01/08/2022 | BEAUTY CHATTERJEE | 4.87 | 0 | 0 | 0
215 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jamda (98) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 11) |  | Junior Engineer | ORD/000104/2020-2021 | 141/KSD | 12/02/2021 | 27/02/2021 | ASOKE KUMAR SAHU | 3.84 | 0 | 0 | 58
216 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malcharar (100) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-D) (Sl. No.- 7) |  | Junior Engineer | ORD/000091/2020-2021 | 137/KSD | 12/02/2021 | 27/02/2021 | SUNIL KUMAR MANDAL | 3.65 | 0 | 0 | 0
217 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malcharar (100) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) (Sl. No.- 6) |  | Junior Engineer | ORD/000087/2020-2021 | 136/KSD | 12/02/2021 | 27/02/2021 | SUNIL KUMAR MANDAL | 3.65 | 0 | 0 | 0
218 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Malcharar (100) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 5) |  | Junior Engineer | ORD/000086/2020-2021 | 135/KSD | 12/02/2021 | 27/02/2021 | TAPAN KUMAR MANDAL | 3.69 | 0 | 0 | 0
219 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for installation and providing Internet connectivity of SITI broadband Cable Network for office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. Govt. of West Bengal. |  | Junior Engineer | ORD/000775/2021-2022 | 111/KSD | 15/03/2022 | 15/03/2023 | RAJ KUMAR BAURI | 0.01 | 0 | 0 | 80
220 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work order for Supply of 01 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for official use of Deputy Superintending Engineer, PIU, Bankura, WBDWSIP, P.H.E. Dte. for the Period from 01.03.2022 to 31.08.2022. |  | Junior Engineer | ORD/000723/2021-2022 | 54/KSD | 23/02/2022 | 26/08/2022 | TAPAN KUMAR UPADHYAY | 0.87 | 0 | 0 | 0
221 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying HDPE pipeline from Rajabandh to Dhanara to increase pressure at Dhanara (36) & Gholkuri (27) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ of Augmentation of Zone-J (Rudra) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000472/2022-2023 | 287/BQA | 13/02/2023 | 30/03/2023 | SAMIRUDDIN KHAN | 8.85 | 0 | 0 | 0
222 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Continuation Work order for Supply of 1 (One) No. Diesel/LPG/CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. under Bankura Division, P.H.E. Dte. for the period from 01/01/2023 to 30/06/2023. |  | Junior Engineer | ORD/000729/2022-2023 | 419/KSD | 27/12/2022 | 26/06/2023 | BISWAJIT LAI | 0.86 | 0 | 0 | 20
223 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | "Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Surulia (87) and Jalneja (88) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 02 Nos. Total Household - 145 Nos. " |  | Junior Engineer | ORD/000034/2021-2022 | 1781/BQA | 09/07/2021 | 08/08/2021 | UTTAM KUMAR SINHAMAHAPATRA | 9.23 | 0 | 0 | 20
224 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Continuation Work order for Supply of 1 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for Office of the Executive Engineer, Bankura Division, P.H.E. Dte. for the Period from 01/02/2022 to 31/07/2022. | Assistant Engineer |  | ORD/001046/2021-2022 | 15/KSD | 28/01/2022 | 28/07/2022 | SRIKANTA MONDAL | 0.86 | 0 | 0 | 100
225 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jamda (98) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 10) |  | Junior Engineer | ORD/000102/2020-2021 | 140/KSD | 12/02/2021 | 27/02/2021 | ASOKE KUMAR SAHU | 3.98 | 0 | 0 | 0
226 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | "Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhalkadungri (103), Gosainidihi (104), Hakimsinan (105), Tungcharar (108) & Malbera (109) mouzas under Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 05 Nos. Total Household - 853 Nos. " |  | Junior Engineer | ORD/000039/2021-2022 | 1786/BQA | 09/07/2021 | 08/08/2021 | PARTHA PRATIM CHATAIT | 56.47 | 0 | 0 | 0
227 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | "Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Birkham (110) mouza under Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 01 No. Total Household - 410 Nos. " |  | Junior Engineer | ORD/000041/2021-2022 | 1788/BQA | 09/07/2021 | 08/08/2021 | PARTHA PRATIM CHATAIT | 27.18 | 0 | 0 | 0
228 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Laying HDPE pipeline from Kankri Jharna More to Barikul Primary School to increase pressure in Barikul (179) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-L (Dhankura) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) |  | Junior Engineer | ORD/000061/2022-2023 | 1685/BQA | 27/07/2022 | 26/08/2022 | APEX ENTERPRISE | 7.7 | 0 | 0 | 0
229 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Jamda (98) Mouza for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 02) |  | Junior Engineer | ORD/000120/2022-2023 | 322/KSD | 01/08/2022 | 16/08/2022 | D. S. ENTERPRISE | 3.93 | 0 | 0 | 0
230 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Supplying laying fitting fixing of HDPE pipe line from near Banogram village Mal para to Das Para end towards Durgapur to Bankura road (Right Side) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. [under Jal Jeevan Mission ( JJM) and JAL SWAPNA Programme)] |  | Junior Engineer | ORD/000516/2022-2023 | 509/BSD | 12/07/2022 | 01/08/2022 | BEAUTY CHATTERJEE | 4.95 | 0 | 0 | 0
231 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Zone-L (Dhankura) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-L (Dhankura) :- Ghagra (115), Garra (116), Bauripal (156), Kalabani (157), Katro (158), Huang Khana (160), Punshya (161), Sindriam (162), Kankri Jharna (172), Khejur Khanma (173), Chalkigara (174), Dhoba Kacha (175), Madankata (176), Dangarda (177), Jantadumur (178), Barikul (179) & Lep-Am (180) Total Mouza:- 17 Nos. Total Household - 2137 Nos. | Assistant Engineer | Junior Engineer | ORD/000078/2021-2022 | 2411/BQA | 16/09/2021 | 31/10/2021 | ALOK ENTERPRISE | 135.35 | 0 | 0 | 0
232 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? in Bhabanipathar (90) & Malcharar (100) mouza under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 02) |  | Junior Engineer | ORD/000692/2021-2022 | 27/KSD | 16/02/2022 | 26/02/2022 | SUBHENDU BANERJEE | 3.83 | 0 | 0 | 40
233 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000008/2021-2022 | 273/BQA | 11/02/2022 | 11/02/2022 | Resource Division | 87.84 | 0 | 0 | 0
234 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-I (Part-D) , Total House Hold -170 |  | Junior Engineer | ORD/000405/2020-2021 | 863/BQA | 25/02/2021 | 27/03/2021 | NAYAN BARDHAN | 14.75 | 13.37 | 90.67 | 0
235 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Haludkanali (102) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 1) |  | Junior Engineer | ORD/000044/2020-2021 | 131/KSD | 12/02/2021 | 27/02/2021 | SUBHADIP KOLEY | 4.1 | 0 | 0 | 0
236 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Haludkanali (102) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 2) |  | Junior Engineer | ORD/000045/2020-2021 | 132/KSD | 12/02/2021 | 27/02/2021 | PRADYUMNA KOLEY | 3.92 | 0 | 0 | 0
237 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Buriam (112) & Haludkanali (113) mouzas under Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 02 Nos. Total Household - 420 Nos. |  | Junior Engineer | ORD/000042/2021-2022 | 1789/BQA | 09/07/2021 | 08/08/2021 | SUBHADIP KOLEY | 27.68 | 0 | 0 | 0
238 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Haludkanali (113) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 9) |  | Junior Engineer | ORD/000273/2021-2022 | 679/KSD | 29/09/2021 | 14/10/2021 | SUBHADIP KOLEY | 1.8 | 0 | 0 | 0
239 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Haludkanali (113) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-P (Nachna) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I)at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 05) |  | Junior Engineer | ORD/000365/2021-2022 | 813/KSD | 15/12/2021 | 30/12/2021 | PRADYUMNA KOLEY | 4.71 | 0 | 0 | 0
240 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Ghagra (115) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-L (Dhankura) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 03) |  | Junior Engineer | ORD/000364/2021-2022 | 811/KSD | 15/12/2021 | 30/12/2021 | SUBHADIP KOLEY | 5 | 0 | 0 | 0
241 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | "Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Churapathar (106) & Nachna (107) mouzas under Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 02 Nos. Total Household - 402 Nos. " |  | Junior Engineer | ORD/000040/2021-2022 | 1787/BQA | 09/07/2021 | 08/08/2021 | PRADYUMNA KOLEY | 26.36 | 24.52 | 93 | 0
242 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Wa | SM/07766 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Madandihi(101) & Malcharar (100) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No.- 5) |  | Junior Engineer | ORD/000233/2021-2022 | 675/KSD | 29/09/2021 | 14/10/2021 | SUBHADIP KOLEY | 4.36 | 0 | 0 | 0
Total | [13 empty] | 2637.72 | 62.52 | 2.37