## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Bhara-24, Bhagarara-25, Sanatanpur-26, | SM/08290 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-2) DPR no - 35. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Bhara-24 (24 out of 714), Bhagarara-25 (8 out of 71), Sanatanpur-26, Tala-27, Moula-29, House Hold - 110 | Assistant Engineer | Junior Engineer | ORD/000080/2021-2022 | 2520/BQA | 23/09/2021 | 23/10/2021 | SWAPAN KUMAR DE | 9.21 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Bhara-24, Bhagarara-25, Sanatanpur-26, | SM/08290 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-4) DPR no - 35. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Bhara-24 (120 out of 714), House Hold - 120 |  | Junior Engineer | ORD/000082/2021-2022 | 2522/BQA | 23/09/2021 | 23/10/2021 | MAYA CONSTRUCTION | 10.03 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Bhara-24, Bhagarara-25, Sanatanpur-26, | SM/08290 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with JalJeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-1) DPR no - 35. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Bhagarara-25 (63 out of 71), House Hold ¿ 63 (Sl. No. 01) |  | Junior Engineer | ORD/000124/2021-2022 | 418/VSD | 22/09/2021 | 13/10/2021 | SANU KARMAKAR | 4.61 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Bhara-24, Bhagarara-25, Sanatanpur-26, | SM/08290 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-3) DPR no - 36. Block - Bishnupur,Name of OHR - Bhara,No. of Mouza :- 1 no. i.e.Shaluka - 21(110 out of 125) House Hold - 110 |  | Junior Engineer | ORD/000085/2021-2022 | 2524/BQA | 23/09/2021 | 23/10/2021 | MRITYUNJOY HAZRA | 9.05 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Bhara-24, Bhagarara-25, Sanatanpur-26, | SM/08290 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-3) DPR no - 35. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Bhara-24 (115 out of 714), House Hold - 115 |  | Junior Engineer | ORD/000081/2021-2022 | 2521/BQA | 23/09/2021 | 23/10/2021 | PRASANTA BHUIN | 9.64 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Bhara-24, Bhagarara-25, Sanatanpur-26, | SM/08290 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-5) DPR no - 35. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Bhara- 24 ( 455 out of 714), Total House Hold - 455 |  | Junior Engineer | ORD/000083/2021-2022 | 2523/BQA | 23/09/2021 | 23/10/2021 | AMIYA KUMAR BIT | 37.98 | 2.53 | 6.66 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Bhara-24, Bhagarara-25, Sanatanpur-26, | SM/08290 | Retrofitting | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chatarkanali, No.of Mouza :- 03 nos, (Kherosol, Emokundi & Gopinathpur), Total House Hold - 527.' |  |  | VCH/002326/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | GOUTAM BHATTACHRYYA | 5.69 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Bhara-24, Bhagarara-25, Sanatanpur-26, | SM/08290 | Retrofitting | Extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B), No.of Mouza :- 05 (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gourmohanpur ), (Part-A) |  |  | VCH/002328/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | M/S TARUN KUMAR PATRA | 3.83 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Bhara-24, Bhagarara-25, Sanatanpur-26, | SM/08290 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-2) DPR no - 35. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Bhara-24 (24 out of 714), Bhagarara-25 (8 out of 71), Sanatanpur-26, Tala-27, Moula-29, House Hold - 110 |  |  | VCH/002329/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | SWAPAN KUMAR DE | 8.63 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Bhara-24, Bhagarara-25, Sanatanpur-26, | SM/08290 | Retrofitting | laying extra UPVC pipe line to cover Magra mouza for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002331/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | SK. SAHAJAHAN | 4.13 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Bhara-24, Bhagarara-25, Sanatanpur-26, | SM/08290 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of NABAGRAM (Zone - K) & CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Nabagram, Chinabari No.of Mouza :-Nabagram 10, (Gara, Buripara, Deulbera, Painsabad, Jamboni, metyala,(Bahirdya, Fulkusma, Jambede, Nabagram, Chinabari -: 4, (Bahara, Rangametia, Chhatapathor, Kunkhri Basa Total House Hold - 2598 (PART-A House Hold - 1314) |  |  | VCH/002322/2021-2022 | FHTC/20 | 20/01/2022 | 20/01/2022 | M/S TARUN KUMAR PATRA | 112.14 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Bhara-24, Bhagarara-25, Sanatanpur-26, | SM/08290 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Simlabandh (45) & Bhedua (46) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No.- 12), |  |  | VCH/002332/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | GANESH ROY | 4.99 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Bhara-24, Bhagarara-25, Sanatanpur-26, | SM/08290 | Retrofitting | laying extra UPVC pipe line to cover KELEBOLA mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002330/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | BISWARUP BOSE | 3.02 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Bhara-24, Bhagarara-25, Sanatanpur-26, | SM/08290 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Simlabandh (45) & Bhedua (46) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 13), |  |  | VCH/002333/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | GANESH ROY | 4.98 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Bhara-24, Bhagarara-25, Sanatanpur-26, | SM/08290 | Retrofitting | Extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone- B) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR- KOTALPUKUR (Zone- B), No. of Mouza:- 05 (Gururbud, Radhaballavpur, Meteia Narayanpur, Krishnabati & Gourmohanpur), (Part- B) |  |  | VCH/002327/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | M/S TARUN KUMAR PATRA | 4.81 | 0 | 0 | 0
16 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Bhara-24, Bhagarara-25, Sanatanpur-26, | SM/08290 | Retrofitting | Repairing and renovation of pipe line work in connection with Jal Jeevan Mission(JJM) of Chuamasina Zone-B and Prakash Zone-B Water Supply Scheme under Bishnupur Sub Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer |  | ORD/000644/2022-2023 | 44/VSD | 10/03/2023 | 25/03/2023 | SONU SINGH | 0.96 | 0.34 | 35.63 | 0
17 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Bhara-24, Bhagarara-25, Sanatanpur-26, | SM/08290 | Retrofitting | Creation of 'FHTC (Functional House Hold Tap Connection)' extra house hold in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamasina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Bhora, No. of Mouza :- 4 nos. i.e. Bhora- 44 ,Maula - 48,Sanatanpur - 49,Tala - 46 Total House Hold - 11 | Assistant Engineer | Junior Engineer | ORD/000273/2023-2024 | 156/VSD | 02/06/2023 | 17/06/2023 | SHYAMAPADA DEY | 0.96 | 0 | 0 | 100
18 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamosina Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Bhara-24, Bhagarara-25, Sanatanpur-26, | SM/08290 | Retrofitting | Emergent Repairing works including colour washing at Pump houses, Chlorine Room, Guard Room, Office cum Godown and Boundary Wall for Chuamosina Zone -B Piped Water Supply Scheme within Bishnupur Block under Bishnupur Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002225/2024-2025 | 595\A\VSD | 27/09/2024 | 27/10/2024 | BIT ENTERPRISE | 2.53 | 0 | 0 | 0
Total | [13 empty] | 237.2 | 2.87 | 1.21