## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos. mouzas (Patlapur-33, Hingjuri-34 & Gumut-35) of PR | SM/08293 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Prakash Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Gumut, No. of Mouza :- 3 nos. i.e. Patlapur-33, Hingjuri-34 & Gumut-35, Total House Hold - 886 |  | Junior Engineer | ORD/000137/2021-2022 | 2806/BQA | 11/11/2021 | 11/12/2021 | GOUTAM BHOWMIK | 66.34 | 4.77 | 7.19 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos. mouzas (Patlapur-33, Hingjuri-34 & Gumut-35) of PR | SM/08293 | Retrofitting | Dismantaling & reconstruction of Kastora, Singhir & Majit mouza & Cleaning Wasing the pipeline from Bhaghucha to kechka for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-I W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000153/2022-2023 | 543/BSD | 28/07/2022 | 27/08/2022 | TAPAN KUMAR MANDAL | 4.14 | 4.13 | 99.65 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos. mouzas (Patlapur-33, Hingjuri-34 & Gumut-35) of PR | SM/08293 | Retrofitting | Laying HDPE Pipe Line from Kendsayer to Harekrishnapur to Cover Harekrishnapur mouzas for construction and commissioning of ' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ANCHURI (Zone- T) OHR under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/000951/2022-2023 | FHTC/21 | 21/09/2022 | 21/09/2022 | TAPAS KUMAR HAZRA | 13.26 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos. mouzas (Patlapur-33, Hingjuri-34 & Gumut-35) of PR | SM/08293 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 04 nos (Mobarakpur, Agra, Adra & Sirsara) Total House Hold - 605' |  |  | VCH/001200/2022-2023 | FHTC/30 | 30/09/2022 | 30/09/2022 | GOPAL CHANDRA CHOWDHURY | 20.89 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos. mouzas (Patlapur-33, Hingjuri-34 & Gumut-35) of PR | SM/08293 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone - III) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - III), No. of Mouza :- 01 no., (Kastora), Total House Hold- 55 nos. |  |  | VCH/000661/2022-2023 | FHTC/27 | 27/09/2022 | 27/09/2022 | S K FAZLUL ALAM | 4.81 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos. mouzas (Patlapur-33, Hingjuri-34 & Gumut-35) of PR | SM/08293 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 |  |  | VCH/001172/2022-2023 | FHTC/27 | 27/09/2022 | 27/09/2022 | M/S TARUN KUMAR PATRA | 58.15 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos. mouzas (Patlapur-33, Hingjuri-34 & Gumut-35) of PR | SM/08293 | Retrofitting | Repairing and renovation of pipe line work in connection with Jal Jeevan Mission(JJM) of Chuamasina Zone-B and Prakash Zone-B Water Supply Scheme under Bishnupur Sub Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer |  | ORD/000644/2022-2023 | 44/VSD | 10/03/2023 | 25/03/2023 | SONU SINGH | 0.96 | 0.62 | 64.3 | 0
Total | [13 empty] | 168.56 | 9.52 | 5.65