## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Rol-07 & Chichinga-08) of Rol (Zone - A) unde | SM/08297 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Rol, No. of Mouza :- 2 nos. i.e. Rol-07 & Chichinga-08, Total House Hold - 1421 |  | Junior Engineer | ORD/000090/2021-2022 | 2504/BQA | 23/09/2021 | 23/10/2021 | CREATION CONSTRUCTION | 71.71 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Rol-07 & Chichinga-08) of Rol (Zone - A) unde | SM/08297 | Retrofitting | laying extra UPVC pipe, 15 mm NB PVC (schedule 80) / 20 mm OD HDPE (PE100, Pn16) pipe to cover Gogra, Adhury mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA o f Horaka (Zone - G) under Saltora Block Saltora-Chhatna W/S Scheme (BRGF ph - I project) ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. |  |  | VCH/002360/2021-2022 | FHTC/28 | 28/01/2022 | 28/01/2022 | UNIVERSAL CONSTRUCTION | 4.86 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Rol-07 & Chichinga-08) of Rol (Zone - A) unde | SM/08297 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-5) DPR no - 35. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Bhara- 24 ( 455 out of 714), Total House Hold - 455 |  |  | VCH/002344/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | AMIYA KUMAR BIT | 35.44 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Rol-07 & Chichinga-08) of Rol (Zone - A) unde | SM/08297 | Retrofitting | Laying Extra UPVC Pipe Line to Cover Duyaranda, Kelebela mouzas for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI(Zone- R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002356/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | SOUMITRA BOSE | 4.61 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Rol-07 & Chichinga-08) of Rol (Zone - A) unde | SM/08297 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 03 (Ladna, Mathana, Kodalia(PART-A)), Total House Hold -430 |  |  | VCH/002353/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | UNIVERSAL CONSTRUCTION | 34.9 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Rol-07 & Chichinga-08) of Rol (Zone - A) unde | SM/08297 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- By pass Pipe line Kadakuli more to Chandar main Bazar, Gosh para ,Chandar maibazar Total House Hold -20 |  |  | VCH/002355/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | BIDHAN BANERJEE | 4.84 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Rol-07 & Chichinga-08) of Rol (Zone - A) unde | SM/08297 | Retrofitting | Laying Extra UPVC Pipe Line to Cover Bonkati, Beldanga, Gajabari mouzas for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BANKATI (Zone- R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002357/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | SHYAMAL KUMAR DAS | 4.31 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Rol-07 & Chichinga-08) of Rol (Zone - A) unde | SM/08297 | Retrofitting | Retrofitting works for creacion of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of CHINABARI (Zone - H) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Chinabari, No.of Mouza :- 3, (Mantumra, Kamalpur, Patjuri Agaya ) Total House Hold - 992. |  |  | VCH/003049/2021-2022 | FHTC/27 | 27/03/2022 | 27/03/2022 | M/S TARUN KUMAR PATRA | 73.69 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Rol-07 & Chichinga-08) of Rol (Zone - A) unde | SM/08297 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- By pass Pipe line Chandar main Bazar to Chandar gram end & Baroma kali than (Chomatha), Bramhon para (Part), Chandar maibazar, Total House Hold -25. |  |  | VCH/002354/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | SOMENATH ACHARYYA | 4.8 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Rol-07 & Chichinga-08) of Rol (Zone - A) unde | SM/08297 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01, Oltara(PART-B) Total House Hold - 140 |  |  | VCH/002358/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | GANGADHAR MONDAL | 0.81 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Rol-07 & Chichinga-08) of Rol (Zone - A) unde | SM/08297 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- -01 no (Pinguri (Part-B ), Total House Hold -330 |  |  | VCH/002359/2021-2022 | FHTC/28 | 28/01/2022 | 28/01/2022 | AJIT KUMAR PAUL | 1.56 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Rol-07 & Chichinga-08) of Rol (Zone - A) unde | SM/08297 | Retrofitting | Laying of UPVC & GI pipe line to increase pressure at Chandar Mouza Water Supply Arrangement with allied works at Beliatore Jamini Roy College ground and water supply connection near PWD Sulabha Sauchalaya at Beliatore more under Beliatore W/S Scheme under Bankura Sadar Sub-Division of Bankura Division , PHE Dte. (Jal Jeevan Mission (JJM) and JAL SWAPNA Fund) |  | Junior Engineer | ORD/000332/2022-2023 | 532/BSD | 28/07/2022 | 18/08/2022 | AJIT KUMAR PAUL | 2.58 | 2.58 | 99.86 | 0
13 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Rol-07 & Chichinga-08) of Rol (Zone - A) unde | SM/08297 | Retrofitting | Supplying laying fitting fixing of HDPE pipe line connection from Air valve of Maliara Rising main(Near Ghutgoria village ) to Hindur danga village (under Baguli Mouza ) for Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000441/2022-2023 | 619/BSD | 16/08/2022 | 06/09/2022 | ASHIS KUMAR SAMANTA | 4.89 | 4.88 | 99.67 | 0
14 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Rol-07 & Chichinga-08) of Rol (Zone - A) unde | SM/08297 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Kusmi (195) & Chakrasol (196) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Baricha, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 32) |  | Junior Engineer | ORD/000648/2021-2022 | 762/BQA | 28/03/2022 | 07/04/2022 | GOPAL CHANDRA CHOWDHURY | 4.46 | 1.06 | 23.74 | 0
Total | [13 empty] | 253.45 | 8.51 | 3.36