## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Gopalnagar-05, Uttarkhanda-06, Fatika-09 & Du | SM/08298 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Rol, No. of Mouza :- 4 nos. i.e. Gopalnagar-05, Uttarkhanda-06, Fatika-09 & Durgajal-10, Total House Hold - 1240 |  | Junior Engineer | ORD/000111/2021-2022 | 2688/BQA | 26/10/2021 | 25/11/2021 | SAMRAT REALPROJECTS PRIVATE LIMITED | 62.97 | 52.4 | 83.21 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Gopalnagar-05, Uttarkhanda-06, Fatika-09 & Du | SM/08298 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000013/2022-2023 | 2036/BQA | 29/09/2022 | 29/09/2022 | Resource Division | 1.08 | 0 | 0 | 0
Total | [13 empty] | 64.05 | 52.4 | 81.81