## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos. mouzas (Gopalpur-76, Chakrabia-77, Kharra-78, Arapur-7 | SM/08299 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-2) DPR no.49 Block - Indas, Name of OHR - Birashimul, No. of Mouza :- 02 nos. i.e. Gopalpur-76 & Kharra -78 , Total House Hold - 575 (575 out of 1112) |  | Junior Engineer | ORD/000092/2021-2022 | 2529/BQA | 23/09/2021 | 23/10/2021 | JAI BHARAT COMMERCIAL CORPORATION | 42.21 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos. mouzas (Gopalpur-76, Chakrabia-77, Kharra-78, Arapur-7 | SM/08299 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - Pakhnna & its adjoining Mouzas W/S Scheme, No. of Mouza :- 01 no., (Radhakantapur), Total House Hold - 463 nos |  |  | VCH/002799/2021-2022 | FHTC/5 | 05/03/2022 | 05/03/2022 | GANESH ROY | 26.6 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos. mouzas (Gopalpur-76, Chakrabia-77, Kharra-78, Arapur-7 | SM/08299 | Retrofitting | extra HDPE pipe line from Mukuti Village Tematha more to Jorjhal Roypara of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 02 (Jorshal, Kushma), |  |  | VCH/002619/2021-2022 | FHTC/24 | 24/02/2022 | 24/02/2022 | UNIVERSAL CONSTRUCTION | 4.97 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos. mouzas (Gopalpur-76, Chakrabia-77, Kharra-78, Arapur-7 | SM/08299 | Retrofitting | Extra HDPE pipe line t to cover Valai Bhagan Village of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002613/2021-2022 | FHTC/24 | 24/02/2022 | 24/02/2022 | UNIVERSAL CONSTRUCTION | 3.72 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos. mouzas (Gopalpur-76, Chakrabia-77, Kharra-78, Arapur-7 | SM/08299 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kalipur (Zone- C) under Chatna Block of Saltora - Chatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Kalipur (Zone - C) . No.of Mouza :- 03 ( Nangla, Gidhuria, Majdihi) Total House Hold -436 |  |  | VCH/002609/2021-2022 | FHTC/24 | 24/02/2022 | 24/02/2022 | GOUTAM BHATTACHRYYA | 14.34 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos. mouzas (Gopalpur-76, Chakrabia-77, Kharra-78, Arapur-7 | SM/08299 | Retrofitting | Extra HDPE pipe line to cover Mukundrapur village of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002616/2021-2022 | FHTC/24 | 24/02/2022 | 24/02/2022 | UNIVERSAL CONSTRUCTION | 4.68 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Rol Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos. mouzas (Gopalpur-76, Chakrabia-77, Kharra-78, Arapur-7 | SM/08299 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-1) DPR no.49 Block - Indas, Name of OHR - Birashimul, No. of Mouza :- 04 nos. i.e. Chakrabia-77,Arapur-79,Banberia- 80 & Petan 81 , Total House Hold - 537 (537 out of 1112) | Assistant Engineer | Junior Engineer | ORD/000113/2021-2022 | 2691/BQA | 26/10/2021 | 25/11/2021 | I.R.CONSTRUCTION | 35.96 | 0 | 0 | 80
Total | [13 empty] | 132.47 | 0 | 0