## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Somsar, Karisunda and Betanol B PWSS executed under BRGF in Indus Block of Bankura District | SM/08310 | Retrofitting | Laying extra UPVC pipe line to cover Nutandihi Mouza for Construction and commissioning of FHTC (Functional House Hold Tap Connection) Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme |  |  | VCH/001771/2021-2022 | FHTC/28 | 28/10/2021 | 28/10/2021 | UTTAM KUMAR SINHAMAHAPATRA | 4.85 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Somsar, Karisunda and Betanol B PWSS executed under BRGF in Indus Block of Bankura District | SM/08310 | Retrofitting | Laying extra upvc pipeline to cover Shyambazar (109) mouza for Construction and commissioning of FHTC (Functional House Hold Tap Connection) by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme |  |  | VCH/001770/2021-2022 | FHTC/28 | 28/10/2021 | 28/10/2021 | BHATTACHARYYA ENTERPRISE | 4.86 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Somsar, Karisunda and Betanol B PWSS executed under BRGF in Indus Block of Bankura District | SM/08310 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-II(Part-C) , Total House Hold -172, |  |  | VCH/001767/2021-2022 | FHTC/29 | 29/10/2021 | 29/10/2021 | ASHOKE KUMAR DEY | 13.01 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Somsar, Karisunda and Betanol B PWSS executed under BRGF in Indus Block of Bankura District | SM/08310 | Retrofitting | Laying extra UPVC pipe line to cover Shyam bazar (109) mouza for Construction and commissioning of FHTC (Functional House Hold Tap Connection) by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme, |  |  | VCH/001769/2021-2022 | FHTC/28 | 28/10/2021 | 28/10/2021 | BHATTACHARYYA ENTERPRISE | 4.96 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Somsar, Karisunda and Betanol B PWSS executed under BRGF in Indus Block of Bankura District | SM/08310 | Retrofitting | Lying extra upvc pipe line to cover Jagannathpur mouza for Construction and commissioning of FHTC (Functional House Hold Tap Connection) by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme |  |  | VCH/001768/2021-2022 | FHTC/28 | 28/10/2021 | 28/10/2021 | APEX ENTERPRISE | 4.64 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Somsar, Karisunda and Betanol B PWSS executed under BRGF in Indus Block of Bankura District | SM/08310 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of RADHANAGAR W/S Scheme (Zone-I), RADHANAGAR W/S Scheme (Zone-II), PANCHAL W/S Scheme (Zone-II) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Radhanagar, No. of Mouza for RADHANAGAR W/S Scheme (Z- I) :- 4 nos. i.e. Bankati-45,Kankila-60, Rautara-61 & Dhangora-64, Total House Hold - 945 Block - Bishnupur, Name of OHR - Kakila, No. of Mouza for RADHANAGAR W/S Scheme (Zone-II) :- 5 nos. i.e. Thakurpur-85, Bhatra-86 & Joykrishnapur-87, Janta-83 & Nayer-84, Total House Hold - 1,236 Block - Sonamukhi, Name of OHR - Kanaipur, No. of Mouza for PANCHAL W/S Scheme (Zone-II) :- 7 nos. i.e. Panchal - 164,Kanaipur 159, Kute Madhabpur - 162, Krishnasayer - 156, Suksayer- 157, Aralkola - 163,, Hikimbandh-161, Total House Hold - 1616. |  |  | VCH/002311/2021-2022 | FHTC/20 | 20/01/2022 | 20/01/2022 | UNICON INDIA | 152 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Somsar, Karisunda and Betanol B PWSS executed under BRGF in Indus Block of Bankura District | SM/08310 | Retrofitting | Renovation of 200 mm dia laying rising main of HDPE pipe line from Kumardanga village to rail crossing culvert of Onda water supply scheme under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. part - C under Jal Jeevan Mission and Jal Swapan Programme sl no - 12 |  |  | VCH/002923/2021-2022 | FHTC/21 | 21/03/2022 | 21/03/2022 | ASHISH KUMAR SAMANTA | 3.06 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Somsar, Karisunda and Betanol B PWSS executed under BRGF in Indus Block of Bankura District | SM/08310 | Retrofitting | Renovation of 200 mm dia laying rising main of HDPE pipe line from Kumardanga village to rail crossing culvert of Onda water supply scheme under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. under Jal Jeevan Mission and Jal Swapan Programme sl no - 15 part - A |  |  | VCH/002922/2021-2022 | FHTC/21 | 21/03/2022 | 21/03/2022 | ASHISH KUMAR SAMANTA | 4.17 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Somsar, Karisunda and Betanol B PWSS executed under BRGF in Indus Block of Bankura District | SM/08310 | Retrofitting | Renovation of 200 mm dia laying rising main of HDPE pipe line from Kumardanga village to rail crossing culvert of Onda water supply scheme under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. part - B under Jal Jeevan Mission and Jal Swapan Programme sl no - 16 |  |  | VCH/002924/2021-2022 | FHTC/21 | 21/03/2022 | 21/03/2022 | ASHISH KUMAR SAMANTA | 4.58 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Somsar, Karisunda and Betanol B PWSS executed under BRGF in Indus Block of Bankura District | SM/08310 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Arkama (124) & Hazamdihi (233) mouzas by retrofitting Zone-H (Arkama) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000143/2020-2021 | 198/BQA | 18/01/2021 | 17/02/2021 | EARTHMOVING (INDIA) | 39.43 | 0.32 | 0.82 | 0
11 | BANKURA |  | Bankura Division | Providing Functional Household Tap Connection (FHTC) to each and every Household within command area of Somsar, Karisunda and Betanol B PWSS executed under BRGF in Indus Block of Bankura District | SM/08310 | Retrofitting | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 10 no, Khabanigoparpur (Part) Total House Hold-140 |  | Junior Engineer | ORD/000052/2021-2022 | 1931/BQA | 28/07/2021 | 27/08/2021 | SRIKANTA MONDAL | 9.31 | 6.13 | 65.81 | 20
Total | [13 empty] | 244.86 | 6.45 | 2.63