## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Resource | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Bankura District. | SM/08977 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Bankura. |  | Junior Engineer | ORD/000137/2022-2023 | 2855/RS | 20/05/2022 | 17/10/2022 | KARNAJORA AGNIBINA SEVA SAMITY | 221.62 | 221.62 | 100 | 0
2 | BANKURA |  | Resource | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Bankura District. | SM/08977 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM in the districts of the Bankura. |  |  | ORD/000828/2022-2023 | 487/RS | 07/02/2023 | 05/09/2023 | KARNAJORA AGNIBINA SEVA SAMITY | 206.33 | 206.33 | 100 | 49
Total | [13 empty] | 427.96 | 427.96 | 100