## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Madhabpur (11), Andharia (12), Kalsuli (22), Bhalkamuri (23) & Betjharia (24) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under | SM/09227 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Madhabpur (11), Andharia (12), Kalsuli (22), Bhalkamuri (23) & Betjharia (24) mouzas under Parsola, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000102/2021-2022 | 2499/BQA | 23/09/2021 | 23/10/2021 | APEX ENTERPRISE | 35.24 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Madhabpur (11), Andharia (12), Kalsuli (22), Bhalkamuri (23) & Betjharia (24) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under | SM/09227 | Retrofitting | Work Order for Household survey in Madhabpur (11), Andharia (12), Kalsuli (22), Bhalkamuri (23) & Betjharia (24) mouzas under Parsola, Zone-A to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 15) |  | Junior Engineer | ORD/000601/2021-2022 | 801/KSD | 14/12/2021 | 14/03/2022 | TAPAS DEY | 0.19 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Madhabpur (11), Andharia (12), Kalsuli (22), Bhalkamuri (23) & Betjharia (24) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under | SM/09227 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Talanjuri zone - F under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - Talanjuri (Zone - F) . No.of Mouza :- Baharkhulia Total House Hold - 104 sl no - 14 |  |  | VCH/002778/2021-2022 | FHTC/5 | 05/03/2022 | 05/03/2022 | SUBHANKAR BANERJEE | 4.95 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Madhabpur (11), Andharia (12), Kalsuli (22), Bhalkamuri (23) & Betjharia (24) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under | SM/09227 | Retrofitting | Extra UPVC pipe line for Retrofitting works for creation of FHTC (Functional House Hold Tap Connection)¿ in Talanjuri zone - F under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - Talanjuri (Zone - F) . No.of Mouza :- Baharkhulia Total House Hold - 104 sl no - 15 |  |  | VCH/002777/2021-2022 | FHTC/5 | 05/03/2022 | 05/03/2022 | SUBHANKAR BANERJEE | 4.68 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Madhabpur (11), Andharia (12), Kalsuli (22), Bhalkamuri (23) & Betjharia (24) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under | SM/09227 | Retrofitting | Providing service for operation of 10 nos laboratory under Bankura Disctrict under Bankura Division, PHE Dte. for the period 01.11.2020 to 31.10.2021 |  |  | VCH/002642/2021-2022 | FHTC/10 | 10/02/2022 | 10/02/2022 | CLIFFORD FACILITY SERVICES PVT. LTD. | 6.16 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Madhabpur (11), Andharia (12), Kalsuli (22), Bhalkamuri (23) & Betjharia (24) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under | SM/09227 | Retrofitting | laying Extra UPVC pipeline to cover Tilaboni (72) mouza for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by retrofitting Zone-B (Tilaboni) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh , Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/002773/2021-2022 | FHTC/5 | 05/03/2022 | 05/03/2022 | SANJOY PATRA | 4.71 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Madhabpur (11), Andharia (12), Kalsuli (22), Bhalkamuri (23) & Betjharia (24) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under | SM/09227 | Retrofitting | Retrofitting works for creacion of ¿FHTC (Functional House Hold Tap Connection)¿ in Talanjuri zone - F under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - Talanjuri (Zone - F) . No.of Mouza :- Talanjuri purnia Total House Hold - 43 sl no - 13 |  |  | VCH/002775/2021-2022 | FHTC/5 | 05/03/2022 | 05/03/2022 | SUBHANKAR BANERJEE | 4.18 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Madhabpur (11), Andharia (12), Kalsuli (22), Bhalkamuri (23) & Betjharia (24) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under | SM/09227 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-II(Part-B), Total House Hold -264 |  |  | VCH/002780/2021-2022 | FHTC/5 | 05/03/2022 | 05/03/2022 | ASOKE BHATTACHARYYA | 2.27 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Madhabpur (11), Andharia (12), Kalsuli (22), Bhalkamuri (23) & Betjharia (24) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under | SM/09227 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Mamra (16), Baradhara (17), Kukrakhondar (18), Gilirpahari (19), Tushkutari (20) & Hansapathar (21) mouzas under Parsola, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/000209/2022-2023 | FHTC/11 | 11/04/2022 | 11/04/2022 | GOUTAM BHATTACHRYYA | 32.23 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Madhabpur (11), Andharia (12), Kalsuli (22), Bhalkamuri (23) & Betjharia (24) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under | SM/09227 | Retrofitting | Household survey in Madhabpur, Andharia, Kalsuli, Betharia (24) mouzas under Pasola zone -A to provide of ¿FHTC (Functional House Hold Tap Connection)¿ in by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. sl no - 15 |  |  | VCH/000464/2022-2023 | FHTC/6 | 06/06/2022 | 06/06/2022 | TAPAS DEY | 0.17 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Madhabpur (11), Andharia (12), Kalsuli (22), Bhalkamuri (23) & Betjharia (24) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under | SM/09227 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Malian (23) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 11) |  | Junior Engineer | ORD/000459/2020-2021 | 118/KSD | 11/02/2021 | 03/03/2021 | SUBHANKAR BANERJEE | 4.05 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Madhabpur (11), Andharia (12), Kalsuli (22), Bhalkamuri (23) & Betjharia (24) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under | SM/09227 | Retrofitting | "Estimate for Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Birkham (110) mouza under Zone-P (Nachna) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 01 No. Total Household - 410 Nos. " |  | Junior Engineer | ORD/000041/2021-2022 | 1788/BQA | 09/07/2021 | 08/08/2021 | PARTHA PRATIM CHATAIT | 27.18 | 0 | 0 | 0
Total | [13 empty] | 126.01 | 0 | 0