## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya | SM/09229 | Retrofitting | "Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Makarkol (365) and Jukhanala (366) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 2 Nos. Total Household:- 278 Nos." |  | Junior Engineer | ORD/000119/2021-2022 | 2772/BQA | 08/11/2021 | 08/12/2021 | SRIKANTA MONDAL | 13.54 | 2.58 | 19.08 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya | SM/09229 | Retrofitting | "Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chandpara (357) and Bamandiha (358) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 2 Nos. Total Household:- 369 Nos." |  | Junior Engineer | ORD/000118/2021-2022 | 2771/BQA | 08/11/2021 | 08/12/2021 | ASHOKE KUMAR DEY | 16.6 | 4.22 | 25.45 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya | SM/09229 | Retrofitting | "Construction and commissioning of FHTC (Functional House Hold Tap Connection)¿ in Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 1 No. Total Household:- 182 Nos." |  | Junior Engineer | ORD/000120/2021-2022 | 2773/BQA | 08/11/2021 | 08/12/2021 | GON ASSOCIATES | 9.74 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya | SM/09229 | Retrofitting | " Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345) and Janapara (356) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 2 Nos. Total Household:- 359 Nos." |  | Junior Engineer | ORD/000117/2021-2022 | 2770/BQA | 08/11/2021 | 08/12/2021 | BIJOY KOLEY | 16.44 | 2.39 | 14.51 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya | SM/09229 | Retrofitting | Work Order for Household survey in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 07) |  | Junior Engineer | ORD/000589/2021-2022 | 793/KSD | 14/12/2021 | 14/03/2022 | TAPAS DEY | 0.4 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya | SM/09229 | Retrofitting | Work Order for Repairing and laying of HDPE pipe for Distribution Main along with allied works at culvert portion from Gargaria village more to Taldiha village more [damage due to done during Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte.] of Water Supply Scheme for Gargaria, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 02) |  | Junior Engineer | ORD/000131/2022-2023 | 300/KSD | 26/07/2022 | 05/08/2022 | UTTAM KUMAR SINHAMAHAPATRA | 4.93 | 4.9 | 99.4 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya | SM/09229 | Retrofitting | Work Order for Repairing and laying of UPVC pipe for Distribution Main along with allied works for culvert crossing from Debgram village to Brahamandiha village [damage due to done during Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte.] of Water Supply Scheme for Gargaria, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 33) |  | Junior Engineer | ORD/000568/2021-2022 | 763/BQA | 28/03/2022 | 12/04/2022 | UNITED TRADERS | 4.84 | 4.82 | 99.6 | 0
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya | SM/09229 | Retrofitting | Laying extra HDPE pipe line to cover Taldiha (345) & Janapara (356) mouzas construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Retrofitting of water supply scheme for Gargarya zone - A under its adjoining mouzas under Sarenga water supply scheme (BRGF ph - I project) at block - Sarenga dist - Bankura under Jal Jeevan Mission (JJM) and JAL SWAPNA of under Khatra Sadar Sub - Division of Bankura Division, PHE Dte. sl no - 09 |  |  | VCH/002943/2021-2022 | FHTC/23 | 23/03/2022 | 23/03/2022 | BIJOY KOLEY | 4.06 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya | SM/09229 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sitarampur (352) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 1 No. Total Household:- 279 Nos. |  |  | VCH/002625/2021-2022 | FHTC/24 | 24/02/2022 | 24/02/2022 | TAPAN KUMAR UPADHYAY | 11.3 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya | SM/09229 | Retrofitting | Household survey in Mamra, baradhara, kukrakhondar tusarkanti hanspatha rmouzas under Pasola zone -A to provide of ¿FHTC (Functional House Hold Tap Connection)¿ in by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. sl no - 17 |  |  | VCH/000465/2022-2023 | FHTC/6 | 06/06/2022 | 06/06/2022 | TAPAS DEY | 0.26 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya | SM/09229 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Makarkol (365) & Jukhanala (366) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 27) |  |  | VCH/001308/2022-2023 | FHTC/20 | 20/10/2022 | 20/10/2022 | SRIKANTA MONDAL | 1.12 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya | SM/09229 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sukni Basa (91), Chholagara (96) & Dhadanga (97) mouzas under Zone-O (Madandihi) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/002627/2021-2022 | FHTC/24 | 24/02/2022 | 24/02/2022 | TAPAS GHOSH | 12.24 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya | SM/09229 | Retrofitting | Household survey in Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. |  |  | VCH/000459/2022-2023 | FHTC/6 | 06/06/2022 | 06/06/2022 | TAPAS DEY | 0.38 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya | SM/09229 | Retrofitting | Laying extra UPVC pipe lineto cover Chandpara (357 ) & Bamandiha ( 258) mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of under Khatra sub - Division supply scheme for Garharya (Zone - B) under its adjoining mouzas under Sarenga water supply scheme (BRGF ph - I project) at block - Sarenga dist - Bankura under Khatra Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002932/2021-2022 | FHTC/22 | 22/03/2022 | 22/03/2022 | SANDHYA DEY | 3.02 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya | SM/09229 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Birasimul, No. of Mouza :- 4 nos. i.e. Birasimul-70, Shakrul-71, Suripuskarini-72 & Dhamur-73, Total House Hold - 1343 |  |  | VCH/002786/2021-2022 | FHTC/4 | 04/03/2022 | 04/03/2022 | M/S TARUN KUMAR PATRA | 71.95 | 0 | 0 | 0
16 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya | SM/09229 | Retrofitting | HDPE pipe Bypass line to increase pressure from Pakhnna Head work site to Tajpur village retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000266/2022-2023 | 2323/BQA | 08/12/2022 | 22/01/2023 | NAYAN BARDHAN | 49.26 | 6.68 | 13.55 | 0
17 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Taldiha (345), Janapara (356), Chandpara (357), Bamandiha (358), Makarkol (365), Jukhanala (366) & Baishpatra (367) mouzas by retrofitting of Water Supply Scheme for Gargarya | SM/09229 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Makarkol (365) & Jukhanala (366) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 27) |  | Junior Engineer | ORD/000622/2021-2022 | 757/BQA | 28/03/2022 | 07/04/2022 | SRIKANTA MONDAL | 1.08 | 0 | 0 | 0
Total | [13 empty] | 221.16 | 25.59 | 11.57