## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and it | SM/09233 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Sareskol (32), Jambani (33), Jhulisol (34) & Neturpur (44) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 05) |  | Junior Engineer | ORD/000698/2021-2022 | 97/KSD | 10/03/2022 | 20/03/2022 | SOUMITRA BHATTACHARYA | 4.72 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and it | SM/09233 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Zone-L (Dhankura) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-L (Dhankura) :- Ghagra (115), Garra (116), Bauripal (156), Kalabani (157), Katro (158), Huang Khana (160), Punshya (161), Sindriam (162), Kankri Jharna (172), Khejur Khanma (173), Chalkigara (174), Dhoba Kacha (175), Madankata (176), Dangarda (177), Jantadumur (178), Barikul (179) & Lep-Am (180)Total Mouza:- 17 Nos. Total Household - 2137 Nos. |  |  | VCH/002888/2021-2022 |  | 16/03/2022 | 16/03/2022 | ALOK ENTERPRISE | 59.06 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and it | SM/09233 | Retrofitting | Laying extra HDPE pipe line to Gangnala (230) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Phulberia & its mouzas at Block- Sarenga , Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. sl no - 01 |  |  | VCH/002768/2021-2022 | FHTC/4 | 04/03/2022 | 04/03/2022 | TARINI CHARAN UPADHYAY | 2.45 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and it | SM/09233 | Retrofitting | Household survey in Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. |  |  | VCH/000454/2022-2023 | FHTC/6 | 06/06/2022 | 06/06/2022 | TAPAS DEY | 0.3 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and it | SM/09233 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/002759/2021-2022 | FHTC/4 | 04/03/2022 | 04/03/2022 | SOUMITRA BHATTACHARYA | 43.3 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and it | SM/09233 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-2) DPR no.49Block - Indas, Name of OHR - Birashimul, No. of Mouza :- 02 nos. i.e. Gopalpur-76 & Kharra -78 , Total House Hold - 575 (575 out of 1112) |  |  | VCH/002763/2021-2022 | FHTC/4 | 04/03/2022 | 04/03/2022 | JAI BHARAT COMMERCIAL CORPORATION | 22.27 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and it | SM/09233 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur, Bamandihi, Kamla, Krishnanagar, Bhairabpur (Paschim)) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) Block -Barjora, Name of OHR -No (Direct supply), No.of Mouza :- 02 no., (Harinagara, Kamla), Total House Hold - 283 nos |  |  | VCH/002765/2021-2022 | FHTC/4 | 04/03/2022 | 04/03/2022 | SAIKAT CHOWDHURY | 16.53 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and it | SM/09233 | Retrofitting | Laying Extra 15 mm NB PVC (schedule 80) /20 mm OD HDPE Pipe to cover Paharghata, Begdiha, Hapania mouzas for construction and commissioning of ' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Hapania (Zone- d) under Saltora- Block saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002757/2021-2022 | FHTC/4 | 04/03/2022 | 04/03/2022 | SIB SANKAR CHOWDHURY | 4.96 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and it | SM/09233 | Retrofitting | HDPE pipe Bypass line to increase pressure from Pakhnna Head work site to Tajpur village retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Pakhnna & its adjoining Mouzas W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000266/2022-2023 | 2323/BQA | 08/12/2022 | 22/01/2023 | NAYAN BARDHAN | 49.26 | 10.04 | 20.37 | 0
10 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and it | SM/09233 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000098/2021-2022 | 2495/BQA | 23/09/2021 | 23/10/2021 | SOUMITRA BHATTACHARYA | 57.83 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and it | SM/09233 | Retrofitting | Laying extra HDPE pipeline, construction of different dia valve chamber & other allied works to increase pressure at Sareskol (32) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000662/2022-2023 | 507/BQA | 13/03/2023 | 27/04/2023 | UTTAM KUMAR SINHAMAHAPATRA | 4.81 | 4.74 | 98.58 | 60
12 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas by retrofitting of Water Supply Scheme for Belatikri, Zone-B and it | SM/09233 | Retrofitting | Work Order for Household survey in Sareskol (32), Jambani (33), Jhulisol (34), Chhota Amlatora (41), Baraamlatora (43) & Neturpur (44) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Belatikri, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 02) |  | Junior Engineer | ORD/000582/2021-2022 | 788/KSD | 14/12/2021 | 14/03/2022 | TAPAS DEY | 0.33 | 0 | 0 | 0
Total | [13 empty] | 265.84 | 14.77 | 5.56