## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankur | SM/09237 | Retrofitting | Work Order for Supply, Delivery and Stacking of C.I.D.F. Sluice Valve for ¿FHTC (Functional House Hold Tap Connection)¿ work of Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 02) |  | Junior Engineer | ORD/000282/2021-2022 | 702/KSD | 29/10/2021 | 18/11/2021 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.89 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankur | SM/09237 | Retrofitting | Work Order for Household survey in Parulia (91), Junkaria (92), Tentulia (93), Suknabad (94), Bhaduldoba (96), Memouli (97), Amakunda (98), Kaharan (99), Tarupur (100), Bansi (101), Ganrra (102), Sarasbakra (103), Sovarajpur (104), Sonakanda (105), Tapubaid (106), Jirabaid (107), Banskanali (108), Jharia (109), Ghoradhara (110), Machatora (111), Kamala (112), Sitarampur (113), Sushunia (114), Uparsol (115), Kansachora (116), Taldiha (117) mouzas under Pathardoba, Zone-A to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 21) |  | Junior Engineer | ORD/000678/2021-2022 | 807/KSD | 14/12/2021 | 14/03/2022 | TAPAS DEY | 1.09 | 1.09 | 100 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankur | SM/09237 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Surulia (87) & Nutandihi (93) mouzas by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 06) |  |  | VCH/000781/2022-2023 | FHTC/29 | 29/11/2022 | 29/11/2022 | UTTAM KUMAR SINHAMAHAPATRA | 1.91 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankur | SM/09237 | Retrofitting | Continuation Work Order for Supply of 1 (One) No. Diesel/LPG/CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. under Bankura Division, P.H.E. Dte. for the period from 01/03/2022 to 31/05/2022. | Assistant Engineer |  | ORD/001079/2021-2022 | 25KSD | 16/02/2022 | 04/05/2022 | PARTHA PRATIM CHHATAIT | 0.37 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankur | SM/09237 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Pathardoba, Zone-A & B and Baricha, Zone-B by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 58 Nos. Total Household:- 7982 Nos. Name of Mouzas:- Under Pathardoba, Zone-A :- Parulia (91), Junkaria (92), Tentulia (93), Suknabad (94), Bhaduldoba (96), Memouli (97), Amakunda (98), Kaharan (99), Tarupur (100), Bansi (101), Ganrra (102), Sarasbakra (103), Sovarajpur (104), Sonakanda (105), Tapubaid (106), Jirabaid (107), Banskanali (108), Jharia (109), Ghoradhara (110), Machatora (111), Kamala (112), Sitarampur (113), Sushunia (114), Uparsol (115), Kansachora (116), Taldiha (117) Under Pathardoba, Zone-B:- Baniadoba (95), Shushunia (118), Karakanali (119), Jatiakanali (120), Koldoba (121), Pathardoba (122), Balarampur (123), Masatkhal (124), Rambani (125), Dudhia Doba (126), Namadudhiadoba (127), Badageria (128), Bagakhulia (138) & Kusumdunri (139) Under Baricha, Zone-B:- Barakhulia (188), Keotdhara (189), Balarampur (190), Siuli (191), Kuchakon (192), Bandiara (193), Arra (197), Kusbakra (198), Bhutsahar (199), Barisol (200), Srirampur (201), Beoncha (202), Parasol (203), Mandalgram (183), Patharkhamar (184), Shyampu (185), Pachaparar (186) & Bamunpathri (187) |  | Junior Engineer | ORD/000025/2022-2023 | 1085/BQA | 12/05/2022 | 11/07/2022 | GOPAL CHANDRA CHOWDHURY | 482.88 | 160.87 | 33.31 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankur | SM/09237 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000018/2022-2023 | 2036/BQA | 29/09/2022 | 29/09/2022 | Resource Division | 5.11 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankur | SM/09237 | Retrofitting | Repairing and laying of HDPE pipe for Distribution Main along with allied works from Pukhuria OHR site to Pukhuria School More [damage due to done during Strengthening - Widening of Khatra-Simlapal road by PWD (Roads) Dte.] of Water Supply Scheme for Parsola, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-D) (Sl. No. 11) |  |  | VCH/001451/2022-2023 | FHTC/06 | 06/12/2022 | 06/12/2022 | EARTH MOVING (INDIA) | 4.75 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankur | SM/09237 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of INDAS W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Mirzapur, No. of Mouza :- 02 nos. i.e. (Khosbag-13 & Ausnara-24), Total House Hold - 1094 (Part-C) |  |  | VCH/001453/2022-2023 | FHTC/06 | 06/12/2022 | 06/12/2022 | M/S K.B.CONSTRUCTION | 15.31 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankur | SM/09237 | Retrofitting | Laying of extra UPVC pipe from Bhaghucha to Chuaberia to increase water pressure for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/001537/2022-2023 | FHTC/19 | 19/01/2023 | 19/01/2023 | TAPAN KUMAR MANDAL | 4.49 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankur | SM/09237 | Retrofitting | Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ and laying of HDPE pipeline under Pathardoba, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza- Sonakanda, Tapubaid & Jirabaid | Assistant Engineer | Junior Engineer | ORD/000698/2023-2024 | 2666/BQA | 22/09/2023 | 19/03/2025 | SAIKAT CHOWDHURY | 43.96 | 31.56 | 71.79 | 85
Total | [13 empty] | 563.74 | 193.51 | 34.33