## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Dhengasole (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos. mouzas (Khuliamuri-126, Harabati-127, Dhengasole-128, | SM/09238 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhengasole W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Dhengasole, No. of Mouza :- 06 nos. i.e. Khuliamuri-126, Harabati-127, Dhengasole-128, Lohari-129, Chorkundu-130 & Karra- 131, Total House Hold - 495 |  | Junior Engineer | ORD/000209/2021-2022 | 3045/BQA | 01/12/2021 | 31/12/2021 | PARTHA PRATIM CHHATAIT | 75.62 | 44.76 | 59.19 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Dhengasole (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos. mouzas (Khuliamuri-126, Harabati-127, Dhengasole-128, | SM/09238 | Retrofitting | Creation of 'FHTC (Funtional House Hold Tap Connection)' of left out Mouza, in connection with Jal Jeevan Mission of Dhengasole W/S Scheme (BRGF Ph-I) Block- Bishnupur under Bishnupur Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000545/2022-2023 | 487/BQA | 13/03/2023 | 27/04/2023 | MRITYUNJOY HAZRA | 28.13 | 21.29 | 75.68 | 95
Total | [13 empty] | 103.76 | 66.05 | 63.66