## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Benda (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos. mouzas (Benda-51, Ranikhamar-52, Gopalpur-53, Konarbandh-54 | SM/09239 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Benda W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Abantika, No. of Mouza :- 06 nos. i.e. Benda-51, Ranikhamar-52, Gopalpur-53, Konarbandh-54, Haripur-55 & Banamalipur- 56 , Total House Hold - 735 |  | Junior Engineer | ORD/000186/2021-2022 | 2689/BQA | 26/10/2021 | 25/11/2021 | SAMRAT REALPROJECTS PRIVATE LIMITED | 65.74 | 26.19 | 39.84 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Benda (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos. mouzas (Benda-51, Ranikhamar-52, Gopalpur-53, Konarbandh-54 | SM/09239 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000017/2021-2022 | 473/BQA | 04/03/2022 | 04/03/2022 | Resource Division | 4.53 | 0 | 0 | 0
Total | [13 empty] | 70.26 | 26.19 | 37.27