## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Kuldiha, Napra, Bagulia) of MALIARA (Zone - A) under Bankura | SM/09304 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :-01(Kuldiha ), Total House Hold -233 |  | Junior Engineer | ORD/000504/2020-2021 | 856/BQA | 25/02/2021 | 27/03/2021 | TAPAS PAL | 19.63 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Kuldiha, Napra, Bagulia) of MALIARA (Zone - A) under Bankura | SM/09304 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :-02( Napra(Part-B) , Bagulia ), Total House Hold -323 |  | Junior Engineer | ORD/000462/2020-2021 | 858/BQA | 25/02/2021 | 27/03/2021 | SARKAR CONSTRUCTION | 27.85 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Kuldiha, Napra, Bagulia) of MALIARA (Zone - A) under Bankura | SM/09304 | Retrofitting | Parallel pipe laying of HDPE pipe from Pinguri Village Hunuman mondir to Khatal Bagan Village for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Maliara (Zone -A)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000313/2022-2023 | 554/BSD | 29/07/2022 | 28/08/2022 | SUBHADIP KOLEY | 4.94 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Kuldiha, Napra, Bagulia) of MALIARA (Zone - A) under Bankura | SM/09304 | Retrofitting | Parallel pipe laying of HDPE pipe from Khatal Bagan Village to Kuldiha ground for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Maliara (Zone -A)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000316/2022-2023 | 555/BSD | 29/07/2022 | 28/08/2022 | SUBHANKAR BANERJEE | 4.94 | 4.93 | 99.81 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Kuldiha, Napra, Bagulia) of MALIARA (Zone - A) under Bankura | SM/09304 | Retrofitting | Supplying laying fitting fixing of HDPE pipe line connection from Hindur danga village Main road to Baguli ,Lohara boni & Molboni village ( under Baguli Mouza ) for Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000464/2022-2023 | 620/BSD | 16/08/2022 | 06/09/2022 | ASHOKE KUMAR DEY | 4.86 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Kuldiha, Napra, Bagulia) of MALIARA (Zone - A) under Bankura | SM/09304 | Retrofitting | Parallel pipe laying of HDPE pipe from Kuldiha ground to Kuldiha Village for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Maliara (Zone -A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000317/2022-2023 | 556/BSD | 29/07/2022 | 28/08/2022 | SUBHANKAR BANERJEE | 3.72 | 3.7 | 99.61 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Kuldiha, Napra, Bagulia) of MALIARA (Zone - A) under Bankura | SM/09304 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Amrul Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Heyatnagar, No. of Mouza :- 8 nos. i.e. Srikara-31, Padua-11, Adpara Kumrul-12, Sripur-26, Heyatnagar-27, Maheshpur-28, Meral-29 & Chakmeral-30, Total House Hold - 2465 |  |  | VCH/002445/2021-2022 | FHTC/18 | 18/02/2022 | 18/02/2022 | JAYANTA KUMAR MONDAL | 140.85 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Kuldiha, Napra, Bagulia) of MALIARA (Zone - A) under Bankura | SM/09304 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE - I W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma zone -I, Name of Mouza:-- 2 no., (Barasali, Kukirakur), Total House Hold - 332 nos. |  |  | VCH/002827/2021-2022 | FHTC/9 | 09/03/2022 | 09/03/2022 | TAPAS KUMBHAKAR | 16.02 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Kuldiha, Napra, Bagulia) of MALIARA (Zone - A) under Bankura | SM/09304 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Pukhuria (10) mouzas under Parsola, Zone-B by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/002830/2021-2022 | FHTC/9 | 09/03/2022 | 09/03/2022 | TAPAN KUMAR MANDAL | 13.34 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Kuldiha, Napra, Bagulia) of MALIARA (Zone - A) under Bankura | SM/09304 | Retrofitting | Laying Extra UPVC pipe line to cover Barasali, Kukurakur mouza for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma zone - l water supply scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. sl no - 17 |  |  | VCH/002828/2021-2022 | FHTC/9 | 09/03/2022 | 09/03/2022 | TAPAS KUMBHAKAR | 3.83 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 03 Nos. Mouzas (Kuldiha, Napra, Bagulia) of MALIARA (Zone - A) under Bankura | SM/09304 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Amrul Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Amrul, No. of Mouza :- 10 nos. i.e. Gangabati-32, Maurui-33, Bhagabanbati-34, Nunduri-35, Bajitpur-36, Bangalchwak-37, Keneti-50, Panchkona-51, Amrul-52 & Abdulpur-53, Total House Hold - 2627 |  |  | VCH/002441/2021-2022 | FHTC/18 | 18/02/2022 | 18/02/2022 | KHAN ENTERPRISE | 145.4 | 0 | 0 | 0
Total | [13 empty] | 385.38 | 8.63 | 2.24