## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorthol, Asurabad, Kendbede, Jamthol, Bhelani) of DHABAN (Zo | SM/09305 | Retrofitting | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 1no Jamthol (PART) Total House Hold- 140 |  | Junior Engineer | ORD/000204/2020-2021 | 989/BQA | 26/02/2021 | 28/03/2021 | MRITYUNJOY HAZRA | 9.83 | 0.68 | 6.95 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorthol, Asurabad, Kendbede, Jamthol, Bhelani) of DHABAN (Zo | SM/09305 | Retrofitting | Retrofitting works for creacion of extra 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No. of Mouza :- 01 no., Jorthol (Part), Total House Hold- 75 nos. |  | Junior Engineer | ORD/000548/2021-2022 | 54/BSD | 07/01/2022 | 22/01/2022 | M/S T.P. HAZRA & SONS | 4.91 | 4.91 | 99.98 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorthol, Asurabad, Kendbede, Jamthol, Bhelani) of DHABAN (Zo | SM/09305 | Retrofitting | Bridge crossing at Bhilani by 250mm dia MS Pipe & other allied works at Dhaban under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. (Part-B) |  | Junior Engineer | ORD/000198/2022-2023 | 262/KSD | 12/07/2022 | 27/07/2022 | SIB SANKAR CHOWDHURY | 3.86 | 3.85 | 99.79 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorthol, Asurabad, Kendbede, Jamthol, Bhelani) of DHABAN (Zo | SM/09305 | Retrofitting | Crossing of Road by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Laying of MS Distribution Main for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte (Part -A) Location of site: Bhilani Bridge (Right side) |  | Junior Engineer | ORD/000197/2022-2023 | 261/KSD | 12/07/2022 | 27/07/2022 | SIB SANKAR CHOWDHURY | 4.11 | 4.11 | 100 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorthol, Asurabad, Kendbede, Jamthol, Bhelani) of DHABAN (Zo | SM/09305 | Retrofitting | Crossing of Road by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Laying of MS Distribution Main for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte (Part -B) Location of site: Bhilani Bridge (Left side) . |  | Junior Engineer | ORD/000199/2022-2023 | 258/KSD | 12/07/2022 | 27/07/2022 | SIB SANKAR CHOWDHURY | 4.11 | 4.11 | 100 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorthol, Asurabad, Kendbede, Jamthol, Bhelani) of DHABAN (Zo | SM/09305 | Retrofitting | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 1no Jorthal (PART) Total House Hold- 140 |  |  | VCH/000656/2022-2023 | FHTC/21 | 21/07/2022 | 21/07/2022 | SAIKAT CHOWDHURY | 1.68 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorthol, Asurabad, Kendbede, Jamthol, Bhelani) of DHABAN (Zo | SM/09305 | Retrofitting | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorthol, Asurabad, Kendbede, Jamthol, Bhelani) of DHABAN (Zone - A) under Saltora- Chhatna W/S Scheme (BRGF Ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte |  |  | VCH/002385/2021-2022 | FHTC/21 | 21/02/2022 | 21/02/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 40 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorthol, Asurabad, Kendbede, Jamthol, Bhelani) of DHABAN (Zo | SM/09305 | Retrofitting | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 1no Jorthol (PART) ,Bhelani (PART) Total House Hold- 140 |  |  | VCH/000652/2022-2023 | FHTC/21 | 21/07/2022 | 21/07/2022 | TAPAS KUMAR HAZRA | 1.68 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorthol, Asurabad, Kendbede, Jamthol, Bhelani) of DHABAN (Zo | SM/09305 | Retrofitting | Retrofitting works for creation of extra 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No.of Mouza :- 01 no., Taljoria (Part), Total House Hold- 35 nos. |  | Junior Engineer | ORD/000487/2021-2022 | 55/BSD | 07/01/2022 | 22/01/2022 | TAPAS KUMAR HAZRA | 4.29 | 0 | 0 | 40
10 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorthol, Asurabad, Kendbede, Jamthol, Bhelani) of DHABAN (Zo | SM/09305 | Retrofitting | Retrofitting works for creacion of extra 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban. No. of Mouza :- 01 no., Jorthol (Part), Total House Hold- 75 nos. |  | Junior Engineer | ORD/000478/2021-2022 | 54/BSD | 07/01/2022 | 22/01/2022 | M/S T.P. HAZRA & SONS | 4.91 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorthol, Asurabad, Kendbede, Jamthol, Bhelani) of DHABAN (Zo | SM/09305 | Retrofitting | Retrofitting works for creation of extra 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of DHABAN (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Dhaban, No.of Mouza :- 01 no., Jorethol (Part), Total House Hold- 38 nos. | Assistant Engineer | Junior Engineer | ORD/000990/2022-2023 | 345/KSD | 16/08/2022 | 05/09/2022 | TAPAS KUMAR HAZRA | 1.61 | 0.82 | 51.03 | 100
12 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorthol, Asurabad, Kendbede, Jamthol, Bhelani) of DHABAN (Zo | SM/09305 | Retrofitting | Work Order for Laying Extra UPVC Pipe Line to Cover Jamthol mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Dhaban (Zone- A) under Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. (Sl. No. 10) | Assistant Engineer | Junior Engineer | ORD/000162/2023-2024 | 107/KSD | 28/04/2023 | 28/05/2023 | TAPAS KUMAR HAZRA | 0.84 | 0 | 0 | 100
13 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorthol, Asurabad, Kendbede, Jamthol, Bhelani) of DHABAN (Zo | SM/09305 | Retrofitting | Work Order for Household survey of retrofitting works of creation of ¿FHTC (Functional House Hold Tap Connection)¿ in connection with Jal Jeevan Mission (JJM) and Jal Swapna under Saltora-Chhatna W/S Scheme (BRGF Ph-I Project) under Bankura Division of Bankura Division, P.H.E. Dte. Block- Chhatna, Name of OHR- Dhaban, Hapania, Jorehira, Kalipur, Tilna, Chinabari, Bandagal & Nabagram, No. of Mouza- 97 Nos., Total Household- 1868 Nos. (Sl. No. 02) | Assistant Engineer | Junior Engineer | ORD/000879/2022-2023 | 38/KSD | 13/03/2023 | 12/04/2023 | TAPAS DEY | 0.62 | 0.62 | 100 | 100
14 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorthol, Asurabad, Kendbede, Jamthol, Bhelani) of DHABAN (Zo | SM/09305 | Retrofitting | Work Order for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, No. of Mouza :- Jamthol, Total House Hold :-7 nos. | Assistant Engineer | Junior Engineer | ORD/000164/2023-2024 | 109/KSD | 28/04/2023 | 28/05/2023 | TAPAS KUMAR HAZRA | 0.45 | 0.42 | 92.94 | 100
15 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofittings works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas (Jorthol, Asurabad, Kendbede, Jamthol, Bhelani) of DHABAN (Zo | SM/09305 | Retrofitting | Design Making & Erection of Disply board using Logo and tag line of Jal Jeevan Mission to the place at different work sites Kendbede (05), Bhelani (14), Dhaban (22), Sidhaberia (25) & Kuladabar (09) of Swajal Gram/Har Ghar Jal Villages for awarness generation among the pepole of Bankura Sadar Sub- Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001058/2023-2024 | 1174/BSD | 22/11/2023 | 07/12/2023 | TAPAS DEY | 0.69 | 0.67 | 96.91 | 100
Total | [13 empty] | 83.6 | 20.19 | 24.15