## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 nos. Mouzas (Shirpurnama, Baiarampur, Digit, Salbeda, Tetularakh, saburbandh, | SM/09314 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Saburbadh, Name of Mouza:-- 01 no., (Saburbandh), Total House Hold - 428 nos. |  | Junior Engineer | ORD/000157/2021-2022 | 2836/BQA | 16/11/2021 | 16/12/2021 | RUFIKUL MONDAL | 20.41 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 nos. Mouzas (Shirpurnama, Baiarampur, Digit, Salbeda, Tetularakh, saburbandh, | SM/09314 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora . Name of OHR- Saburbadh . Name of Mouza:-- 01 no., (Tetularakh), Total House Hold - 348 nos. |  | Junior Engineer | ORD/000190/2021-2022 | 2991/BQA | 25/11/2021 | 25/12/2021 | N H ENTERPRISE | 16.12 | 16.11 | 99.96 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 nos. Mouzas (Shirpurnama, Baiarampur, Digit, Salbeda, Tetularakh, saburbandh, | SM/09314 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Saburbandh under Saburbandh W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Saburbandh No. of Mouza :- 01 nos Saburbandh (Part), Total House Hold- 40 nos. |  | Junior Engineer | ORD/000474/2021-2022 | 207/BSD | 11/03/2022 | 21/03/2022 | RUFIKUL MONDAL | 3.51 | 2.49 | 70.74 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 nos. Mouzas (Shirpurnama, Baiarampur, Digit, Salbeda, Tetularakh, saburbandh, | SM/09314 | Retrofitting | Laying extra UPVC pipe line to cover Digit mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A) |  | Junior Engineer | ORD/000124/2022-2023 | 466/BSD | 06/06/2022 | 21/06/2022 | TAPAN KUMAR UPADHYAY | 4.54 | 4.42 | 97.27 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 nos. Mouzas (Shirpurnama, Baiarampur, Digit, Salbeda, Tetularakh, saburbandh, | SM/09314 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Saburbandh under Saburbandh W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Saburbandh No.of Mouza :- 01 nos Saburbandh Total House Hold- 12 nos. |  | Junior Engineer | ORD/000263/2022-2023 | 605/BSD | 16/08/2022 | 06/09/2022 | MOHAMMAD HASAN KHAN | 4.52 | 4.16 | 92.14 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 nos. Mouzas (Shirpurnama, Baiarampur, Digit, Salbeda, Tetularakh, saburbandh, | SM/09314 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Saburbadh, Name of Mouza:- 05 nos, (Rajpara, keshar kundi, krishnapur, Digit, Salbeda), Total House Hold - 340 nos. |  |  | VCH/000214/2022-2023 | FHTC/11 | 11/04/2022 | 11/04/2022 | TAPAN KUMAR UPADHYAY | 7.59 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 nos. Mouzas (Shirpurnama, Baiarampur, Digit, Salbeda, Tetularakh, saburbandh, | SM/09314 | Retrofitting | Laying extra UPVC pipeline to cover Tetularakh mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/000654/2022-2023 | FHTC/21 | 21/07/2022 | 21/07/2022 | N H ENTERPRISE | 4.03 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 nos. Mouzas (Shirpurnama, Baiarampur, Digit, Salbeda, Tetularakh, saburbandh, | SM/09314 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of HAPANIA (Zone - D) of Chhatna Block under Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Hapania, No.of Mouza :- 07 (Siulibona, Metyala, Khayerbani, Patharghata, Hapania, Goyaldanga, Bagdiha) Total House Hold - 1131 |  |  | VCH/002726/2021-2022 | FHTC/3 | 03/03/2022 | 03/03/2022 | SIB SANKAR CHOWDHURY | 47.08 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 nos. Mouzas (Shirpurnama, Baiarampur, Digit, Salbeda, Tetularakh, saburbandh, | SM/09314 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Saburbadh, Name of Mouza:- 05 nos, (Rajpara, keshar kundi, krishnapur, Digit, Salbeda), Total House Hold - 340 nos. |  | Junior Engineer | ORD/000158/2021-2022 | 2837/BQA | 16/11/2021 | 16/12/2021 | TAPAN KUMAR UPADHYAY | 16.4 | 8.81 | 53.73 | 0
10 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 nos. Mouzas (Shirpurnama, Baiarampur, Digit, Salbeda, Tetularakh, saburbandh, | SM/09314 | Retrofitting | Laying extra UPVC pipe line to cover Dighit & Salbeda mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- B) |  | Junior Engineer | ORD/000126/2022-2023 | 467/BSD | 06/06/2022 | 21/06/2022 | TAPAN KUMAR UPADHYAY | 3.55 | 3.38 | 95.18 | 0
11 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 nos. Mouzas (Shirpurnama, Baiarampur, Digit, Salbeda, Tetularakh, saburbandh, | SM/09314 | Retrofitting | Laying extra UPVC pipe line to cover Krishnapur & Salbeda mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- C) |  | Junior Engineer | ORD/000128/2022-2023 | 468/BSD | 06/06/2022 | 21/06/2022 | TAPAN KUMAR UPADHYAY | 3.83 | 3.8 | 99.35 | 0
12 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 nos. Mouzas (Shirpurnama, Baiarampur, Digit, Salbeda, Tetularakh, saburbandh, | SM/09314 | Retrofitting | Repairing & relaying of UPVC Pipeline at Chatarkanali, Banspitali, Sirpuranama & tentularakha of Saburbandh Water Supply Scheme under Bankura Sadar Sub-Division, of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000343/2022-2023 | 540/BSD | 28/07/2022 | 27/08/2022 | BROTIN UPADHYAY | 4.08 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 nos. Mouzas (Shirpurnama, Baiarampur, Digit, Salbeda, Tetularakh, saburbandh, | SM/09314 | Retrofitting | Laying Extra HDPE Pipe Line from keshar kundi to Rajpura village to increase water pressure for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000503/2022-2023 | 613/BSD | 16/08/2022 | 06/09/2022 | TAPAN KUMAR UPADHYAY | 3.39 | 3.39 | 99.92 | 0
14 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 nos. Mouzas (Shirpurnama, Baiarampur, Digit, Salbeda, Tetularakh, saburbandh, | SM/09314 | Retrofitting | Laying Extra HDPE Pipe Line to Cover Rajpara, keshar kundi mouza & Dismantling, reconstruction of concrete for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000504/2022-2023 | 611/BSD | 16/08/2022 | 06/09/2022 | TAPAN KUMAR UPADHYAY | 4.97 | 4.96 | 99.89 | 0
15 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 nos. Mouzas (Shirpurnama, Baiarampur, Digit, Salbeda, Tetularakh, saburbandh, | SM/09314 | Retrofitting | Laying Extra HDPE Pipe Line from Saburbandh pump house to keshar kundi village to increase water pressure for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000663/2022-2023 | 612/BSD | 16/08/2022 | 06/09/2022 | M/S S.M ENTERPRISE | 4.99 | 4.98 | 99.98 | 0
16 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 nos. Mouzas (Shirpurnama, Baiarampur, Digit, Salbeda, Tetularakh, saburbandh, | SM/09314 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Saburbadh, Name of Mouza:-- 02 no., (Shirpurnama, Baiarampur), Total House Hold - 1059 nos. | Assistant Engineer | Junior Engineer | ORD/000178/2021-2022 | 2908/BQA | 23/11/2021 | 23/12/2021 | DAS & CHAKRABORTY | 44.89 | 38.98 | 86.84 | 100
17 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 11 nos. Mouzas (Shirpurnama, Baiarampur, Digit, Salbeda, Tetularakh, saburbandh, | SM/09314 | Retrofitting | Survey work for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Saburbadh, Name of Mouza:-- 11 nos, (Shirpurnama, Baiarampur, Digit, Salbeda, Tetularakh, Saburbandh, Keshar Kundi, Rajpara, Krishnapur, Iswada, Narayanpur), Total House Hold - 2464 nos. |  | Junior Engineer | ORD/000878/2021-2022 | 67/BSD | 14/01/2022 | 14/04/2022 | TAPAS DEY | 0.82 | 0.74 | 90.22 | 99
Total | [13 empty] | 194.7 | 96.23 | 49.42