## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mousas (Garerban, Ekteswar (Part, 30%), Shyamdaspur, Bhadul, Bhutsahar, Bejg | SM/09315 | Retrofitting | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos mousas (Garerban, Ekteswar (Part, 30%), of pipe water supply scheme for Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Ekteswar, No.of Mouza :- 02 no., (Garerban, Ekteswar (Part, 30%), Total House Hold - 480 nos. | Assistant Engineer | Junior Engineer | ORD/000187/2021-2022 | 2988/BQA | 25/11/2021 | 25/12/2021 | MAKALI CONSTRUCTION | 21.48 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mousas (Garerban, Ekteswar (Part, 30%), Shyamdaspur, Bhadul, Bhutsahar, Bejg | SM/09315 | Retrofitting | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 01 nos mousa (Sanabandh), of pipe water supply scheme for Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Ekteswar (II), No.of Mouza :- 01 no., (Sanabandh) Total House Hold - 937 nos. | Assistant Engineer | Junior Engineer | ORD/000188/2021-2022 | 2989/BQA | 25/11/2021 | 25/12/2021 | NEW STAR CONSTRUCTION | 45.11 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mousas (Garerban, Ekteswar (Part, 30%), Shyamdaspur, Bhadul, Bhutsahar, Bejg | SM/09315 | Retrofitting | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos mousa (Bhadul, Bhutsahar & Bejgram) of pipe water supply scheme for Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Ekteswar (II), No.of Mouza :- 03 nos, (Bhadul, Bhutsahar & Bejgram), Total House Hold - 1166 nos. | Assistant Engineer | Junior Engineer | ORD/000127/2021-2022 | 2792/BQA | 11/11/2021 | 11/12/2021 | ASOKE BHATTACHARYYA | 58.88 | 47.29 | 80.31 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mousas (Garerban, Ekteswar (Part, 30%), Shyamdaspur, Bhadul, Bhutsahar, Bejg | SM/09315 | Retrofitting | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 01 nos mousa (Shyamdaspur), of pipe water supply scheme for Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Ekteswar (II), No.of Mouza :- 01 no., (Shyamdaspur), Total House Hold - 1112 nos. | Assistant Engineer | Junior Engineer | ORD/000126/2021-2022 | 2791/BQA | 11/11/2021 | 11/12/2021 | BISWARUP BOSE | 52.83 | 35.2 | 66.63 | 100
5 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mousas (Garerban, Ekteswar (Part, 30%), Shyamdaspur, Bhadul, Bhutsahar, Bejg | SM/09315 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000002/2021-2022 | 2816/BQA | 12/11/2021 | 12/11/2021 | Resource Division | 3.98 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mousas (Garerban, Ekteswar (Part, 30%), Shyamdaspur, Bhadul, Bhutsahar, Bejg | SM/09315 | Retrofitting | SURVEY WORK of Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of EKTESWAR (Zone - II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Ekteswar (II) No.of Mouza :- 07 nos, (Ekteswar Garerbon , Shyamdaspur, Bhadul, Bhutsahar, Bejagram, Sanabandh) , Total House Hold - 3695 nos. |  | Junior Engineer | ORD/000920/2021-2022 | 64/BSD | 14/01/2022 | 14/04/2022 | TAPAS DEY | 1.23 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mousas (Garerban, Ekteswar (Part, 30%), Shyamdaspur, Bhadul, Bhutsahar, Bejg | SM/09315 | Retrofitting | Laying of HDPE pipe line from Jagannathpur to Bankuradanga & Muktapur Village to increase pressure in Bankuradanga Mouza & MuktapurMouza for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000005/2022-2023 | 893/BQA | 18/04/2022 | 18/05/2022 | AMITAVA CHAKRABORTY | 29.71 | 14.37 | 48.36 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mousas (Garerban, Ekteswar (Part, 30%), Shyamdaspur, Bhadul, Bhutsahar, Bejg | SM/09315 | Retrofitting | Laying HDPE Pipe Line from Chatarkanali OHR site to Bahadurpur,to increase presure in Bahadurpur & Bagrakonda mouzas for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of ARJUNPUR (ZONE-N) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000443/2021-2022 | 511/BQA | 10/03/2022 | 09/04/2022 | SOUMITRA BOSE | 23.15 | 9.58 | 41.4 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mousas (Garerban, Ekteswar (Part, 30%), Shyamdaspur, Bhadul, Bhutsahar, Bejg | SM/09315 | Retrofitting | SURVEY WORK of Rectro fitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of EKTESWAR (Zone - II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Ekteswar (II) No.of Mouza :- 07 nos, (Ekteswar Garerbon , Shyamdaspur, Bhadul, Bhutsahar, Bejagram, Sanabandh) , Total House Hold - 3695 nos. |  |  | VCH/000252/2022-2023 | FHTC/12 | 12/04/2022 | 12/04/2022 | TAPAS DEY | 0.99 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mousas (Garerban, Ekteswar (Part, 30%), Shyamdaspur, Bhadul, Bhutsahar, Bejg | SM/09315 | Retrofitting | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mousas (Garerban, Ekteswar (Part, 30%), Shyamdaspur, Bhadul, Bhutsahar, Bejgram & Sanbandha) of pipe water supply scheme for Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002388/2021-2022 | FHTC/21 | 21/02/2022 | 21/02/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 105 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mousas (Garerban, Ekteswar (Part, 30%), Shyamdaspur, Bhadul, Bhutsahar, Bejg | SM/09315 | Retrofitting | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos mousa (Bhadul, Bhutsahar & Bejgram) of pipe water supply scheme for Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Ekteswar (II), No.of Mouza :- 03 nos, (Bhadul, Bhutsahar & Bejgram), Total House Hold - 1166 nos. |  |  | VCH/002845/2021-2022 | FHTC/14 | 14/03/2022 | 14/03/2022 | ASOKE BHATTACHARYYA | 11.59 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mousas (Garerban, Ekteswar (Part, 30%), Shyamdaspur, Bhadul, Bhutsahar, Bejg | SM/09315 | Retrofitting | Laying Extra UPVC Pipe Line for Shyamdaspur to Cover Shyamdaspur mouzas for construction and commissioning of FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of EKTESWAR (Zone - II) OHR under Ekteswar and its adjoining mouzas W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A) | Assistant Engineer | Junior Engineer | ORD/000372/2022-2023 | 49/BQA | 05/01/2023 | 19/02/2023 | BISWARUP BOSE | 4.94 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 07 nos mousas (Garerban, Ekteswar (Part, 30%), Shyamdaspur, Bhadul, Bhutsahar, Bejg | SM/09315 | Retrofitting | Laying Extra UPVC Pipe Line for Shyamdaspur to Cover Shyamdaspur mouzas for construction and commissioning of FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of EKTESWAR (Zone - II) OHR under Ekteswar and its adjoining mouzas W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- B) | Assistant Engineer | Junior Engineer | ORD/000373/2022-2023 | 50/BQA | 05/01/2023 | 19/02/2023 | BISWARUP BOSE | 4.98 | 0 | 0 | 0
Total | [13 empty] | 363.88 | 106.44 | 29.25