## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE - I W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone - I, Name of Mouza:- 01 no., (Harakabad), Total House Hold - 174 nos. |  | Junior Engineer | ORD/000155/2021-2022 | 2835/BQA | 16/11/2021 | 16/12/2021 | RAHUL CHATERJEE | 6.51 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE - I W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma zone -I, Name of Mouza:-- 2 no., (Barasali, Kukirakur), Total House Hold - 332 nos. |  | Junior Engineer | ORD/000151/2021-2022 | 2831/BQA | 16/11/2021 | 16/12/2021 | TAPAS KUMBHAKAR | 16.02 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma zone -II, Name of Mouza:-- 1 no., (Kamalhir), Total House Hold - 344 nos. |  | Junior Engineer | ORD/000135/2021-2022 | 2800/BQA | 11/11/2021 | 11/12/2021 | JAGADISH BANERJEE | 16.69 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -II, Name of Mouza:-- 2 no., (Bakulia, Saheb danga), Total House Hold - 255 nos. |  | Junior Engineer | ORD/000138/2021-2022 | 2801/BQA | 11/11/2021 | 11/12/2021 | ACHARJEE & SON | 12.25 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -II, Name of Mouza:-- 1 no., (Dahuka), Total House Hold - 277 nos. |  | Junior Engineer | ORD/000139/2021-2022 | 2802/BQA | 11/11/2021 | 11/12/2021 | GOURANGA CHATTERJEE | 13.68 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -II, Name of Mouza:-- 3 nos, (Bhuban Bandi, Swattwakuri, Saltura), Total House Hold - 273 nos. |  | Junior Engineer | ORD/000140/2021-2022 | 2803/BQA | 11/11/2021 | 11/12/2021 | GOUTAM GHOSH | 13.5 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone - I, Name of Mouza:-- 2 no., (Bhangucha , Illambajar), Total House Hold - 264 nos. |  | Junior Engineer | ORD/000141/2021-2022 | 2804/BQA | 11/11/2021 | 11/12/2021 | PARESH CHANDRA LAYEK | 12.67 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -I, Name of Mouza:-- 03 nos, (Chandbad, Chaukhuri, Singhir), Total House Hold - 257 nos. |  | Junior Engineer | ORD/000152/2021-2022 | 2832/BQA | 16/11/2021 | 16/12/2021 | GANGADHAR MONDAL | 12.17 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -I, Name of Mouza:-- 02 no., (Kechka, Chuaberia), Total House Hold - 483 nos. |  | Junior Engineer | ORD/000153/2021-2022 | 2833/BQA | 16/11/2021 | 16/12/2021 | SRIKANTA MONDAL | 22.08 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -I, Name of Mouza:-- 1 no., (Beltikri), Total House Hold - 242 nos. |  | Junior Engineer | ORD/000150/2021-2022 | 2830/BQA | 16/11/2021 | 16/12/2021 | M/S SUPRIYA CHATTERJEE | 11.6 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -(II), Name of Mouza:-- 1 no., (Salma), Total House Hold - 881 nos. |  | Junior Engineer | ORD/000134/2021-2022 | 2799/BQA | 11/11/2021 | 11/12/2021 | DAUD ALI KHAN | 38.77 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Laying extra UPVC Pipe Line to Cover (Bhuban Bandi, Swattwakuri, Saltura), mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000501/2021-2022 | 252/BSD | 15/03/2022 | 25/03/2022 | GOUTAM GHOSH | 2.34 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Water supply arrangement at different school of Salma & Cleaning of Chokage Existing pipelinefrom Kastora Bouripara to Muslimpara & Bhangucha to Beltukri of Salma (Zone I & III) under Salma W/S Scheme of Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. |  | Junior Engineer | ORD/000549/2021-2022 | 810/BSD | 06/08/2021 | 16/08/2021 | TAPAN KUMAR MANDAL | 2.94 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Laying of extra UPVC pipe from Bhaghucha to Chuaberia to increase water pressure for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000151/2022-2023 | 541/BSD | 28/07/2022 | 27/08/2022 | TAPAN KUMAR MANDAL | 4.49 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Laying extra UPVC Pipe Line to Cover Majit mouza and dismantling, reconstruction of concrete for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -I W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000155/2022-2023 | 560/BSD | 29/07/2022 | 19/08/2022 | MD. AFSAR ALI | 3.57 | 0 | 0 | 0
16 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone - II) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - II), No. of Mouza :- 01 no., Salma (Part), Habitation- Dahuka, Gopalnagar, Total House Hold- 43 nos. |  | Junior Engineer | ORD/000462/2021-2022 | 222/BSD | 11/03/2022 | 21/03/2022 | DAUD ALI KHAN | 3.88 | 0 | 0 | 0
17 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone - I) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - I), No. of Mouza :- 01 no., (Kukrakuli), Total House Hold- 67 nos. |  | Junior Engineer | ORD/000481/2021-2022 | 218/BSD | 11/03/2022 | 21/03/2022 | TAPAS KUMBHAKAR | 3.8 | 0 | 0 | 0
18 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma (Zone - II) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - II), No. of Mouza :- 01 no., Salma (Part), Habitation- Gobindpur, Total House Hold- 98 nos. |  | Junior Engineer | ORD/000463/2021-2022 | 223/BSD | 11/03/2022 | 21/03/2022 | SAMIRUDDIN KHAN | 4.98 | 0 | 0 | 0
19 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone - I) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - I), No. of Mouza :- 01 no., (Beltukri), Total House Hold- 23 nos. |  | Junior Engineer | ORD/000492/2021-2022 | 224/BSD | 11/03/2022 | 21/03/2022 | M/S SUPRIYA CHATTERJEE | 4.57 | 0 | 0 | 0
20 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Laying extra UPVC Pipe Line to Cover Bakulia & Sahebdanga mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE - II W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000497/2021-2022 | 234/BSD | 15/03/2022 | 25/03/2022 | ACHARJEE & SON | 3.32 | 0 | 0 | 0
21 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Laying extra UPVC /HDPE Pipe Line to cover Dahuka village interconnection with house connection pipe & Dismantling, reconstruction of concrete for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -I W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000229/2022-2023 | 562/ BSD | 29/07/2022 | 19/08/2022 | DAUD ALI KHAN | 0.71 | 0 | 0 | 0
22 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Laying Extra HDPE Pipe Line to Cover Gobindpur mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA (ZONE - II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. |  | Junior Engineer | ORD/000636/2021-2022 | 164/BSD | 16/02/2022 | 26/02/2022 | DAUD ALI KHAN | 2.6 | 0 | 0 | 0
23 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Laying extra UPVC Pipe Line to Cover , (Bhangucha , Illambajar), mouza & Dismantling & reconstruction of concrete for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-I W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte . |  | Junior Engineer | ORD/000567/2021-2022 | 279/BSD | 17/03/2022 | 27/03/2022 | PARESH CHANDRA LAYEK | 4.32 | 0 | 0 | 0
24 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Laying extra HDPE Pipe Line from OHR Zone II to Dahuka village to increase water pressure for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -I W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000228/2022-2023 | 561/ BSD | 29/07/2022 | 19/08/2022 | DAUD ALI KHAN | 4.92 | 0 | 0 | 0
25 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Laying of 15 mm NB PVC (schedule 80) /20 mm OD HDPE (PE100, Pn16) to Cover Salma mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA (ZONE - II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. ,under Bankura Sadar Sub- Division of Bankura Division PHE Dte. |  | Junior Engineer | ORD/000635/2021-2022 | 281/BSD | 17/03/2022 | 27/03/2022 | DAUD ALI KHAN | 1.58 | 0 | 0 | 0
26 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Laying extra HDPE Pipe Line to Cover Gobindpur mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma (Zone - II) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. sl no - 19 |  |  | VCH/001227/2022-2023 | FHTC/27 | 27/09/2022 | 27/09/2022 | DAUD ALI KHAN | 1.72 | 0 | 0 | 0
27 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Laying extra UPVC pipeline to cover Kechka & Chuaberia mouzas for retrofitting works 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I ) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/000646/2022-2023 | FHTC/14 | 14/07/2022 | 14/07/2022 | SRIKANTA MONDAL | 3.81 | 0 | 0 | 0
28 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -II, Name of Mouza:-- 2 no., (Bakulia, Saheb danga), Total House Hold - 255 nos |  |  | VCH/000726/2022-2023 | FHTC/12 | 12/08/2022 | 12/08/2022 | ACHARJEE & SON | 12.25 | 0 | 0 | 0
29 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Laying extra UPVC pipe lineto cover Beltikri mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma zone - l water supply scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002938/2021-2022 | FHTC/23 | 23/03/2022 | 23/03/2022 | M/S SUPRIYA CHATTERJEE | 2.98 | 0 | 0 | 0
30 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | laying extra UPVC pipe line to cover Horakabaid mouzas Retrofitting works for creation 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Salma Zone - l under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/003081/2021-2022 | FHTC/30 | 30/03/2022 | 30/03/2022 | RAHUL CHATERJEE | 2.52 | 0 | 0 | 0
31 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01 ( Ratganj Madhav pur ), Total House Hold -154 |  |  | VCH/002569/2021-2022 | FHTC/26 | 26/02/2022 | 26/02/2022 | RUFIKUL MONDAL | 10.75 | 0 | 0 | 0
32 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | laying extra HDPE pipe line to cover Gopalnagar mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma zone - ll water supply scheme under Bankura sadar sub - Division of Bankura Division, PHE Dte. |  |  | VCH/003003/2021-2022 | FHTC/26 | 26/03/2022 | 26/03/2022 | DAUD ALI KHAN | 4.07 | 0 | 0 | 0
33 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | laying extra UPVC pipe line to cover Kamalhit mouzas Construction and commissioning of of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma zone - ll W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/003085/2021-2022 | FHTC/30 | 30/03/2022 | 30/03/2022 | SOMA BANERJEE | 4.51 | 0 | 0 | 0
34 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Laying extra UPVC pipe to cover Bhuban Bandi, Swattwakuri mouza for retrofitting works for creation of FHTC in connection with Jal Jeevan Mission Programme and Jal Swapna of Salma Zone -II W/S Scheme |  |  | VCH/000553/2022-2023 |  | 18/07/2022 | 18/07/2022 | GOUTAM GHOSH | 2.29 | 0 | 0 | 0
35 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Harakabad of pipe water supply scheme for SALMA & adjoining mouzas (Zone I & II) under Bankura Sadar Sub - Division of Ba |  |  | VCH/001209/2022-2023 | FHTC/15 | 15/09/2022 | 15/09/2022 | RAHUL CHATERJEE | 2.05 | 0 | 0 | 0
36 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Laying extra UPVC pipe lineto cover Chandbad , Chaukhuri, Singhir Construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA Salma (Zone - l ) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. . |  |  | VCH/003002/2021-2022 | FHTC/26 | 26/03/2022 | 26/03/2022 | GANGADHAR MONDAL | 0.74 | 0 | 0 | 0
37 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | laying extra HDPE pipe line to cover Gopalnagar mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma zone - ll water supply scheme under Bankura sadar sub - Division of Bankura Division, PHE Dte. |  |  | VCH/003004/2021-2022 | FHTC/26 | 26/03/2022 | 26/03/2022 | DAUD ALI KHAN | 4.74 | 0 | 0 | 0
38 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | SURVEY WORK of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of EKTESWAR (Zone - I) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - NOT Name of Mouza:-- Ekteswar (Part) & Sankardihi, Total House Hold - 452 nos. |  |  | VCH/000251/2022-2023 | FHTC/12 | 12/04/2022 | 12/04/2022 | TAPAS DEY | 0.15 | 0 | 0 | 0
39 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Rupaghagra (190), Sarulia (191), Saluka (213), Bamnisol (214), Khaerpahari (220) & Bhalukkhunya (221) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/002565/2021-2022 | FHTC/26 | 26/02/2022 | 26/02/2022 | PARAMESWAR CHOWDHURY | 47.88 | 0 | 0 | 0
40 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 02 ( Bahadur pur , Oltara(PART-A), Total House Hold -141 |  |  | VCH/002567/2021-2022 | FHTC/26 | 26/02/2022 | 26/02/2022 | RUFIKUL MONDAL | 9.81 | 0 | 0 | 0
41 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Survey work for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme for SALMA & adjoining mouzas (Zone I & II) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma zone -II, Name of Mouza:-- 20 nos, (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, Swattwakuri, Harakabad Kukirakuri, Chandbad Chaukhuri, Singhir, Majit, Bhanguch , Illambajar, Barasal, Kechka, Chuaberia, Beltikri), Total House Hold - 3957 nos. |  |  | VCH/000257/2022-2023 | FHTC/12 | 12/04/2022 | 12/04/2022 | TAPAS DEY | 1.13 | 0 | 0 | 0
42 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma (Zone - II) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - II), No. of Mouza :- 01 no., Salma (Part), Habitation- Gobindpur, Total House Hold- 98 nos. |  |  | VCH/001228/2022-2023 | FHTC/27 | 27/09/2022 | 27/09/2022 | SAMIRUDDIN KHAN | 4.97 | 0 | 0 | 0
43 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone - II) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - II), No. of Mouza :- 02 no., (Bakulia & Sahebdanga) Total House Hold- 70 nos. |  | Junior Engineer | ORD/000479/2021-2022 | 253/BSD | 15/03/2022 | 25/03/2022 | BASUDEB ACHARJEE | 4.96 | 0 | 0 | 0
44 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma (Zone - I) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - I), No. of Mouza :- 01 no., (Beltukri), Total House Hold- 23 nos. | Assistant Engineer | Junior Engineer | ORD/000612/2021-2022 | 224/BSD | 11/03/2022 | 21/03/2022 | M/S SUPRIYA CHATTERJEE | 4.57 | 0 | 0 | 0
45 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Laying HDPE Pipe Line from Durlavpur air valve to Durlavpur Muslim para for increase water pressure at Swattkuri, Kamalhir, Durlavpu for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma (Zone- I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000976/2022-2023 | 566/BSD | 29/07/2022 | 19/08/2022 | JAGADISH BANERJEE | 3.35 | 0 | 0 | 0
46 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone - I, Name of Mouza:-- 02 no., Majit ( Part), Singhir (Part), Total House Hold - 20 nos. |  | Junior Engineer | ORD/000042/2022-2023 | 462/BSD | 06/06/2022 | 16/06/2022 | MD. AFSAR ALI | 1.66 | 0 | 0 | 0
47 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Laying extra UPVC Pipe Line to Dahuka village of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE- II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000118/2022-2023 | 458/BSD | 06/06/2022 | 21/06/2022 | GOURANGA CHATTERJEE | 3.75 | 0 | 0 | 0
48 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Laying extra UPVC pipe line & extra 15 mm NB PVC (schedule 80) / 20 mm OD HDPE (PE100, Pn16) pipe to Cover Kendana mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-III W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000638/2021-2022 | 273/BSD | 17/03/2022 | 27/03/2022 | SK. SAHAJAHAN | 3.63 | 0 | 0 | 0
49 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Dismantaling & reconstruction of Kastora, Singhir & Majit mouza & Cleaning Wasing the pipeline from Bhaghucha to kechka for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-I W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000153/2022-2023 | 543/BSD | 28/07/2022 | 27/08/2022 | TAPAN KUMAR MANDAL | 4.14 | 0 | 0 | 0
50 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Restoration & renovation 100 mm dia connecting line carrying structure including all related works & Clearing the chokage of upvc line Durlavpur to Bhubanbadhi, interconnection with BRGF Line for W/S arrangement at Salma Zone- III including contruction of valve chamber at Salma zone-II Water Supply Scheme under Bankura Sadar Sub-Division, of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000306/2022-2023 | 469/BSD | 06/06/2022 | 21/06/2022 | DAUD ALI KHAN | 4.95 | 0 | 0 | 0
51 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I & II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone - I, Name of Mouza:-- 01 no., (Majit), Total House Hold - 175 nos. |  | Junior Engineer | ORD/000154/2021-2022 | 2834/BQA | 16/11/2021 | 16/12/2021 | MD. AFSAR ALI | 7.96 | 0 | 0 | 0
52 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Laying of extra UPVC pipe from Bhaghucha to Chuaberia to increase water pressure for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/001537/2022-2023 | FHTC/19 | 19/01/2023 | 19/01/2023 | TAPAN KUMAR MANDAL | 4.49 | 0 | 0 | 0
53 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 20 nos. Mouzas (Bakulia, Saheb Danga, Saltura, Salma Dahuka, Kamalhir, Bhubandi, | SM/09316 | Retrofitting | Laying of extra UPVC pipeline from OHR Zone- III to Kendana village to increase water pressure for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-III W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/001536/2022-2023 | FHTC/19 | 19/01/2023 | 19/01/2023 | TAPAN KUMAR MANDAL | 4.68 | 0 | 0 | 0
Total | [13 empty] | 388.43 | 0 | 0