## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 18 Nos. Mouzas, (Khirpai, Suribedia, Hanulia, Banagram, Bandardiha, Mansthol, Sh | SM/09319 | Retrofitting | Laying HDPE Pipe Line from Bangora to vanderber to increase water pressure at Saldiha,Vanderber for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Keshra (Zone - I) W/S Scheme under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000371/2022-2023 | 48/BQA | 05/01/2023 | 05/04/2023 | M/S ABU KADER KHAN | 3.57 | 2.61 | 73.12 | 78
2 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 18 Nos. Mouzas, (Khirpai, Suribedia, Hanulia, Banagram, Bandardiha, Mansthol, Sh | SM/09319 | Retrofitting | Retrofitting works for creacion of ¿FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of KESHRA (Zone - I) under Chhana Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Keshra, No. of Mouza :- 18 nos, (Khirpai, Suribedia, Hanulia, Banagram, Bandardiha, Mansthol, Shaldiha, Rampur, Lakshmishol, Khirshole, Chakta magara, Joytradihi, Pithabad, Bhandarber, Keshra, Mahishadanga, Hetatora, Baliguma), Total House Hold - 2926 nos. |  | Junior Engineer | ORD/000248/2021-2022 | 3361/BQA | 31/12/2021 | 01/03/2022 | M/S D.K.H CONSTRUCTION | 145.99 | 145.98 | 100 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 18 Nos. Mouzas, (Khirpai, Suribedia, Hanulia, Banagram, Bandardiha, Mansthol, Sh | SM/09319 | Retrofitting | Laying Extra HDPE Pipe Line to Cover Saldiha (Katabari gram, Napit para) mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KESHRA (Zone - I) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000570/2022-2023 | 367/KSD | 29/08/2022 | 18/09/2022 | M/S D.K.H CONSTRUCTION | 4.19 | 4.19 | 100 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 18 Nos. Mouzas, (Khirpai, Suribedia, Hanulia, Banagram, Bandardiha, Mansthol, Sh | SM/09319 | Retrofitting | Laying Extra HDPE Pipe Line to Cover Pithabad, Keshra (Maldanga Village) mouza for retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KESHRA (Zone - I) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000568/2022-2023 | 369/KSD | 29/08/2022 | 18/09/2022 | M/S D.K.H CONSTRUCTION | 3.2 | 3.2 | 99.86 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 18 Nos. Mouzas, (Khirpai, Suribedia, Hanulia, Banagram, Bandardiha, Mansthol, Sh | SM/09319 | Retrofitting | Laying Extra HDPE Pipe Line to Cover Hanulia, Laxmisole, Vandarber mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KESHRA (Zone - I) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000580/2022-2023 | 337/KSD | 16/08/2022 | 05/09/2022 | M/S D.K.H CONSTRUCTION | 3.99 | 3.99 | 100 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 18 Nos. Mouzas, (Khirpai, Suribedia, Hanulia, Banagram, Bandardiha, Mansthol, Sh | SM/09319 | Retrofitting | Laying Extra HDPE Pipe Line to Cover Suribedia, Keshra, Khirpai mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KESHRA (Zone - I) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000577/2022-2023 | 335/KSD | 16/08/2022 | 05/09/2022 | M/S D.K.H CONSTRUCTION | 4.58 | 4.58 | 100 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 18 Nos. Mouzas, (Khirpai, Suribedia, Hanulia, Banagram, Bandardiha, Mansthol, Sh | SM/09319 | Retrofitting | Laying Extra HDPE Pipe Line to Cover Saldiha (Bouri para, Tati para, Baisnab para) mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of KESHRA (Zone - I) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000590/2022-2023 | 365/KSD | 29/08/2022 | 18/09/2022 | M/S D.K.H CONSTRUCTION | 4.99 | 4.99 | 99.85 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 18 Nos. Mouzas, (Khirpai, Suribedia, Hanulia, Banagram, Bandardiha, Mansthol, Sh | SM/09319 | Retrofitting | Laying extra HDPE Pipe Line to Cover Masthol, Baliguma mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KESHRA (Zone - I) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000574/2022-2023 | 363/ KSD | 29/08/2022 | 18/09/2022 | M/S D.K.H CONSTRUCTION | 4.82 | 4.82 | 99.92 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 18 Nos. Mouzas, (Khirpai, Suribedia, Hanulia, Banagram, Bandardiha, Mansthol, Sh | SM/09319 | Retrofitting | Survey work for Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of KESHRA (Zone - I) under Chhana Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Keshra, No.of Mouza :- 18 nos, (Khirpai, Suribedia, Hanulia, Banagram, Bandardiha, Mansthol,Shaldiha, Rampur, Lakshmishol, Khirshole, Chakta magara, Joytradihi, Pithabad, Bhandarber, Keshra, Mahishadanga, Hetatora, Baliguma) Total House Hold - 2926 nos. |  | Junior Engineer | ORD/000879/2021-2022 | 72/BSD | 14/01/2022 | 14/04/2022 | TAPAS DEY | 0.98 | 0.94 | 96.48 | 0
Total | [13 empty] | 176.32 | 175.3 | 99.42