## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa | SM/09320 | Retrofitting | SURVEY WORK of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No. of Mouza :- 06 nos, (Tantkanali, Harialgora, Keshra, Jugsaha, Salboni & Shitaldihi), Total House Hold - 2035 nos. |  | Junior Engineer | ORD/000579/2021-2022 | 66/BSD | 14/01/2022 | 14/04/2022 | TAPAS DEY | 0.68 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa | SM/09320 | Retrofitting | Laying extra HDPE Pipe Line to Cove Salboni mouza for construction and commissioning of'' 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000661/2021-2022 | 268/BSD | 17/03/2022 | 27/03/2022 | PARTHA PRATIM CHHATAIT | 4.97 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa | SM/09320 | Retrofitting | laying extra HDPE pipe line to cover Keshra mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Harialgora zone - o under Bankura - l & ll & Barjora W/S Scheme (BRGF ph - I project) within Barjora block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte part - B |  |  | VCH/003071/2021-2022 | FHTC/30 | 30/03/2022 | 30/03/2022 | PARTHA PRATIM CHHATAIT | 4.81 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa | SM/09320 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kayma (215), Hatbari (216), Karbhanga (217), Bhadkunra (218), Asanjhor (219) & Baragarra (289) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/002573/2021-2022 | FHTC/26 | 26/02/2022 | 26/02/2022 | KHAN ENTERPRISE | 59.28 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa | SM/09320 | Retrofitting | laying extra HDPE pipe line to cover Keshra mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Harialgora zone - o under Bankura - l & ll & Barjora W/S Scheme (BRGF ph - I project) within Barjora block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte part - A. |  |  | VCH/003072/2021-2022 | FHTC/30 | 30/03/2022 | 30/03/2022 | PARTHA PRATIM CHHATAIT | 4.89 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa | SM/09320 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuporsol Zone- A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Majuria, No. of Mouza :- 02 nos. i.e. Chotobankadaha-148 and Bandrya- 150, Total House Hold - 534 ( Out of 703) |  |  | VCH/002571/2021-2022 | FHTC/26 | 26/02/2022 | 26/02/2022 | SUBHENDU SEKHAR GORAI | 34.27 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa | SM/09320 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SABURBANDH W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Saburbadh, Name of Mouza:-- 01 no., (Saburbandh), Total House Hold - 428 nos. |  |  | VCH/002570/2021-2022 | FHTC/26 | 28/02/2022 | 28/02/2022 | RUFIKUL MONDAL | 20.4 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa | SM/09320 | Retrofitting | SURVEY WORK of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No. of Mouza :- 06 nos, (Tantkanali, Harialgora, Keshra, Jugsaha, Salboni & Shitaldihi), Total House Hold - 2035 nos. |  |  | VCH/000253/2022-2023 | FHTC/12 | 12/04/2022 | 12/04/2022 | TAPAS DEY | 0.51 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa | SM/09320 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora , Name of OHR - JOYKRISHNAPUR (Zone - I) . No.of Mouza :- 01 ( Ratganj Madhav pur ), Total House Hold -154 |  |  | VCH/002569/2021-2022 | FHTC/26 | 26/02/2022 | 26/02/2022 | RUFIKUL MONDAL | 10.75 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa | SM/09320 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Sonamukhi, Name of OHR - Jamdoba. No. of Mouza :- 2 nos. i.e. Jamdoba-154 & Ichharia-155 , Habitation's Name : Jamdoba, Roypara, Tantipara, Kalaberia & Kalyanpur, Total House Hold - 140 |  |  | VCH/002572/2021-2022 | FHTC/26 | 26/02/2022 | 26/02/2022 | MOHAN KUMAR ROY | 0.66 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa | SM/09320 | Retrofitting | laying extra HDPE pipe line to cover (Tantkanali, Harialgora, Keshra, Jugsha & shitaldihi mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Harialgora zone - o under Bankura - l & ll & Barjora W/S Scheme (BRGF ph - I project) within Barjora block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte |  |  | VCH/003073/2021-2022 | FHTC/30 | 30/03/2022 | 30/03/2022 | PARTHA PRATIM CHHATAIT | 4.9 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa | SM/09320 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HORIALGORA (Zone -O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph. - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Horialgora No.of Mouza :- 01 nos. junbedia( Ramkrishnapolly & sushundanga) Total House Hold -60 nos. |  | Junior Engineer | ORD/000337/2022-2023 | 606/BSD | 16/08/2022 | 06/09/2022 | GANESH ROY | 4.8 | 0 | 0 | 100
13 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa | SM/09320 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No. of Mouza :- 06 nos, (Tantkanali, Salboni, Harialgora, Keshra, Jugsaha & Shitaldihi), Total House Hold - 2035 nos. |  | Junior Engineer | ORD/000256/2021-2022 | 3164/BQA | 17/12/2021 | 15/02/2022 | PARTHA PRATIM CHATAIT | 101.36 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa | SM/09320 | Retrofitting | Laying of HDPE pipe line from Jagannathpur to Bankuradanga & Muktapur Village to increase pressure in Bankuradanga Mouza & MuktapurMouza for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000005/2022-2023 | 893/BQA | 18/04/2022 | 18/05/2022 | AMITAVA CHAKRABORTY | 29.71 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa | SM/09320 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HORIALGORA (Zone -OJ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph. - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Horialgora No.of Mouza :- 01 nos. junbedia( chattar Bekari goly) Total House Hold -70 nos. |  | Junior Engineer | ORD/000338/2022-2023 | 608/BSD | 16/08/2022 | 06/09/2022 | GANESH ROY | 4.91 | 0 | 0 | 0
16 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa | SM/09320 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HORIALGORA (Zone -OJ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph. - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Horialgora No.of Mouza :- 01 nos. junbedia( Palashtala) Total House Hold -63 nos. |  | Junior Engineer | ORD/000339/2022-2023 | 610/BSD | 16/08/2022 | 06/09/2022 | GANESH ROY | 4.96 | 0 | 0 | 0
17 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa | SM/09320 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HORIALGORA (Zone -OJ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph. - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Horialgora No.of Mouza :- 01 nos. junbedia (junbedia more) Total House Hold -60 nos. |  | Junior Engineer | ORD/000335/2022-2023 | 601/BSD | 16/08/2022 | 06/09/2022 | GANESH ROY | 4.99 | 0 | 0 | 0
18 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa | SM/09320 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HORIALGORA (Zone -OJ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph. - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Horialgora No.of Mouza :- 01 nos. junbedia (uttar arabindanagar & Indrapasta) Total House Hold -50 nos. |  | Junior Engineer | ORD/000336/2022-2023 | 603/BSD | 16/08/2022 | 06/09/2022 | GANESH ROY | 4.99 | 0 | 0 | 0
19 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 06 nos mousas (Tantkanali, Harialgora, Sa | SM/09320 | Retrofitting | Laying HDPE pipeline to increase pressure in Labdapara (265) & Birkham (266) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-IIB (Hetiasol) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/001427/2022-2023 | FHTC/23 | 23/12/2022 | 23/12/2022 | PARTHA PRATIM CHHATAIT | 5.98 | 0 | 0 | 0
Total | [13 empty] | 307.83 | 0 | 0