## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Sashpur Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Shashpur-75, Narayanpur-82, Thakuranidighi | SM/09324 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Sashpur Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Dhamur, No. of Mouza :- 09 nos. i.e. Shashpur-75, Narayanpur-82, Thakuranidighi-63, Dharmapur-64, Charigram-65, Baikunthapur-68, Manaharpur-74, Biharpuskarini-94 & Barajpota-95 , Total House Hold - 2264 |  | Junior Engineer | ORD/000419/2021-2022 | 440/BQA | 03/03/2022 | 02/05/2022 | PRINCE INDUTRIES (INDIA) | 140.28 | 136.12 | 97.04 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Sashpur Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Shashpur-75, Narayanpur-82, Thakuranidighi | SM/09324 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000023/2021-2022 | 474/BQA | 04/03/2022 | 04/03/2022 | Resource Division | 13.92 | 0 | 0 | 0
Total | [13 empty] | 154.2 | 136.12 | 88.28