## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishnan | SM/09327 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur, Bamandihi, Kamla, Krishnanagar, Bhairabpur (Paschim)) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) Block -Barjora, Name of OHR - No (Direct supply), No. of Mouza:- 01 no., (Krishnanagar ), Total House Hold -1227 nos |  | Junior Engineer | ORD/000132/2021-2022 | 2797/BQA | 11/11/2021 | 11/12/2021 | MUNMUN UPADHYAY | 72.28 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishnan | SM/09327 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla,Krishnanagar , Bhairabpur (Paschim)) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) Block -Barjora, Name of OHR - No (Direct supply), No.of Mouza :- 01 no., (Bhairabpur (Paschim), Total House Hold -367 nos |  | Junior Engineer | ORD/000133/2021-2022 | 2798/BQA | 11/11/2021 | 11/12/2021 | BEAUTY CHATTERJEE | 21.6 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishnan | SM/09327 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur, Bamandihi, Kamla, Krishnanagar, Bhairabpur (Paschim)) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) Block -Barjora, Name of OHR -No (Direct supply), No.of Mouza :- 02 no., (Harinagara, Kamla), Total House Hold - 283 nos |  | Junior Engineer | ORD/000131/2021-2022 | 2796/BQA | 11/11/2021 | 11/12/2021 | SAIKAT CHOWDHURY | 16.55 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishnan | SM/09327 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur , Harinagara , Raghunathpur,Bamandihi, Kamla,Krishnanagar, Bhairabpur (Paschim)) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) Block -Barjora, Name of OHR -No (Direct supply), No. of Mouza :- 04 nos, (Ronalejora, Shyampur, Bhagabanpur, Raghunathpur), Total House Hold -580 nos |  | Junior Engineer | ORD/000129/2021-2022 | 2794/BQA | 11/11/2021 | 11/12/2021 | RANABIR CHATTERJEE | 34.39 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishnan | SM/09327 | Retrofitting | Supply of VALVE including loading, unloading, stacking etc. all comlete for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur , Harinagara , Raghunathpur,Bamandihi, Kamla,Krishnanagar , Bhairabpur (Paschim)) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IB) |  | Junior Engineer | ORD/000191/2022-2023 | 350/BSD | 12/04/2022 | 27/04/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.96 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishnan | SM/09327 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur, Bamandihi, Kamla, Krishnanagar, Bhairabpur (Paschim)) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) Block -Barjora, Name of OHR - No (Direct supply), No. of Mouza:- 01 no., (Krishnanagar ), Total House Hold -1227 nos |  |  | VCH/002868/2021-2022 | FHTC/15 | 15/03/2022 | 15/03/2022 | MUNMUN UPADHYAY | 72.26 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishnan | SM/09327 | Retrofitting | Extra HDPE pipe line to increase pressure at Kotgram Village Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Haringara & Kamala mouzas of Barjora (left out )W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. |  |  | VCH/002885/2021-2022 |  | 16/03/2022 | 16/03/2022 | SAIKAT CHOWDHURY | 4.57 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishnan | SM/09327 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 04 ( Vidyadharpur, Cherabasta, Aina gobindapur & Mukundapur.) Total House Hold - 604 |  |  | VCH/002745/2021-2022 | FHTC/3 | 03/03/2022 | 03/03/2022 | UNICON INDIA | 116.51 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishnan | SM/09327 | Retrofitting | Extra HDPE pipe line to increase pressure at Haringara Village Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Haringara & Kamala mouzas of Barjora (left out )W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. |  |  | VCH/000232/2022-2023 | FHTC/11 | 11/04/2022 | 11/04/2022 | SAIKAT CHOWDHURY | 2.79 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishnan | SM/09327 | Retrofitting | Extra HDPE pipe line to increase pressure at Kotgram Village Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Haringara & Kamala mouzas of Barjora (left out )W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. |  |  | VCH/000233/2022-2023 | FHTC/11 | 11/04/2022 | 11/04/2022 | SAIKAT CHOWDHURY | 4.57 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishnan | SM/09327 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of (Ronalejora, shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur, Bamandihi, Kamla, krishnanagar, Barjora W/S Scheme (left out mouzas of barjora BRGF ph - I project) within Barjora block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, zone IB Name of OHR - no (direct supply) No. of Mouza :- 10 nos. . Total House Hold -3147 sl no - 15 |  |  | VCH/000246/2022-2023 | FHTC/12 | 12/04/2022 | 12/04/2022 | TAPAS DEY | 0.83 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishnan | SM/09327 | Retrofitting | laying extra HDPE pipe line to cover Babundihi main road towards Bilmalpur village to cover Bilmalpur mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Barjora water supply scheme (left out mouzas of barjora block under BRGF ph - l ) within Barjora block under Bankura sadar sub - Division of Bankura Division, PHE Dte. zone - IB sl no - 09 |  |  | VCH/002970/2021-2022 | FHTC/26 | 25/03/2022 | 25/03/2022 | RANABIR CHATTERJEE | 4.69 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishnan | SM/09327 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Bhairabpur (Paschim) of Barjora W/S Scheme (left out mouzas of Barjora block under BRGF PH - I within Barjoa block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora Name of OHR- direct supply , Name of Mouza:-- 1 no., (BBhairabpur (Paschim), Total House Hold - 42 nos sl no - 01. |  |  | VCH/002941/2021-2022 | FHTC/23 | 23/03/2022 | 23/03/2022 | BEAUTY CHATTERJEE | 4.59 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishnan | SM/09327 | Retrofitting | laying extra HDPE pipe line to cover Jomadargram more to Babundihi Talpukur more to increse pressute in Bamandihi mouzas for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Barjora W/S Scheme (BRGF ph - I project) within Barjora block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte zone - IB sl no - 08 |  |  | VCH/003068/2021-2022 | FHTC/30 | 30/03/2022 | 30/03/2022 | RANABIR CHATTERJEE | 4.72 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishnan | SM/09327 | Retrofitting | Laying extra HDPE pipe lineto Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Bhairabpur (paschim) of Barjora water supply scheme (left out mouzas of Barjora block under (BRGF ph - I project) block - Barjora under Bankura sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR- No (direct supply) Name of Mouza:-- 1 no., (Bhairabpur) (Paschim) sl No- 09 |  |  | VCH/002940/2021-2022 | FHTC/23 | 23/03/2022 | 23/03/2022 | BEAUTY CHATTERJEE | 4.72 | 0 | 0 | 0
16 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishnan | SM/09327 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur, Bamandihi, Kamla, Krishnanagar, Bhairabpur (Paschim)) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase- I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) Block -Barjora, Name of OHR -No(Direct supply), No.of Mouza :- 02 nos, (Bilmalpur , Bamandihi,), Total House Hold -690 nos |  |  | VCH/000268/2022-2023 | FHTC/18 | 18/04/2022 | 18/04/2022 | RANABIR CHATTERJEE | 25.21 | 0 | 0 | 0
17 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishnan | SM/09327 | Retrofitting | Extra HDPE pipe line to increase pressure at Haringara Village Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Haringara & Kamala mouzas of Barjora (left out )W/S Scheme within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. |  |  | VCH/002884/2021-2022 |  | 16/03/2022 | 16/03/2022 | SAIKAT CHOWDHURY | 2.79 | 0 | 0 | 0
18 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishnan | SM/09327 | Retrofitting | supply of sluice valve restruration of concrete road, construction of valve chamber with all allied work to Sarari village under Barjora water supply scheme (including left out BRGF ph - l ) under BRGF ph - l within Barjora block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Sl no - 05 zone - lll |  |  | VCH/003106/2021-2022 | FHTC/30 | 30/03/2022 | 30/03/2022 | M/S TARUN KUMAR PATRA | 3.64 | 0 | 0 | 0
19 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishnan | SM/09327 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur, Bamandihi, Kamla, Krishnanagar, Bhairabpur (Paschim)) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase- I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) Block -Barjora, Name of OHR -No(Direct supply), No.of Mouza :- 02 nos, (Bilmalpur , Bamandihi,), Total House Hold -690 nos |  | Junior Engineer | ORD/000130/2021-2022 | 2795/BQA | 11/11/2021 | 11/12/2021 | RANABIR CHATTERJEE | 40.68 | 0 | 0 | 0
20 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishnan | SM/09327 | Retrofitting | Additional pipe line laying at Bhairabpur Paschim mouza and providing 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) Block -Barjora, Name of OHR - No (Direct supply), Name of Mouza :- Bhairabpur (Paschim), Total House Hold - 10 nos |  | Junior Engineer | ORD/000328/2022-2023 | 531/BSD | 28/07/2022 | 18/08/2022 | BEAUTY CHATTERJEE | 4.1 | 0 | 0 | 0
21 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishnan | SM/09327 | Retrofitting | extra HDPE pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA at Ronalejora, Shyampur & Bhagabanpur mouza of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) |  | Junior Engineer | ORD/000765/2022-2023 | 536/BSD | 28/07/2022 | 18/08/2022 | RANABIR CHATTERJEE | 4.98 | 0 | 0 | 0
22 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 10 nos. Mouzas (Ronalejora, Shyampur, Bhagabanpur, Bilmalpur, Harinagara, Raghunathpur,Bamandihi, Kamla, Krishnan | SM/09327 | Retrofitting | Extra HDPE pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA at Bilmalpur mouza of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IB) |  | Junior Engineer | ORD/000766/2022-2023 | 537/BSD | 28/07/2022 | 18/08/2022 | RANABIR CHATTERJEE | 4.8 | 0 | 0 | 0
Total | [13 empty] | 456.24 | 0 | 0