## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Chak Kulbana, Methyali, Nutangram, Pratappur, Sitarampur, Salgara) of BARJORA Water Supply Scheme | SM/09330 | Retrofitting | Retrofitting works for creation of ¿FHTC (Functional House Hold Tap Connection¿ in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 6 nos. Mouzas (Chak Kulbana, Methyali, Nutangram, Pratapur, Sitarampur, Salgara) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase ¿ I) within Barjora Block under Bankura Sadar Sub ¿ Division, PHE Dte. (Zone ¿ IA). Block ¿ Barjora, Name of OHR ¿ BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase ¿ I) (Zone ¿ IA) No. of Mouza :- 06 (Chak Kulbana, Methyali, Nutangram, Pratapur, Sitarampur, Salgara) Total House Hold ¿ 2226 nos. |  | Junior Engineer | ORD/000258/2021-2022 | 3167/BQA | 17/12/2021 | 15/02/2022 | GOPAL CHANDRA CHOUDHURY | 134.03 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Chak Kulbana, Methyali, Nutangram, Pratappur, Sitarampur, Salgara) of BARJORA Water Supply Scheme | SM/09330 | Retrofitting | Supply of VALVE including loading, unloading, stacking etc. all comlete for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Chak Kulbana, Methyali, Nutangram, Pratappur, Sitarampur, Salgara) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IA) |  | Junior Engineer | ORD/000187/2022-2023 | 347/BSD | 12/04/2022 | 27/04/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.95 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Chak Kulbana, Methyali, Nutangram, Pratappur, Sitarampur, Salgara) of BARJORA Water Supply Scheme | SM/09330 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Chak Kulbana, Methyali, Nutangram, Pratappur, Sitarampur, Salgara) of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IA) |  |  | VCH/002389/2021-2022 | FHTC/21 | 21/02/2022 | 21/02/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 70 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Chak Kulbana, Methyali, Nutangram, Pratappur, Sitarampur, Salgara) of BARJORA Water Supply Scheme | SM/09330 | Retrofitting | Survey work for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Chak Kulbana, Methyali, Nutangram, Pratappur, Sitarampur, Salgara) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IA) Block -Barjora, Name of OHR -BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA) . No.of Mouza :-06 nos, (Chak Kulbana, Methyali, Nutangram, Pratappur, Sitarampur, Salgara), Total House Hold - 2226 nos. |  |  | VCH/000248/2022-2023 | FHTC/12 | 12/04/2022 | 12/04/2022 | TAPAS DEY | 0.74 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Chak Kulbana, Methyali, Nutangram, Pratappur, Sitarampur, Salgara) of BARJORA Water Supply Scheme | SM/09330 | Retrofitting | Laying fitting fixing of HDPE pipe from Kulbona Village to Tikhargram village to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IA) Block -Barjora, Name of OHR -BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA |  | Junior Engineer | ORD/000141/2022-2023 | 564/BSD | 29/07/2022 | 28/08/2022 | GOPAL CHANDRA CHOWDHURY | 4.99 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Chak Kulbana, Methyali, Nutangram, Pratappur, Sitarampur, Salgara) of BARJORA Water Supply Scheme | SM/09330 | Retrofitting | Laying fitting fixing of HDPE pipe from Ghutgoria to Kulbona Village to increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IA) Block -Barjora, Name of OHR -BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA) |  | Junior Engineer | ORD/000143/2022-2023 | 563/BSD | 29/07/2022 | 28/08/2022 | GOPAL CHANDRA CHOWDHURY | 4.99 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 06 nos. Mouzas (Chak Kulbana, Methyali, Nutangram, Pratappur, Sitarampur, Salgara) of BARJORA Water Supply Scheme | SM/09330 | Retrofitting | Household survey work for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IA, IB, III & IV). Block - Barjora, Name of OHR:- BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) Zone-IA, IB, III & IV, No. of Mouza:- 31 nos. (Chak Kulbana, Methyali, Nutangram, Pratappur, Sitarampur, Salgara), (Tikargram, Kishoripur, Patharajuri, Gokulmathura, Joysinghapur, Paharpur), (Basudevpur uttar, Mandarboni, Radhanagar, Payermohan, Shushunia, Sarali, Bishanpur, Harirampur, Birshinghapur, Sonargram, Madanhati, Hatasuria, Sahebdihi) & (Sahorjora, Dejuri, Asuria Madhabpur, Namobandh Sitarampur, Muktatore, Deucha), Total House Hold- 902 nos. | Assistant Engineer | Junior Engineer | ORD/000102/2023-2024 | 325/BSD | 06/04/2023 | 05/06/2023 | TAPAS DEY | 0.3 | 0 | 0 | 100
Total | [13 empty] | 220 | 0 | 0