## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09454 | Augmentation | Extra Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)'at different school, ICDS and health centre in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rampur W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000023/2022-2023 | 114/VSD | 19/04/2022 | 10/05/2022 | SWAPAN KUMAR DE | 2.3 | 2.16 | 93.85 | 0
2 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09454 | Augmentation | Work order for Preparation of D.P.R.(consultancy work) in connection with the augmentation of ground water based piped water supply scheme for Rampur to accommodate FHTC under Jal Sapno Mission under Sonamukhi Block in Bankura District under Bankura Division, PHE Dte. (Sl. No. 3) [Estimated Cost Rs. Quotated Rate] |  | Junior Engineer | ORD/000653/2021-2022 | 424/C/VSD | 23/09/2021 | 03/10/2021 | SIRCON ENGINEERING SERVICES | 2.66 | 2.66 | 100 | 0
3 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09454 | Augmentation | Construction of boundary wall approx 80 mtr long at augmentation of Rampur water supply scheme (pump house no 2) under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000397/2022-2023 | 63/BQA | 05/01/2023 | 04/02/2023 | GON ASSOCIATES | 5.62 | 5.62 | 99.98 | 100
4 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09454 | Augmentation | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Rampur W/S Scheme under Bishnupur Sub-Division, P.H.E. Dte. of Bankura Division P.H.E. Dte. (2nd Call) OHR Capacity- 350 m3 |  | Junior Engineer | ORD/000777/2022-2023 | 146//VSD | 18/05/2022 | 02/06/2022 | GLORY ENGINEERS SYNDICATE | 1.4 | 1.4 | 100 | 0
5 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09454 | Augmentation | Land Development work for construction of boundary wall at augmentation work of Rampur Water Supply Scheme Pump House No 3 Boundary wall under Bishnupur Sub Division. | Assistant Engineer |  | ORD/000230/2023-2024 | 151/VSD | 02/06/2023 | 17/06/2023 | CHATERJEE ENTERPRISE | 0.99 | 0.97 | 98.08 | 20
6 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09454 | Augmentation | Construction of Retaining wall for Land development work for construction of boundary wall at augmentation work of Rampur Water Supply Scheme Pump House No. 3 Boundary wall under Bishnupur Sub Division. | Assistant Engineer |  | ORD/000240/2023-2024 | 152/VSD | 02/06/2023 | 02/07/2023 | RANABIR CHATTERJEE | 0.35 | 0.35 | 99.9 | 20
7 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09454 | Augmentation | Supply of 1 (one) No. Diesel/ LPG/ CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, R.W.S. Bankura Sub- Division, P.H.E. Dte. W.e.f. 22.01.2023 to 21.07.2023. | Assistant Engineer | Junior Engineer | ORD/001105/2022-2023 | 05./BK | 19/01/2023 | 29/07/2023 | CHANPA SINGHA | 0.86 | 1.35 | 157.58 | 30
8 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09454 | Augmentation | SUPPLY, DELIVERY OF CIDF PIPE LINE FOR 350 CUM OHR OF AUGMENTATION OF RAMPUR PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM UNDER BISHNUPUR SUB DIVISION OF BANKURA DIVISION,PHE Dte. SM CODE : SM/09454 | Assistant Engineer | Junior Engineer | ORD/000868/2023-2024 | 3024/BQA | 03/11/2023 | 18/12/2023 | SUBHANKAR BANERJEE | 5.96 | 5.96 | 100 | 100
9 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09454 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000053/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 73.9 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09454 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000059/2023-2024 | 2525/BQA | 08/09/2023 | 08/09/2023 | Resource Division | 13.01 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09454 | Augmentation | Rail Bhoomi Crossing Seva (IR-RBCS) |  |  | BILL/01411/2023-2024 | FHTC/11 | 03/11/2023 | 03/11/2023 | SOUTH EASTERN RAILWAY | 5.17 | 0 | 0 | 0
12 | BANKURA |  | Bankura Mechanical | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09454 | Augmentation | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. |  |  | BILL/00127/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09454 | Augmentation | Construction of boundary wall approx 78 mtr long at augmentation of Rampur water supply scheme (pump house no 3) under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000396/2022-2023 | 62/BQA | 05/01/2023 | 04/02/2023 | RANABIR CHATTERJEE | 5.54 | 5.54 | 99.97 | 20
14 | BANKURA |  | Bankura Mechanical | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09454 | Augmentation | Acceptance cum Formal work order for the work of -Electrical and illumination works related to instrument and laboratory requirment for proposed Water Testing Laboratory at PHED OHR site, Sonamukhi Municipal Water Supply scheme , Bankura under infrostructure development and diffrent water testing laboratories regarding NABL Accreditation recognition under Bankura Mechanical Division, PHE Dte.Dist-Bankura, Releted to supported activities under Jal Jiban Mission. | Assistant Engineer |  | ORD/000403/2022-2023 | 985/BMSD | 29/07/2022 | 13/08/2022 | RAJIB COMPANY | 4.27 | 3.82 | 89.62 | 100
15 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09454 | Augmentation | Repairing of 2 nos pump house for augmentation of Rampur water supply scheme under Bishnupur Sub Division of Bankura Division, PHE Dte. (TSM/008992) (SM/09454) (AAFS- PH212245837S000 ) | Assistant Engineer | Junior Engineer | ORD/000557/2022-2023 | 521/BQA | 14/03/2023 | 28/04/2023 | BIT ENTERPRISE | 3.62 | 3.17 | 87.82 | 100
16 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09454 | Augmentation | Creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for augmentation of Rampur W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Sonamukhi, Name of OHR - Rampur, No. of Mouza :- 10 nos. i.e. PASCHIM NABASAN (41), DHUBRAJHATI (42), RAPATGANG (56),PARB BATIA (57), BAHULIA (58),SAL CHATURIA (59), PATJOR (60), HAMIRHATI (61), RAMPUR (65), JASHRA (67) , Total House Hold - 2112. (2nd Call) (TSM/008992) (SM/09454) (AAFS- PH212245837S000) | Assistant Engineer | Junior Engineer | ORD/000005/2023-2024 | 765/BQA | 04/04/2023 | 26/08/2024 | RANABIR CHATTERJEE | 92.2 | 92.2 | 100 | 100
17 | BANKURA |  | Bankura Mechanical | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09454 | Augmentation | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. |  |  | BILL/01664/2023-2024 | BP-2023-24-177 | 22/03/2024 | 22/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.12 | 0 | 0 | 0
18 | BANKURA |  | Bankura Mechanical | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09454 | Augmentation | Acceptance cum Formal work order for the work of Name of Work:Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Rampur piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Sonamukhi Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 938/BMD | 12/05/2023 | 08/11/2023 | M/S BIPUL BANERJEE | 19.85 | 8.24 | 41.52 | 41
19 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09454 | Augmentation | Construction and commissioning of RCC Over Head Reservoir of capacity 350 cum and staging height 20 mtr.with allied works for Augmentation of Rampur Piped W/S underSonamukhi Block of Bankura Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/000448/2021-2022 | 548/BQA | 11/03/2022 | 09/06/2022 | SUBHANKAR BANERJEE | 66.77 | 65.23 | 97.7 | 95
20 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09454 | Augmentation | Sinking of 1 no 300mm X 200mm X 200m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe for Augmentation of Rampur water supply scheme under Bishnupur Sub-Division of Bankura Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000395/2022-2023 | 61/BQA | 05/01/2023 | 01/07/2025 | MAYA CONSTRUCTION | 18.74 | 13.74 | 73.32 | 95
21 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09454 | Augmentation | SOIL INVESTIGATION FOR 20 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN SONAMUKHI BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000414/2022-2023 | 352/BQA | 21/02/2023 | 23/03/2023 | G.MITRA AND ASSOCIATES | 18.88 | 15.11 | 80 | 100
22 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09454 | Augmentation | Laying distribution system including allied works for Augmentation of RAMPUR Piped W/S. Scheme of Sonamukhi block of Bankura District under Bankura Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/000049/2023-2024 | 903/BQA | 20/04/2023 | 31/05/2024 | UNIVERSAL CONSTRUCTION | 156.6 | 125.4 | 80.08 | 100
Total | [13 empty] | 503.28 | 352.92 | 70.12