## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Morar Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Block under Bishnupur Sub - Division of Bankura D | SM/09472 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Morar Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Basudebpur, No. of Mouza :- 19 nos. i.e. Gosainpur - 72,Gopalpur - 73,Jangal Bankati - 74, Radhadamodarpur - 75,Kamarpukur - 76, Belsulia - 109,Dumohani - 110,Bangele - 111, Siromonipur - 104,Moyra pukur - 105,Dhenga pathar - 106,Basudebpur - 107, Tribunka - 108, Hereparbbat - 77,Madhuban - 78,Chaugan - 102,Kural Bari-103,Dundure - 116,Pirragara - 120, Total House Hold - 2785 | Assistant Engineer | Junior Engineer | ORD/000027/2022-2023 | 1086/BQA | 12/05/2022 | 07/05/2023 | GOPAL CHANDRA CHOWDHURY | 235.11 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Morar Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Block under Bishnupur Sub - Division of Bankura D | SM/09472 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA at different Mouza's of Left out House Holds of Morar Zone-A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Benebandhi, No. of Mouza :- 7 nos. i.e.Dadwasbati-98, Kusumbani-99, Chougan-102, Dundure-116, Morar-117, Ghugimura-121, Jharia-122, Total House Hold -70 |  | Junior Engineer | ORD/000028/2022-2023 | 110/VSD | 19/04/2022 | 10/05/2022 | AJIT KUMAR DUTTA | 4.52 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Morar Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Block under Bishnupur Sub - Division of Bankura D | SM/09472 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Morar Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Basudebpur, No. of Mouza :- 01 no. i.e. Morar - 117, House Hold - 1806 |  | Junior Engineer | ORD/000392/2021-2022 | 203/BQA | 01/02/2022 | 02/04/2022 | M/S TARUN KUMAR PATRA | 171.51 | 154.02 | 89.8 | 0
4 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Morar Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Block under Bishnupur Sub - Division of Bankura D | SM/09472 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000007/2021-2022 | 271/BQA | 11/02/2022 | 11/02/2022 | Resource Division | 91.96 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Morar Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Block under Bishnupur Sub - Division of Bankura D | SM/09472 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000015/2021-2022 | 475/BQA | 04/03/2022 | 04/03/2022 | Resource Division | 11.11 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Morar Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Block under Bishnupur Sub - Division of Bankura D | SM/09472 | Retrofitting | Laying of UPVC pipeline for running drinking water supply arrangement to sumangalam home at Kharikasuli with in Morar post office within Bishnupur block under Morar zone - A water supply scheme (BRGF Bishnupur ) under Bishnupur sub - Division under Bankura Division, PHE Dte. |  |  | VCH/000280/2022-2023 | FHTC/26 | 26/04/2022 | 26/04/2022 | KOUSIK MONDAL | 2.58 | 0 | 0 | 0
Total | [13 empty] | 516.78 | 154.02 | 29.8