## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chak Muktapur (172), Pathar Kata (233), Maudi (234), Tunka (235), Hati Bari (255), Asan Bani (256), Agarda (257), Dhang Hari (258), Baga Khulia (259), Hetemoa (260), Jadab Na | SM/09478 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000003/2021-2022 | 2891/BQA | 22/11/2021 | 22/11/2021 | Resource Division | 165.74 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chak Muktapur (172), Pathar Kata (233), Maudi (234), Tunka (235), Hati Bari (255), Asan Bani (256), Agarda (257), Dhang Hari (258), Baga Khulia (259), Hetemoa (260), Jadab Na | SM/09478 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chak Muktapur (172), Pathar Kata (233), Maudi (234), Tunka (235), Hati Bari (255), Asan Bani (256), Agarda (257), Dhang Hari (258), Baga Khulia (259), Hetemoa (260), Jadab Nagar (261), Jagannath Bati (262), Bhaji Bari (263), Ramar Chun Puan (264), Agarda Purusottampur (271), Basuri Bera (272), Gopinathpur (273), Chak Tunka (274), Muktapur (275), Lauria (276) & Kanaijuri (277) mouzas by retrofitting Agarda and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household - 2536 nos. |  | Junior Engineer | ORD/000403/2021-2022 | 318/BQA | 22/02/2022 | 23/04/2022 | UNIVERSAL CONSTRUCTION | 123.11 | 40.63 | 33 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chak Muktapur (172), Pathar Kata (233), Maudi (234), Tunka (235), Hati Bari (255), Asan Bani (256), Agarda (257), Dhang Hari (258), Baga Khulia (259), Hetemoa (260), Jadab Na | SM/09478 | Retrofitting | Household survey in Chak Muktapur (172), Pathar Kata (233), Maudi (234), Tunka (235), Hati Bari (255), Asan Bani (256), Agarda (257), Dhang Hari (258), Baga Khulia (259), Hetemoa (260), Jadab Nagar (261), Jagannath Bati (262), Bhaji Bari (263), Ramar Chun Puan (264), Agarda Purusottampur (271), Basuri Bera (272), Gopinathpur (273), Chak Tunka (274), Muktapur (275), Lauria (276) & Kanaijuri (277) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Agarda and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000890/2021-2022 | 87/BSD | 28/01/2022 | 28/03/2022 | TAPAS DEY | 0.85 | 0 | 0 | 100
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chak Muktapur (172), Pathar Kata (233), Maudi (234), Tunka (235), Hati Bari (255), Asan Bani (256), Agarda (257), Dhang Hari (258), Baga Khulia (259), Hetemoa (260), Jadab Na | SM/09478 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000006/2021-2022 | 150/BQA | 27/01/2022 | 27/01/2022 | Resource Division | 11.94 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chak Muktapur (172), Pathar Kata (233), Maudi (234), Tunka (235), Hati Bari (255), Asan Bani (256), Agarda (257), Dhang Hari (258), Baga Khulia (259), Hetemoa (260), Jadab Na | SM/09478 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000027/2021-2022 | 567/BQA | 17/03/2022 | 17/03/2022 | Resource Division | 15.6 | 0 | 0 | 0
Total | [13 empty] | 317.24 | 40.63 | 12.81