## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Mandalkuli (Zone- IIIA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programm | SM/09496 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lakat (161), Sarigari (163), Makli (164), Satpatta (240), Mandankuli (241), Madanpur (242), Asurgerya (243), Belpahari (244), Amritpal (245), Chapapal (260), Dhekikata (261) & Dangarsai (262) mouzas under Mandalkuli (Zone-IIIA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 12 Nos. Total Household:- 2906 Nos. |  | Junior Engineer | ORD/000260/2021-2022 | 3169/BQA | 17/12/2021 | 15/02/2022 | GOPAL CHANDRA CHOUDHURY | 152.35 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Mandalkuli (Zone- IIIA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programm | SM/09496 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lakat (161), Sarigari (163), Makli (164), Satpatta (240), Mandankuli (241), Madanpur (242), Asurgerya (243), Belpahari (244), Amritpal (245), Chapapal (260), Dhekikata (261) & Dangarsai (262) mouzas under Mandalkuli (Zone-IIIA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 12 Nos. Total Household:- 2906 Nos. |  | Junior Engineer | ORD/000314/2021-2022 | 07/BQA | 03/01/2022 | 04/03/2022 | GOPAL CHANDRA CHOUDHURY | 152.35 | 152.74 | 100.26 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Mandalkuli (Zone- IIIA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programm | SM/09496 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Lakat (161), Sarigari (163), Makli (164) & Mandankuli (241) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Mandalkuli (Zone-IIIA) under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 17) |  | Junior Engineer | ORD/000645/2021-2022 | 747/BQA | 28/03/2022 | 07/04/2022 | GOPAL CHANDRA CHOWDHURY | 4.97 | 4.85 | 97.66 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Mandalkuli (Zone- IIIA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programm | SM/09496 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Satpatta (240), Madanpur (242) & Asurgerya (243) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Mandalkuli (Zone-IIIA) under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 29) |  | Junior Engineer | ORD/000646/2021-2022 | 759/BQA | 28/03/2022 | 07/04/2022 | GOPAL CHANDRA CHOWDHURY | 4.96 | 4.86 | 98.1 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Mandalkuli (Zone- IIIA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programm | SM/09496 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Belpahari (244), Amritpal (245), Chapapal (260), Dhekikata (261) & Dangarsai (262) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Mandalkuli (Zone-IIIA) under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 31) |  | Junior Engineer | ORD/000647/2021-2022 | 761/BQA | 28/03/2022 | 07/04/2022 | GOPAL CHANDRA CHOWDHURY | 4.95 | 4.47 | 90.37 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Mandalkuli (Zone- IIIA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programm | SM/09496 | Retrofitting | Household survey in Lakat ( 161) Sarigari (163) Makli (164) Satpatta (240) Mandankuli (241) Madanpur (242) dhekikata (260) & Dhekikata ( 262) mouza Mandalkuli zone IIIA to provide of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. sl no - 17 |  |  | VCH/000453/2022-2023 | FHTC/6 | 06/06/2022 | 06/06/2022 | TAPAS DEY | 0.73 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Mandalkuli (Zone- IIIA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programm | SM/09496 | Retrofitting | Work Order for Household survey in Lakat (161), Sarigari (163), Makli (164), Satpatta (240), Mandankuli (241), Madanpur (242), Asurgerya (243), Belpahari (244), Amritpal (245), Chapapal (260), Dhekikata (261) & Dangarsai (262) mouzas under Mandalkuli (Zone-IIIA) to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 17) |  | Junior Engineer | ORD/000681/2021-2022 | 856/KSD | 31/12/2021 | 31/03/2022 | TAPAS DEY | 0.97 | 0.23 | 24.26 | 0
Total | [13 empty] | 321.26 | 167.16 | 52.03