## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Mandalkuli (Zone-IIIB) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme | SM/09497 | Retrofitting | Household survey in Sagarchaka (258) Kamalpur (259) siribani (311) chamtabaid (312) Dhau ( 316) Pakadihi ( 318) Melara (319) mouzas under Mandalkuli (Zone-IIIB) to provide of ¿FHTC (Functional House Hold Tap Connection)¿ in by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme. sl no - 18 |  |  | VCH/000462/2022-2023 | FHTC/6 | 06/06/2022 | 06/06/2022 | TAPAS DEY | 0.41 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Mandalkuli (Zone-IIIB) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme | SM/09497 | Retrofitting | Work Order for Household survey in Sagarchaka (258), Kamalpur (259), Sirisbani (311), Chamtabaid (312), Phulkusma (313), Namosol (314), Mandaldiha (315), Dhau (316), Benagerya (317), Pakadihi (318) & Melera (319) mouzas under Mandalkuli (Zone-IIIB) to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 18) |  | Junior Engineer | ORD/000682/2021-2022 | 857/KSD | 31/12/2021 | 31/03/2022 | TAPAS DEY | 1.11 | 0.56 | 50.8 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Mandalkuli (Zone-IIIB) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme | SM/09497 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ with laying of HDPE pipeline in Sagarchaka (258), Namosol (314) & Phulkusma (313) mouza by retrofitting of Mandalkuli (Zone-IIIB) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000668/2022-2023 | 510/BQA | 13/03/2023 | 27/04/2023 | GOPAL CHANDRA CHOWDHURY | 19.91 | 19.76 | 99.27 | 50
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Mandalkuli (Zone-IIIB) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme | SM/09497 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sagarchaka (258), Kamalpur (259), Sirisbani (311), Chamtabaid (312), Phulkusma (313), Namosol (314), Mandaldiha (315), Dhau (316), Benagerya (317), Pakadihi (318) & Melera (319) mouzas under Mandalkuli (Zone-IIIB) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 11 Nos. Total Household:- 3319 Nos. | Assistant Engineer | Junior Engineer | ORD/000313/2021-2022 | 06/BQA | 03/01/2022 | 04/03/2022 | GOPAL CHANDRA CHOUDHURY | 160.06 | 151.02 | 94.35 | 65
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas under Mandalkuli (Zone-IIIB) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme | SM/09497 | Retrofitting | Repairing and laying of UPVC pipe for Distribution Main along with allied works from Phulkusma Bazar to Durga Mandir [damage done during making of cement concrete road from Phulkusma Bazar to Durgamandir by Bankura Zilla Parishad] of Water Supply Scheme for Mandalkuli, Zone-IIIB under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dt | Assistant Engineer | Junior Engineer | ORD/001151/2023-2024 | 361/BQA | 06/02/2024 | 22/03/2024 | SUBHADIP KOLE | 2.82 | 0 | 0 | 0
Total | [13 empty] | 184.3 | 171.34 | 92.97