## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kama (65), Benkakocha (66), Kulam (67), Makhnu (68), Chaltha (71), Bethuala (72), Panijia (73), Pithagerya (74), Ghagra (115), Jamgerya (117), Maula (118), Katiam (119), Mith | SM/09498 | Retrofitting | Household survey in Kama (65), Benkakocha (66) Kulam (67), chalthat (71) Jamperya (117) Maula (118) Mitha -Am (122) & Laladi (155) mouzas retrofitting Zone- K (Makhnu), of improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/003067/2021-2022 | FHTC/30 | 30/03/2022 | 30/03/2022 | TAPAS DEY | 0.54 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kama (65), Benkakocha (66), Kulam (67), Makhnu (68), Chaltha (71), Bethuala (72), Panijia (73), Pithagerya (74), Ghagra (115), Jamgerya (117), Maula (118), Katiam (119), Mith | SM/09498 | Retrofitting | Laying 100mm and 150 mm dia DI pipeline at Routara (129) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000471/2022-2023 | 286/BQA | 13/02/2023 | 30/03/2023 | ASOKE KUMAR SAHU | 2.03 | 0 | 0 | 20
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kama (65), Benkakocha (66), Kulam (67), Makhnu (68), Chaltha (71), Bethuala (72), Panijia (73), Pithagerya (74), Ghagra (115), Jamgerya (117), Maula (118), Katiam (119), Mith | SM/09498 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000014/2021-2022 | 453/BQA | 03/03/2022 | 03/03/2022 | Resource Division | 16.1 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kama (65), Benkakocha (66), Kulam (67), Makhnu (68), Chaltha (71), Bethuala (72), Panijia (73), Pithagerya (74), Ghagra (115), Jamgerya (117), Maula (118), Katiam (119), Mith | SM/09498 | Retrofitting | Work Order for Household survey in Kama (65), Benkakocha (66), Kulam (67), Makhnu (68), Chaltha (71), Bethuala (72), Panijia (73), Pithagerya (74), Ghagra (115), Jamgerya (117), Maula (118), Katiam (119), Mitha-Am (122) & Laladi (155) mouzas to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Zone- K (Makhnu) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 19) | Assistant Engineer | Junior Engineer | ORD/000683/2021-2022 | 858/KSD | 31/12/2021 | 16/02/2025 | TAPAS DEY | 0.98 | 0 | 0 | 70
Total | [13 empty] | 19.65 | 0 | 0