## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 22 nos. mouzas (Alutia, Chholagasa, Satkhulia, Tilajuri, Aljharia, Dhengagora, Bagmara, Katharia, Bijpur, Siulib | SM/09499 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JAMTORA (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jamtora, No. of Mouza :- 22 nos, (Bagmara, Katharia, Bijpur, Siulibona, Palla, Sigergara, Dumda, Alutia, Chholagasa, Satkhulia, Tilajuri, Aljhara, Dhengagora, Bankati, Jamtora, Meghakata, Dhagara, Nanduara, Aturibana, Chhopania, Karkari, Garbona), Total House Hold - 2721 nos. |  | Junior Engineer | ORD/000249/2021-2022 | 3362/BQA | 31/12/2021 | 01/03/2022 | M/S D.K.H CONSTRUCTION | 155.31 | 57.13 | 36.79 | 0
2 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 22 nos. mouzas (Alutia, Chholagasa, Satkhulia, Tilajuri, Aljharia, Dhengagora, Bagmara, Katharia, Bijpur, Siulib | SM/09499 | Retrofitting | Survey work for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JAMTORA (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jamtora, No. of Mouza :- 22, Name of mouza:- Alutia [194], Chholagasa [192], Satkhulia [178], Tilajuri [173], Aljharia [182], Dhengagora [183), Bagmara [185], Katharia [174], Bijpur [188], Siulibona [189], Palla [195], Sigergara [175], Dumda [172], Bankati [181], Jamtora [180], Meghakata [187], Dhagara [186], Nanduara [184], Aturibana [179], Chhopania [177], Karkari [176] & Garbona [191], Total House Hold - 2721 nos. |  | Junior Engineer | ORD/000555/2021-2022 | 70/BSD | 14/01/2022 | 14/04/2022 | TAPAS DEY | 0.91 | 0.83 | 91.44 | 0
3 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 22 nos. mouzas (Alutia, Chholagasa, Satkhulia, Tilajuri, Aljharia, Dhengagora, Bagmara, Katharia, Bijpur, Siulib | SM/09499 | Retrofitting | Laying Extra HDPE Pipe Line to Cover Palla, Karkari mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JAMTORA (Zone - G) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000270/2022-2023 | 340/KSD | 16/08/2022 | 05/09/2022 | M/S D.K.H CONSTRUCTION | 2.88 | 2.88 | 100 | 0
4 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 22 nos. mouzas (Alutia, Chholagasa, Satkhulia, Tilajuri, Aljharia, Dhengagora, Bagmara, Katharia, Bijpur, Siulib | SM/09499 | Retrofitting | Laying Extra HDPE Pipe Line to Cover Meghakata, Chholagasa mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JAMTORA (Zone - G) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000271/2022-2023 | 336/KSD | 16/08/2022 | 05/09/2022 | M/S D.K.H CONSTRUCTION | 4.11 | 4.11 | 100 | 0
5 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 22 nos. mouzas (Alutia, Chholagasa, Satkhulia, Tilajuri, Aljharia, Dhengagora, Bagmara, Katharia, Bijpur, Siulib | SM/09499 | Retrofitting | Laying Extra HDPE Pipe Line to Cover Siulibona, Alutia mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JAMTORA (Zone - G) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000272/2022-2023 | 338/KSD | 16/08/2022 | 05/09/2022 | M/S D.K.H CONSTRUCTION | 4.32 | 4.32 | 100 | 0
6 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 22 nos. mouzas (Alutia, Chholagasa, Satkhulia, Tilajuri, Aljharia, Dhengagora, Bagmara, Katharia, Bijpur, Siulib | SM/09499 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of JAMTORA (Zone - G) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jamtora, No. of Mouza :- 22 nos, (Bagmara, Katharia, Bijpur, Siulibona, Palla, Sigergara, Dumda, Alutia, Chholagasa, Satkhulia, Tilajuri, Aljhara, Dhengagora, Bankati, Jamtora, Meghakata, Dhagara, Nanduara, Aturibana, Chhopania, Karkari, Garbona), Total House Hold - 2721 nos. |  |  | VCH/003063/2021-2022 | FHTC/30 | 30/03/2022 | 30/03/2022 | M/S D.K.H CONSTRUCTION | 98.17 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 22 nos. mouzas (Alutia, Chholagasa, Satkhulia, Tilajuri, Aljharia, Dhengagora, Bagmara, Katharia, Bijpur, Siulib | SM/09499 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dighi (85) mouza by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 07) |  |  | VCH/001487/2022-2023 | FHTC/19 | 19/12/2022 | 19/12/2022 | PRADYUMNA KOLEY | 2.23 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 22 nos. mouzas (Alutia, Chholagasa, Satkhulia, Tilajuri, Aljharia, Dhengagora, Bagmara, Katharia, Bijpur, Siulib | SM/09499 | Retrofitting | Laying HDPE pipeline to increase pressure in Malian (23) Mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-Malian of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 03) |  |  | VCH/001484/2022-2023 | FHTC/19 | 19/12/2022 | 19/12/2022 | SUBHANKAR BANERJEE | 4.67 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 22 nos. mouzas (Alutia, Chholagasa, Satkhulia, Tilajuri, Aljharia, Dhengagora, Bagmara, Katharia, Bijpur, Siulib | SM/09499 | Retrofitting | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-III W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte Block - Saltora, G.P. - Salma, No.of Mouza :- 01 no., (Kendana), Total House Hold - 272 nos |  |  | VCH/001486/2022-2023 | FHTC/19 | 19/12/2022 | 19/12/2022 | SK. SAHAJAHAN | 12.79 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 22 nos. mouzas (Alutia, Chholagasa, Satkhulia, Tilajuri, Aljharia, Dhengagora, Bagmara, Katharia, Bijpur, Siulib | SM/09499 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA at different Mouza's of Left out House Holds of Chakuparsole Zone - A & Zone-B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Majuria, No. of Mouza :-12 nos. i.e.Majuria-135, Dhabani-136, Chitrang-137, Indkuri-139, Majdiha-142, Hatiaghora-143, Chanchar-144, Amdohara-147, Choto Bankadaha-148, Bharamara-149, Dhandol-153, Pholbani-154, Total House Hold -65 |  |  | VCH/001483/2022-2023 | FHTC/19 | 19/12/2022 | 19/12/2022 | AJIT KUMAR DUTTA | 4.07 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 22 nos. mouzas (Alutia, Chholagasa, Satkhulia, Tilajuri, Aljharia, Dhengagora, Bagmara, Katharia, Bijpur, Siulib | SM/09499 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Phulberia (278) & Dhanara (279) mouzas by retrofitting of Piped Water Supply Scheme for Dhanara & Its Adjoining Mouzas at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/001490/2022-2023 | FHTC/19 | 19/12/2022 | 19/12/2022 | EARTH MOVING (INDIA) | 4.62 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 22 nos. mouzas (Alutia, Chholagasa, Satkhulia, Tilajuri, Aljharia, Dhengagora, Bagmara, Katharia, Bijpur, Siulib | SM/09499 | Retrofitting | Reconstruction concrete at Jolhari mouza for construction and commissioning of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhaban (Zone - A) under Chhatna- Block of Saltora-Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub- Division of Bankura Division PHE Dte. |  |  | VCH/001501/2022-2023 | FHTC/27 | 27/12/2022 | 27/12/2022 | TAPAS KUMBHAKAR | 4.31 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 22 nos. mouzas (Alutia, Chholagasa, Satkhulia, Tilajuri, Aljharia, Dhengagora, Bagmara, Katharia, Bijpur, Siulib | SM/09499 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chak Muktapur (172), Pathar Kata (233), Maudi (234), Tunka (235), Hati Bari (255), Asan Bani (256), Agarda (257), Dhang Hari (258), Baga Khulia (259), Hetemoa (260), Jadab Nagar (261), Jagannath Bati (262), Bhaji Bari (263), Ramar Chun Puan (264), Agarda Purusottampur (271), Basuri Bera (272), Gopinathpur (273), Chak Tunka (274), Muktapur (275), Lauria (276) & Kanaijuri (277) mouzas by retrofitting Agarda and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte.Total Household - 2536 nos. |  |  | VCH/001491/2022-2023 | FHTC/19 | 19/12/2022 | 19/12/2022 | UNIVERSAL CONSTRUCTION | 21.12 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 22 nos. mouzas (Alutia, Chholagasa, Satkhulia, Tilajuri, Aljharia, Dhengagora, Bagmara, Katharia, Bijpur, Siulib | SM/09499 | Retrofitting | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 01 no., (Barachaka), Total House Hold- 60 nos. |  |  | VCH/001485/2022-2023 | FHTC/19 | 19/12/2022 | 19/12/2022 | BASUDEB ACHARJEE | 4.07 | 0 | 0 | 0
Total | [13 empty] | 323.57 | 69.27 | 21.41