## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136), Suritari (139), Kanthalia (140), Gobindasol (141), Bheduasol (142), Muchikata (143), Churku (144) & Syamadihi (145) mouzas by retrofitting Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 18 Nos. Total Household:- 3581 Nos. |  | Junior Engineer | ORD/000316/2021-2022 | 09/BQA | 03/01/2022 | 04/03/2022 | GOPAL CHANDRA CHOUDHURY | 210.38 | 210.32 | 99.97 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Suritari (139) (Part) & Kanthalia (140) (Part) mouzas for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 18) |  | Junior Engineer | ORD/000506/2021-2022 | 748/BQA | 28/03/2022 | 07/04/2022 | GOPAL CHANDRA CHOWDHURY | 4.89 | 4.88 | 99.88 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Rudra (38), Mahespur (52), Chirkun Kanali (54) & Budh Khila (60) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone-J (Rudra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 20) |  | Junior Engineer | ORD/000507/2021-2022 | 750/BQA | 28/03/2022 | 07/04/2022 | GOPAL CHANDRA CHOWDHURY | 2.53 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Rautara (129) (Part) & Bansdiha (130) (Part) mouzas for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 22) |  | Junior Engineer | ORD/000508/2021-2022 | 752/BQA | 28/03/2022 | 07/04/2022 | GOPAL CHANDRA CHOWDHURY | 4.87 | 4.87 | 99.97 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Rautara (129) mouza (Part) for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 26) |  | Junior Engineer | ORD/000509/2021-2022 | 756/BQA | 28/03/2022 | 07/04/2022 | GOPAL CHANDRA CHOWDHURY | 4.98 | 4.98 | 99.92 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Tamakhun (62) mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-J (Rudra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 28) |  | Junior Engineer | ORD/000510/2021-2022 | 758/BQA | 28/03/2022 | 07/04/2022 | GOPAL CHANDRA CHOWDHURY | 4.45 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Bansdiha (130) (Part) & Jhilimili (131) (Part) mouzas for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 05) |  | Junior Engineer | ORD/000502/2021-2022 | 738/BQA | 28/03/2022 | 07/04/2022 | GOPAL CHANDRA CHOWDHURY | 4.72 | 4.7 | 99.63 | 0
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Jhilimili (131) (Part) & Bhurrudanga (133) mouzas for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 09) |  | Junior Engineer | ORD/000503/2021-2022 | 741/BQA | 28/03/2022 | 07/04/2022 | GOPAL CHANDRA CHOWDHURY | 4.97 | 4.97 | 99.99 | 0
9 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Kanthalia (140) (Part), Muchikata (143), Churku (144) & Syamadihi (145) mouzas for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 12) |  | Junior Engineer | ORD/000504/2021-2022 | 743/BQA | 28/03/2022 | 07/04/2022 | GOPAL CHANDRA CHOWDHURY | 3.78 | 3.78 | 99.99 | 0
10 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Serengda (135), Tilabani (136) & Suritari (139) (Part) mouzas for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 16) |  | Junior Engineer | ORD/000505/2021-2022 | 746/BQA | 28/03/2022 | 07/04/2022 | GOPAL CHANDRA CHOWDHURY | 4.95 | 4.94 | 99.93 | 0
11 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Kasakend (134) mouza for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- A) (Sl. No. 22) |  | Junior Engineer | ORD/000525/2021-2022 | 83/KSD | 09/03/2022 | 19/03/2022 | GOPAL CHANDRA CHOWDHURY | 4.98 | 4.96 | 99.63 | 0
12 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Kasakend (134) mouza for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part- B) (Sl. No. 23) |  | Junior Engineer | ORD/000526/2021-2022 | 84/KSD | 09/03/2022 | 19/03/2022 | GOPAL CHANDRA CHOWDHURY | 4.99 | 4.99 | 99.97 | 0
13 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | Laying extra HDPE pipeline to cover Jhilimili (131) part & Bhurrudanga ( 133) mouza Construction and commissioning of FHTC (Functional House Hold Tap Connection) in work of Zone-N (Khejuria), by improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme.under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 09 |  |  | VCH/000564/2022-2023 |  | 18/07/2022 | 18/07/2022 | GOPAL CHANDRA CHOWDHURY | 4.97 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | Laying extra HDPE pipeline to cover Bansdiha (130) part & Jhilimili (131) part mouza Construction and commissioning of FHTC (Functional House Hold Tap Connection) in work of Zone-N (Khejuria), by improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme.under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 05 |  |  | VCH/000563/2022-2023 |  | 18/07/2022 | 18/07/2022 | GOPAL CHANDRA CHOWDHURY | 4.7 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | Laying extra HDPE pipeline to cover Suritari ( 139) part & Kanthalia (140) part mouza Construction and commissioning of FHTC (Functional House Hold Tap Connection) in work of Zone-N (Khejuria), by improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme.under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 16 |  |  | VCH/000566/2022-2023 |  | 18/07/2022 | 18/07/2022 | GOPAL CHANDRA CHOWDHURY | 4.88 | 0 | 0 | 0
16 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | Laying extra HDPE pipeline to cover Rautara( 129) mouza part Construction and commissioning of FHTC (Functional House Hold Tap Connection) in work of Zone-N (Khejuria), by improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme.under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 26 |  |  | VCH/000561/2022-2023 |  | 18/07/2022 | 18/07/2022 | GOPAL CHANDRA CHOWDHURY | 4.98 | 0 | 0 | 0
17 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | Laying extra HDPE pipeline to cover Kanthalia (140) part Muchikata (143) churku (144) & Syamadihi (145) mouza Construction and commissioning of FHTC (Functional House Hold Tap Connection) in work of Zone-N (Khejuria), by improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme.under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 12 |  |  | VCH/000567/2022-2023 |  | 18/07/2022 | 18/07/2022 | GOPAL CHANDRA CHOWDHURY | 3.78 | 0 | 0 | 0
18 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | Household survey in Gunpura (126), Khejura (127) Ramgal (128), Rautara (129) Tilabani (136) Suritari (139) Kanthalia (140) Gobindasol (141 ) .......... mouzas reation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Zone - N (Khejuria ) of improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh & Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. sl no - 20 |  |  | VCH/000245/2022-2023 | FHTC/12 | 12/04/2022 | 12/04/2022 | TAPAS DEY | 0.65 | 0 | 0 | 0
19 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | Laying extra HDPE pipeline to cover Sarengda (135) tilabani ( 136) & Suritari ( 139) part mouza Construction and commissioning of FHTC (Functional House Hold Tap Connection) in work of Zone-N (Khejuria), by improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme.under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 16 |  |  | VCH/000565/2022-2023 |  | 18/07/2022 | 18/07/2022 | GOPAL CHANDRA CHOWDHURY | 4.94 | 0 | 0 | 0
20 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | Laying extra HDPE pipeline to cover Rautara( 129) mouza part & Bansdiha (130) part Construction and commissioning of FHTC (Functional House Hold Tap Connection) in work of Zone-N (Khejuria), by improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme.under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 22 |  |  | VCH/000562/2022-2023 |  | 18/07/2022 | 18/07/2022 | GOPAL CHANDRA CHOWDHURY | 4.87 | 0 | 0 | 0
21 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | Work Order for Household survey in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136), Suritari (139), Kanthalia (140), Gobindasol (141), Bheduasol (142), Muchikata (143), Churku (144) & Syamadihi (145) mouzas to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Zone- N (Khejuria) of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 20) |  | Junior Engineer | ORD/000684/2021-2022 | 859/KSD | 31/12/2021 | 31/03/2022 | TAPAS DEY | 1.19 | 0.55 | 45.88 | 0
22 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | Work Order for Supply, Delivery and Stacking of C.I.D.F. Sluice Valve for ¿FHTC (Functional House Hold Tap Connection)¿ work of Chiltore & its adjoining mouzas water supply scheme under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) |  | Junior Engineer | ORD/000596/2022-2023 | 171/KSD | 17/05/2022 | 06/06/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 0.97 | 0.97 | 100 | 0
23 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | Extra pipe line for increase pressure Gosaipur, Gobindrapur & Godhardihi retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) of GADARDIHI (Zone- E) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph- I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora. | Assistant Engineer | Junior Engineer | ORD/000826/2022-2023 | 216/BSD | 28/02/2023 | 15/03/2023 | SONU SINGH | 0.97 | 0.97 | 100 | 0
24 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gunpura (126), Khejura (127), Ramgar (128), Rautara (129), Bansdiha (130), Jhilimili (131), Sereshbad (132), Bhurrudanga (133), Kasakend (134), Serengda (135), Tilabani (136) | SM/09500 | Retrofitting | UPVC pipe line damaged during construction of drain from the end of Indas Panchayat samity in connection with Jal Jeevan Mission (JJM) of Indas Water Supply scheme under Bishnupur Sub Division PHE Dte of Bankura Division PHE Dte. |  | Junior Engineer | ORD/000820/2022-2023 | 23/VSD | 15/02/2023 | 16/02/2023 | SONU SINGH | 0.15 | 0.15 | 98.96 | 0
Total | [13 empty] | 297.54 | 256.03 | 86.05