## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Murakata Ghosh Para, Total House Hold -75 |  | Junior Engineer | ORD/000469/2020-2021 | 562/ BSD | 13/11/2020 | 04/12/2020 | SOMA BANERJEE | 4.81 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Lobason Bauri Para, Total House Hold -76 |  | Junior Engineer | ORD/000465/2020-2021 | 558/ BSD | 13/11/2020 | 04/12/2020 | TAPAS PAL | 4.85 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- Murakata Roy Para, Total House Hold -75 |  | Junior Engineer | ORD/000468/2020-2021 | 561/ BSD | 13/11/2020 | 04/12/2020 | ASHIS PAL | 4.8 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , G.P -Chandar , Name of Village Kadakuli Man Para, Total House Hold -70 |  | Junior Engineer | ORD/000463/2020-2021 | 556/ BSD | 13/11/2020 | 04/12/2020 | GON ASSOCIATES | 4.59 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P- Chandar, Name of Village-Lobason Roy Para, Total House Hold -73 |  | Junior Engineer | ORD/000466/2020-2021 | 559/ BSD | 13/11/2020 | 04/12/2020 | M/S BANERJEE & BANERJEE | 4.71 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- Lobason Maheswa Para, Total House Hold -75 |  | Junior Engineer | ORD/000467/2020-2021 | 560/ BSD | 13/11/2020 | 04/12/2020 | SOMENATH ACHARYYA | 4.81 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Kadakuli Roy Para, Total House Hold -75 |  | Junior Engineer | ORD/000464/2020-2021 | 557/ BSD | 13/11/2020 | 04/12/2020 | SANJOY MONDAL | 4.82 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Murakata ,Chandar Durgamondir para (part), Total House Hold -45. |  | Junior Engineer | ORD/000477/2020-2021 | 13/BSD | 06/01/2021 | 27/01/2021 | JAGADISH BANERJEE | 4.73 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Lobason Bauri Para, Chandar Shib mondir Namo Para & Brimhon para Total House Hold -50. |  | Junior Engineer | ORD/000472/2020-2021 | 26/BSD | 06/01/2021 | 27/01/2021 | M/S PAUL BROTHERS | 4.7 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- ChandarBardgan Para (Part- A), Total House Hold -50. |  | Junior Engineer | ORD/000478/2020-2021 | 27/BSD | 06/01/2021 | 27/01/2021 | MAYA CONSTRUCTION | 4.44 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Chandar Bardgan Para (Part- B), Total House Hold - 50. |  | Junior Engineer | ORD/000479/2020-2021 | 14/BSD | 06/01/2021 | 27/01/2021 | TAPAN KUMAR UPADHYAY | 4.48 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- By pass Pipe line Kadakuli more to Chandar main Bazar, Gosh para ,Chandar maibazar Total House Hold -20 |  | Junior Engineer | ORD/000493/2020-2021 | 28 / BSD | 06/01/2021 | 27/01/2021 | BIDHAN BANERJEE | 4.84 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- By pass Pipe line Chandar main Bazar to Chandar gram end & Baroma kali than (Chomatha), Bramhon para (Part), Chandar maibazar, Total House Hold -25. |  | Junior Engineer | ORD/000475/2020-2021 | 29/BSD | 06/01/2021 | 27/01/2021 | SOMENATH ACHARYYA | 4.81 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Chandar Bardgan Para (Part- C), Total House Hold -50. |  | Junior Engineer | ORD/000480/2020-2021 | 30/BSD | 06/01/2021 | 27/01/2021 | MANAS DEY | 4.56 | 0 | 0 | 10
15 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , G.P -Chandar, Name of Village - Kadakuli Man Para, Chandar Bramhon Para & Chatterjee para Total House Hold -40. |  | Junior Engineer | ORD/000470/2020-2021 | 31/BSD | 06/01/2021 | 27/01/2021 | GON ASSOCIATES | 4.47 | 0 | 0 | 10
16 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Kadakuli Roy Para, Chandar Rail line para, school , health center, Total House Hold -52. |  | Junior Engineer | ORD/000471/2020-2021 | 10/BSD | 06/01/2021 | 27/01/2021 | SANJOY MONDAL | 4.8 | 0 | 0 | 0
17 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- Murakata ,Main road to durga mondir (Part), Total House Hold -35. |  | Junior Engineer | ORD/000476/2020-2021 | 12/BSD | 06/01/2021 | 27/01/2021 | ASHIS PAL | 4.75 | 0 | 0 | 0
18 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- By pass Pipe line Kadakuli more to Chandar main Bazar, Gosh para ,Chandar maibazar Total House Hold -20. |  | Junior Engineer | ORD/000474/2020-2021 | 28/BSD | 06/01/2021 | 27/01/2021 | BIDHAN BANERJEE | 4.84 | 0 | 0 | 0
19 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P- Chandar, Name of Village-Lobason Roy Para, Chandar main road to Bhramhon para, Dom para, Total House Hold -34. |  | Junior Engineer | ORD/000473/2020-2021 | 11/BSD | 06/01/2021 | 27/01/2021 | M/S BANERJEE & BANERJEE | 4.83 | 0 | 0 | 0
20 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BELIATORE Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name. of Mouza :- Murakata, Total House Hold - 45 nos. |  | Junior Engineer | ORD/000873/2021-2022 | 12/BSD | 07/01/2022 | 22/01/2022 | BIDHAN BANERJEE | 4.98 | 0 | 0 | 0
21 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BELIATORE Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name. of Mouza :- Nabasan, Total House Hold - 35 nos. |  | Junior Engineer | ORD/000874/2021-2022 | 10/BSD | 07/01/2022 | 22/01/2022 | SOMENATH ACHARYYA | 4.9 | 0 | 0 | 65
22 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BELIATORE Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name. of Mouza :- Chhandar (Part), Total House Hold - 40 nos. |  | Junior Engineer | ORD/000875/2021-2022 | 11/BSD | 07/01/2022 | 22/01/2022 | SOMENATH ACHARYYA | 4.98 | 0 | 0 | 0
23 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-3) DPR no - 36.Block - Bishnupur,Name of OHR - Bhara,No. of Mouza :- 1 no. i.e.Shaluka - 21(110 out of 125) House Hold - 110 |  |  | VCH/002352/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | MRITYUNJOY HAZRA | 8.3 | 0 | 0 | 0
24 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | extra UPVC pipe line of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYKRISHNAPUR (Zone - I) ) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block -Barjora, Name of OHR - JOYKRISHNAPUR (Zone- I) Name of mouza - 03 nos, Phulberia (PART- B), Sirsa & Joykrishna pur Sarenga (PART- A) |  |  | VCH/002351/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | M/S T.P. HAZRA & SONS | 3.25 | 0 | 0 | 0
25 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 01, Magra(PART-II )Total House Hold - 139.' |  |  | VCH/002346/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | TAPAN KUMAR UPADHYAY | 2.37 | 0 | 0 | 0
26 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Work Order for Laying extra HDPE pipeline to cover Simlabandh (45) & Bhedua (46) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No.- 13), |  |  | VCH/002333/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | GANESH ROY | 4.98 | 0 | 0 | 0
27 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of PANCHAL W/S Scheme (Zone - I) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Sonamukhi, Name of OHR - Jamdoba. No. of Mouza :- 3 nos. i.e. Jamdoba-154, Ichharia-155 and Bhabanipur- 165 , Habitation's Name : Jamdoba, Roypara, Tantipara,Ichharia,Dhallapara,Amchura, Kalaberia, Kalyanpur,Bhramanpara,Bhabanipur & Murhura. Total House Hold - 162 |  |  | VCH/002345/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | MOHAN KUMAR ROY | 4.69 | 0 | 0 | 0
28 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 ( Barapukura), Total House Hold -114 |  |  | VCH/002347/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | TAPAN KUMAR SARKAR | 1.1 | 0 | 0 | 0
29 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creacion of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of SHYAMPUR (Zone - E) under Saltora-Block , Saitora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Shyampur, No.of Mouza :- 01, Shyampu (part) Total House Hold - 453. |  |  | VCH/002809/2021-2022 | FHTC/5 | 05/03/2022 | 05/03/2022 | GOUTAM BHATTACHRYYA | 27.54 | 0 | 0 | 0
30 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Betanal Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-2) DPR no. 43Block - Indas, Name of OHR - Dighalgram, No. of Mouza :- 02 nos. i.e. Barabaikunthapur-125 & Habispur-127 , Total House Hold - 245 (245 out of 549) |  |  | VCH/002335/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | TAPAN KUMAR MANDAL | 16.4 | 0 | 0 | 0
31 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of DADHIMUKHA (Zone - D) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - DADHIMUKHA (Zone - D) . No.of Mouza :- 02 , (Saldanga , Muktapur ), Total House Hold -253 |  |  | VCH/002334/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | SUBHENDU SEKHAR GORAI | 1.78 | 0 | 0 | 0
32 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. (Phase-5) DPR no - 35. Block - Bishnupur, Name of OHR - Bhara, No. of Mouza :- 1 no. i.e. Bhara- 24 ( 455 out of 714), Total House Hold - 455 |  |  | VCH/002344/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | AMIYA KUMAR BIT | 35.44 | 0 | 0 | 0
33 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P - Chandar, Name of Village- Lobason Maheswa Para, Total House Hold -75 |  |  | VCH/002349/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | SOMENATH ACHARYYA | 4.79 | 0 | 0 | 0
34 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 03 (Ladna, Mathana, Kodalia(PART-A)), Total House Hold -430 |  |  | VCH/002353/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | UNIVERSAL CONSTRUCTION | 34.9 | 0 | 0 | 0
35 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P- Chandar, Name of Village-Lobason Roy Para, Chandar main road to Bhramhon para, Dom para, Total House Hold -34. |  |  | VCH/002348/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | M/S BANERJEE & BANERJEE | 4.81 | 0 | 0 | 0
36 | BANKURA |  | Bankura Division | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 05 Nos. Mouzas {Nabasan (150), Chhandar (151), Murakata (153), Pataspur (154) & Chandaibot Ramchandrapur (156)} | SM/09501 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Mukundapur (114), Khakrakanali (115) & Nagri (116) mouzas by retrofitting Zone-G (Kadra) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Khatra, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/002350/2021-2022 | FHTC/25 | 25/01/2022 | 25/01/2022 | APEX ENTERPRISE | 6.7 | 0 | 0 | 0
Total | [13 empty] | 261.56 | 0 | 0