## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Mahesana, Bhuinya Pasa, Budhanpur, Rahir, Chaka, Sanotalpara, A | SM/09502 | Retrofitting | Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of BAKSIBANDH (Zone - J) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Baksibandh, No.of Mouza :- 17 nos, (Mahesana, Bhudhanpur, Bhuinyapara, Rahir, Chaka, Sanotalpara, Antkuria, Maheskhapur, Khaerboni, Chaintore, Panjangora, Bakshibandh, Khobradihi, Amlatora, Upordihi, Chinabari, Amakunda ), Total House Hold - 2274 nos. |  | Junior Engineer | ORD/000251/2021-2022 | 3374/ BQA | 31/12/2021 | 01/03/2022 | ASHISH KUMAR SAMANTA | 115.16 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Mahesana, Bhuinya Pasa, Budhanpur, Rahir, Chaka, Sanotalpara, A | SM/09502 | Retrofitting | Laying of HDPE pipe Line from Chaka Adibasi Para to Samsanghat of Chhatna block under Saltora -Chhatna W/S Scheme under BQA (HQ) of Bankura Division P.H.E. Dte. |  | Junior Engineer | ORD/000626/2021-2022 | 693/BSD | 11/06/2021 | 26/06/2021 | SIB SANKAR CHOWDHURY | 3.94 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Mahesana, Bhuinya Pasa, Budhanpur, Rahir, Chaka, Sanotalpara, A | SM/09502 | Retrofitting | Survey work for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of BAKSIBANDH (Zone - J) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Baksibandh, No. of Mouza :- 17 nos., (Mahesana [206], BhuinyaPasa [207], Budhanpur [208], Rahir [242], Chaka [211], Sanotalpa [209], Antkuria [213], Maheskhuri [204], Khaerboni [212], Chaintore [205], Panjongora [210], Baksibandh [203], Khobradihi [216], Amlatore [215], Upordihi [214], Chinabari [202] & Amakunda [190] , Total House Hold - 2274 nos. |  | Junior Engineer | ORD/000554/2021-2022 | 71/BSD | 14/01/2022 | 14/04/2022 | TAPAS DEY | 0.76 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Mahesana, Bhuinya Pasa, Budhanpur, Rahir, Chaka, Sanotalpara, A | SM/09502 | Retrofitting | Laying of HDPE pipe Line at Chaka Bridge to Chaka Santal Primari School due to damage by construction of PMGSY Road & Panchayet Road of Chhatna block under Saltora -Chhatna W/S Scheme under BQA (HQ) of Bankura Division P.H.E. Dte. |  | Junior Engineer | ORD/000200/2022-2023 | 692/BSD | 11/06/2022 | 26/06/2022 | SIB SANKAR CHOWDHURY | 4.94 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Mahesana, Bhuinya Pasa, Budhanpur, Rahir, Chaka, Sanotalpara, A | SM/09502 | Retrofitting | Laying of HDPE pipe Line from Chaka ICDS Centre to Harimela due to damage by construction of PMGSY Road & Panchayet Road of Chhatna block under Saltora -Chhatna W/S Scheme under BQA (HQ) of Bankura Division P.H.E. Dte |  | Junior Engineer | ORD/000624/2021-2022 | 690/BSD | 11/06/2021 | 26/06/2021 | SIB SANKAR CHOWDHURY | 4.95 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Mahesana, Bhuinya Pasa, Budhanpur, Rahir, Chaka, Sanotalpara, A | SM/09502 | Retrofitting | Laying extra HDPE Pipe Line to Cover Mahesana, Bhuinyapara, mouza retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BAKSIBANDH (Zone - J) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000598/2021-2022 | 269/BSD | 17/03/2022 | 27/03/2022 | ASHIS KUMAR SAMANTA | 4.51 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Mahesana, Bhuinya Pasa, Budhanpur, Rahir, Chaka, Sanotalpara, A | SM/09502 | Retrofitting | Laying extra HDPE Pipe Line to Cover Khobradihi, Amlatora, Amakunda mouza retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BAKSIBANDH (Zone - J) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000595/2021-2022 | 271/BSD | 17/03/2022 | 27/03/2022 | ASHIS KUMAR SAMANTA | 4.91 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Mahesana, Bhuinya Pasa, Budhanpur, Rahir, Chaka, Sanotalpara, A | SM/09502 | Retrofitting | Laying extra HDPE Pipe Line to Cover Chaintore, Khayerboni mouza retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BAKSIBANDH (Zone - J) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000597/2021-2022 | 267/BSD | 17/03/2022 | 27/03/2022 | ASHIS KUMAR SAMANTA | 4.9 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Mahesana, Bhuinya Pasa, Budhanpur, Rahir, Chaka, Sanotalpara, A | SM/09502 | Retrofitting | Dismantling & reconstruction of concrete at chaka Adibasi para to Primary School for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Baksibandh (Zone - J) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000203/2022-2023 | 347/KSD | 16/08/2022 | 05/09/2022 | SIB SANKAR CHOWDHURY | 3.86 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Mahesana, Bhuinya Pasa, Budhanpur, Rahir, Chaka, Sanotalpara, A | SM/09502 | Retrofitting | laying extra HDPE Pipe Line to Cover Chinabari, mouza retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of BAKSIBANDH (Zone - J) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000600/2021-2022 | 265/BSD | 17/03/2022 | 27/03/2022 | ASHIS KUMAR SAMANTA | 4.91 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Mahesana, Bhuinya Pasa, Budhanpur, Rahir, Chaka, Sanotalpara, A | SM/09502 | Retrofitting | Construction of S.S.P including laying of P.V.C extension pipe Line at Tegori Hari Mandir to Namapara & Golgora Bouripara of Chhatna block under Saltora -Chhatna W/S Scheme under BQA (HQ) of Bankura Division P.H.E. Dte. |  | Junior Engineer | ORD/000625/2021-2022 | 691/BSD | 11/06/2021 | 26/06/2021 | SIB SANKAR CHOWDHURY | 4.91 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Mahesana, Bhuinya Pasa, Budhanpur, Rahir, Chaka, Sanotalpara, A | SM/09502 | Retrofitting | Interconnection with R/M including Laying of HDPE Pipe Line from Kamalpur-Harigram road to Rahir to increase water pressure at Rahir, chaka mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Boxibandh (Zone - J) of Chhatna Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000459/2022-2023 | 238/BQA | 08/02/2023 | 25/03/2023 | TARINI CHARAN UPADHYAY | 8.56 | 0 | 0 | 50
13 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Mahesana, Bhuinya Pasa, Budhanpur, Rahir, Chaka, Sanotalpara, A | SM/09502 | Retrofitting | Laying Extra HDPE Pipe Line to Cover Maheskhapri, Upardihi,Antkuria, Chinabari,Santalpara,Baxibandh mouza for retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of BAKSIBANDH (Zone - J) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000425/2022-2023 | 178/BQA | 30/01/2023 | 16/03/2023 | ASHIS KUMAR SAMANTA | 12.05 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Mahesana, Bhuinya Pasa, Budhanpur, Rahir, Chaka, Sanotalpara, A | SM/09502 | Retrofitting | Work Order for Construction of valve chamber at Chintore, Budhanpur, Mahesana, Chinabari mouza of Boxibandh (Zone- I) of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Boxibandh (Zone- I) W/S Scheme under Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/000159/2023-2024 | 104/KSD | 28/04/2023 | 13/05/2023 | ASHIS KUMAR SAMANTA | 0.98 | 0 | 0 | 80
15 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Mahesana, Bhuinya Pasa, Budhanpur, Rahir, Chaka, Sanotalpara, A | SM/09502 | Retrofitting | Work Order for Construction of valve Amakunda, Upardihi, Bhuinyapara mouza of Boxibandh (Zone- I) of retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Boxibandh (Zone- I) W/S Scheme under Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/000160/2023-2024 | 105/KSD | 28/04/2023 | 13/05/2023 | ASHIS KUMAR SAMANTA | 0.84 | 0 | 0 | 80
16 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Mahesana, Bhuinya Pasa, Budhanpur, Rahir, Chaka, Sanotalpara, A | SM/09502 | Retrofitting | Laying HDPE Pipe Line from Amlatora more to Khobradihi to increase water pressure at Khoradihi of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Boxibandh (Zone - J) of Chhatna Block under Saltora Chhatna W/S Scheme (BRGF ph-I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/001099/2022-2023 | 182/BQA | 30/01/2023 | 16/03/2023 | ASHIS KUMAR SAMANTA | 10.99 | 0 | 0 | 100
17 | BANKURA |  | Bankura Division | Construction and commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Mahesana, Bhuinya Pasa, Budhanpur, Rahir, Chaka, Sanotalpara, A | SM/09502 | Retrofitting | Interconnection with R/M including Laying of HDPE Pipe Line from Kamalpur-Harigram road to Rahir to increase water pressure at Rahir, chaka mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Boxibandh (Zone - J) of Chhatna Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. ( Part-A ) | Assistant Engineer | Junior Engineer | ORD/000449/2022-2023 | 237/BQA | 08/02/2023 | 01/04/2026 | ASHIS KUMAR SAMANTA | 8.56 | 0 | 0 | 0
Total | [13 empty] | 199.72 | 0 | 0