## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Beliara-65 & Dejhat-66) of PRAKASH (Zone | SM/09504 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Prakash Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte.DPR no - 15. Block - Bishnupur, Name of OHR - Gumut, No. of Mouza :- 2 nos. i.e. Beliara-65 & Dejhat-66, Total House Hold - 977 |  | Junior Engineer | ORD/000210/2021-2022 | 3046/BQA | 01/12/2021 | 31/12/2021 | PARAMESWAR CHOWDHURY | 72.35 | 10.6 | 14.65 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Beliara-65 & Dejhat-66) of PRAKASH (Zone | SM/09504 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kushmuri Zone-B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Gobindapur, No. of Mouza :- 10 nos. i.e. Jinkara-19, Srirampur-20, Pratapmath-21, Belbandbi-22, Kapshit-23, Paharpur-55, Fatepur-56, Baragobindapur-59, Thakurinipuskarini-60 & Karardanga-62, Total House Hold - 2610 |  |  | VCH/001546/2022-2023 | FHTC/06 | 06/01/2023 | 06/01/2023 | M/S TARUN KUMAR PATRA | 93.05 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Beliara-65 & Dejhat-66) of PRAKASH (Zone | SM/09504 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bamni (42) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/001547/2022-2023 | FHTC/06 | 06/01/2023 | 06/01/2023 | GANESH ROY | 6.02 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Beliara-65 & Dejhat-66) of PRAKASH (Zone | SM/09504 | Retrofitting | Parallel pipe laying of HDPE pipe from Pinguri Village Hunuman mondir to Khatal Bagan Village for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Maliara (Zone -A)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/001526/2022-2023 | FHTC/18 | 18/01/2023 | 18/01/2023 | SUBHADIP KOLEY | 4.93 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Beliara-65 & Dejhat-66) of PRAKASH (Zone | SM/09504 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of TELEBEDIA (Zone - M) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte Block - Bankura- II, Name of OHR - Tilabedia, No.of Mouza :- 02 nos, (Mouladanga & Mithila), Total House Hold - 519.. ( Sl .No.- 19) |  |  | VCH/001523/2022-2023 | FHTC/18 | 18/01/2023 | 18/01/2023 | PARAMESWAR CHOWDHURY | 2.78 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Beliara-65 & Dejhat-66) of PRAKASH (Zone | SM/09504 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 |  |  | VCH/001602/2022-2023 | FHTC/10 | 10/01/2023 | 10/01/2023 | M/S TARUN KUMAR PATRA | 34.61 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Beliara-65 & Dejhat-66) of PRAKASH (Zone | SM/09504 | Retrofitting | Parallel pipe laying of HDPE pipe from Pinguri village football ground to Pinguri Village Hunuman mondir for increase pressure of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Maliara (Zone -A)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/001524/2022-2023 | FHTC/18 | 18/01/2023 | 18/01/2023 | SUBHADIP KOLEY | 4.93 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Beliara-65 & Dejhat-66) of PRAKASH (Zone | SM/09504 | Retrofitting | Laying of HDPE pipe from Maliara OHR site to Pinguri village football ground for increase pressure of Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for Maliara(Zone -A)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/001525/2022-2023 | FHTC/18 | 18/01/2023 | 18/01/2023 | SUBHADIP KOLEY | 4.8 | 0 | 0 | 0
Total | [13 empty] | 223.47 | 10.6 | 4.74