## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Patadubi (54), Angadpur (85), Bhaluka (86), Karra (87), Hemchabad (88), Bikrampur (103), Indkata (104), Lohari Brindaban (123), Kochkhalui (124), Brindabanpur (125), Shushina | SM/09521 | Retrofitting | Household survey in Patadubi (54), Angadpur (85), Bhaluka (86), Karra (87), Hemchabad (88), Bikrampur (103), Indkata (104), Lohari Brindaban (123), Kochkhalui (124), Brindabanpur (125), Shushina Gobindarampur (126), Ramar Gram (127) & Hatiband (128) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Bikrampur and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000887/2021-2022 | 93/BSD | 28/01/2022 | 28/03/2022 | TAPAS DEY | 0.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Patadubi (54), Angadpur (85), Bhaluka (86), Karra (87), Hemchabad (88), Bikrampur (103), Indkata (104), Lohari Brindaban (123), Kochkhalui (124), Brindabanpur (125), Shushina | SM/09521 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000030/2021-2022 | 569/BQA | 17/03/2022 | 17/03/2022 | Resource Division | 9.3 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Patadubi (54), Angadpur (85), Bhaluka (86), Karra (87), Hemchabad (88), Bikrampur (103), Indkata (104), Lohari Brindaban (123), Kochkhalui (124), Brindabanpur (125), Shushina | SM/09521 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Patadubi (54) Angadpur (85) Bhaluka (86) Karra (87) Hemchabad (88) Bikrampur (103), Indkata (104), Lohari Brindaban (123), Kochkhalui (124), Brindabanpur (125), Shushina Gobindarampur (126), Ramar Gram (127) & Hatiband (128) mouzas by retrofitting Bikrampur and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total House Hold - 1510 nos. | Assistant Engineer | Junior Engineer | ORD/000319/2021-2022 | 3370/BQA | 31/12/2021 | 01/04/2026 | M/S TARUN KUMAR PATRA | 75.2 | 0 | 0 | 0
Total | [13 empty] | 85.01 | 0 | 0