## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bauri Danga (266), Chak Bagmari (267), Bagmari Maheshpur (268), Khar Bari Badni (269), Patangapur (284), Chanda Bila (285), Bhagaban Bati (286), Bakinala (287), Jama Dhara (2 | SM/09522 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bauri Danga (266) Chak Bagmari (267) Bagmari Maheshpur (268) Khar Bari Badni (269), Patangapur (284), Chanda Bila (285), Bhagaban Bati (286), Bakinala (287), Jama Dhara (288), Mahish Doba (289), Bena Bandi (290) & Bhedua (291) mouzas by retrofitting Jamadhara and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total House Hold - 1047 nos. | Assistant Engineer | Junior Engineer | ORD/000399/2021-2022 | 301/BQA | 18/02/2022 | 20/03/2022 | M/S BIPUL BANERJEE | 70.8 | 36.33 | 51.31 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bauri Danga (266), Chak Bagmari (267), Bagmari Maheshpur (268), Khar Bari Badni (269), Patangapur (284), Chanda Bila (285), Bhagaban Bati (286), Bakinala (287), Jama Dhara (2 | SM/09522 | Retrofitting | Household survey in Bauri Danga (266), Chak Bagmari (267), Bagmari Maheshpur (268), Khar Bari Badni (269), Patangapur (284), Chanda Bila (285), Bhagaban Bati (286), Bakinala (287), Jama Dhara (288), Mahish Doba (289), Bena Bandi (290) & Bhedua (291) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Jamadhara and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000883/2021-2022 | 96/BSD | 28/01/2022 | 30/01/2022 | TAPAS DEY | 0.35 | 0.19 | 55.68 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bauri Danga (266), Chak Bagmari (267), Bagmari Maheshpur (268), Khar Bari Badni (269), Patangapur (284), Chanda Bila (285), Bhagaban Bati (286), Bakinala (287), Jama Dhara (2 | SM/09522 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000031/2021-2022 | 570/BQA | 17/03/2022 | 17/03/2022 | Resource Division | 6.45 | 0 | 0 | 0
Total | [13 empty] | 77.6 | 36.52 | 47.07