## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dunda (1), Krishna Nagar (2), Radhamohanpur (8), Binodnagar (10), Kharigara (11), Kokilpur (12), Kalyani (13), Digshuli (14), Siarbada (22) & Beryak Hamar (23) mouzas by retr | SM/09523 | Retrofitting | Household survey in Dunda (1), Krishna Nagar (2), Radhamohanpur (8), Binodnagar (10), Kharigara (11), Kokilpur (12), Kalyani (13), Digshuli (14), Siarbada (22) & Beryak Hamar (23) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Kalyani and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000891/2021-2022 | 101/BSD | 28/01/2022 | 28/03/2022 | TAPAS DEY | 0.47 | 0.28 | 59.42 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dunda (1), Krishna Nagar (2), Radhamohanpur (8), Binodnagar (10), Kharigara (11), Kokilpur (12), Kalyani (13), Digshuli (14), Siarbada (22) & Beryak Hamar (23) mouzas by retr | SM/09523 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000032/2021-2022 | 572/BQA | 17/03/2022 | 17/03/2022 | Resource Division | 8.76 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Dunda (1), Krishna Nagar (2), Radhamohanpur (8), Binodnagar (10), Kharigara (11), Kokilpur (12), Kalyani (13), Digshuli (14), Siarbada (22) & Beryak Hamar (23) mouzas by retr | SM/09523 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Dunda (1), Krishna Nagar (2), Radhamohanpur (8), Binodnagar (10), Kharigara (11), Kokilpur (12), Kalyani (13), Digshuli (14), Siarbada (22) & Beryak Hamar (23) mouzas by retrofitting Kalyani and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 1422 nos. | Assistant Engineer | Junior Engineer | ORD/000415/2021-2022 | 436/BQA | 03/03/2022 | 01/10/2026 | GOUTAM BHOWMIK | 89.6 | 41.32 | 46.12 | 62
Total | [13 empty] | 98.84 | 41.6 | 42.09