## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Daldagi (15), Chakgopalpur (16), Lauda (17), Amlagura (18), Goaladangar (19), Patlabani (20) & Ramkrishnapur (21) mouzas by retrofitting Kalyani and adjoining Mouzas Water Su | SM/09524 | Retrofitting | Household survey in Daldagi (15), Chakgopalpur (16), Lauda (17), Amlagura (18), Goaladangar (19), Patlabani (20) & Ramkrishnapur (21) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Kalyani and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000886/2021-2022 | 102/BSD | 28/01/2022 | 30/01/2022 | TAPAS DEY | 0.59 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Daldagi (15), Chakgopalpur (16), Lauda (17), Amlagura (18), Goaladangar (19), Patlabani (20) & Ramkrishnapur (21) mouzas by retrofitting Kalyani and adjoining Mouzas Water Su | SM/09524 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000033/2021-2022 | 573/BQA | 17/03/2022 | 17/03/2022 | Resource Division | 10.84 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Daldagi (15), Chakgopalpur (16), Lauda (17), Amlagura (18), Goaladangar (19), Patlabani (20) & Ramkrishnapur (21) mouzas by retrofitting Kalyani and adjoining Mouzas Water Su | SM/09524 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Daldagi (15), Chakgopalpur (16), Lauda (17), Amlagura (18), Goaladangar (19), Patlabani (20) & Ramkrishnapur (21) mouzas by retrofitting Kalyani and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total House Hold - 1759 nos. | Assistant Engineer | Junior Engineer | ORD/000318/2021-2022 | 3369/BQA | 31/12/2021 | 31/03/2026 | M/S TARUN KUMAR PATRA | 75.43 | 0 | 0 | 0
Total | [13 empty] | 86.85 | 0 | 0