## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Haryaki (24), Balguma (25), Bahara Band (26), Rasiknagarpur (27), Kadagot (28), Layada Dumarya (29), Gholkunda (30), Madhabpur (31) & Chakuparsol (32) mouzas by retrofitting | SM/09531 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Haryaki (24), Balguma (25), Bahara Band (26), Rasiknagarpur (27), Kadagot (28), Layada Dumarya (29), Gholkunda (30), Madhabpur (31) & Chakuparsol (32) mouzas by retrofitting Ratanpur and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 2017 nos. |  | Junior Engineer | ORD/000404/2021-2022 | 321/BQA | 22/02/2022 | 23/04/2022 | GOUTAM BHATTACHRYYA | 107.67 | 97.86 | 90.89 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Haryaki (24), Balguma (25), Bahara Band (26), Rasiknagarpur (27), Kadagot (28), Layada Dumarya (29), Gholkunda (30), Madhabpur (31) & Chakuparsol (32) mouzas by retrofitting | SM/09531 | Retrofitting | Household survey in Haryaki (24), Balguma (25), Bahara Band (26), Rasiknagarpur (27), Kadagot (28), Layada Dumarya (29), Gholkunda (30), Madhabpur (31) & Chakuparsol (32) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Ratanpur and adjoining Mouzas Water Supply Scheme (Zone-A) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000884/2021-2022 | 105/BSD | 28/01/2022 | 28/03/2022 | TAPAS DEY | 0.67 | 0.58 | 86.37 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Haryaki (24), Balguma (25), Bahara Band (26), Rasiknagarpur (27), Kadagot (28), Layada Dumarya (29), Gholkunda (30), Madhabpur (31) & Chakuparsol (32) mouzas by retrofitting | SM/09531 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000036/2021-2022 | 576/BQA | 17/03/2022 | 17/03/2022 | Resource Division | 12.42 | 0 | 0 | 0
Total | [13 empty] | 120.77 | 98.44 | 81.51