## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kamar Kata (157), Rajduha (158), Krishna Singhpur (159), Jambedya (160), Chingani (161), Geredaha (162), Chak Krishnasinghpur (166), Kelyajuri (167), Dharsona (170), Niada (1 | SM/09533 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection)¿ in Kamar Kata (157), Rajduha (158), Krishna Singhpur (159), Jambedya (160), Chingani (161), Geredaha (162), Chak Krishnasinghpur (166), Kelyajuri (167), Dharsona (170), Niada (171), Dhengasol (173) & Arabani (174) mouzas by retrofitting Chingani and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 756 Nos. ( out of 2270 ) ( Part-C ) | Assistant Engineer | Junior Engineer | ORD/000017/2022-2023 | 925/BQA | 21/04/2022 | 01/04/2027 | PRINCE INDUTRIES (INDIA) | 35.9 | 18.26 | 50.86 | 72
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kamar Kata (157), Rajduha (158), Krishna Singhpur (159), Jambedya (160), Chingani (161), Geredaha (162), Chak Krishnasinghpur (166), Kelyajuri (167), Dharsona (170), Niada (1 | SM/09533 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kamar Kata (157), Rajduha (158), Krishna Singhpur (159), Jambedya (160), Chingani (161), Geredaha (162), Chak Krishnasinghpur (166), Kelyajuri (167), Dharsona (170), Niada (171), Dhengasol (173) & Arabani (174) mouzas by retrofitting Chingani and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 2270 nos. ( 757 out of 2270 )( PART- B ) | Assistant Engineer | Junior Engineer | ORD/000035/2022-2023 | 1213/BQA | 01/06/2022 | 01/10/2026 | APEX ENTERPRISE | 35.93 | 5.49 | 15.27 | 15
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kamar Kata (157), Rajduha (158), Krishna Singhpur (159), Jambedya (160), Chingani (161), Geredaha (162), Chak Krishnasinghpur (166), Kelyajuri (167), Dharsona (170), Niada (1 | SM/09533 | Retrofitting | Household survey in Kamar Kata (157), Rajduha (158), Krishna Singhpur (159), Jambedya (160), Chingani (161), Geredaha (162), Chak Krishnasinghpur (166), Kelyajuri (167), Dharsona (170), Niada (171), Dhengasol (173) & Arabani (174) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Chingani and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000888/2021-2022 | 95/BSD | 28/01/2022 | 28/03/2022 | TAPAS DEY | 0.76 | 0.19 | 25.24 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kamar Kata (157), Rajduha (158), Krishna Singhpur (159), Jambedya (160), Chingani (161), Geredaha (162), Chak Krishnasinghpur (166), Kelyajuri (167), Dharsona (170), Niada (1 | SM/09533 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000038/2021-2022 | 578/BQA | 17/03/2022 | 17/03/2022 | Resource Division | 13.98 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kamar Kata (157), Rajduha (158), Krishna Singhpur (159), Jambedya (160), Chingani (161), Geredaha (162), Chak Krishnasinghpur (166), Kelyajuri (167), Dharsona (170), Niada (1 | SM/09533 | Retrofitting | Supply Laying of HDPE pipe line for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection) in connection with retrofitting and different dia. CIDF Sluice Valve & fittings & Construction of valve chamber at Chingani and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. [First Part] | Assistant Engineer | Junior Engineer | ORD/000537/2025-2026 | 2152/BQA | 30/10/2025 | 01/01/2027 | GOUTAM BHATTACHARYYA | 52.5 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Kamar Kata (157), Rajduha (158), Krishna Singhpur (159), Jambedya (160), Chingani (161), Geredaha (162), Chak Krishnasinghpur (166), Kelyajuri (167), Dharsona (170), Niada (1 | SM/09533 | Retrofitting | Schedule for supply Laying of HDPE pipe line for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection) in connection with retrofitting and different dia. CIDF Sluice Valve & fittings & Construction of valve chamber at Chingani and adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. [Second Part] | Assistant Engineer |  | ORD/000538/2025-2026 | 2153/BQA | 30/10/2025 | 28/01/2026 | SABIR ALI KHAN | 52.5 | 0 | 0 | 0
Total | [13 empty] | 191.57 | 23.93 | 12.49