## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bathan Tara (113), Elyati (114), Nikunjapur (115), Pingrui (116), Balatukri (117), Hira Dangar (137), Tentul Muri (138), Maitha (139), Jambani (140), Nayananandapur (193), Ma | SM/09534 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bathan Tara (113), Elyati (114), Nikunjapur (115), Pingrui (116), Balatukri (117), Hira Dangar (137), Tentul Muri (138), Maitha (139), Jambani (140), Nayananandapur (193), Majdiha (194) & Balarampur (195) mouzas by retrofitting Nikunjapur and adjoining Mouzas Water Supply Scheme (Zone-B) under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 2339 nos. | Assistant Engineer | Junior Engineer | ORD/000020/2022-2023 | 1062/BQA | 10/05/2022 | 29/04/2024 | M/S CARE | 122.18 | 114.94 | 94.08 | 97
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bathan Tara (113), Elyati (114), Nikunjapur (115), Pingrui (116), Balatukri (117), Hira Dangar (137), Tentul Muri (138), Maitha (139), Jambani (140), Nayananandapur (193), Ma | SM/09534 | Retrofitting | Household survey in Bathan Tara (113), Elyati (114), Nikunjapur (115), Pingrui (116), Balatukri (117), Hira Dangar (137), Tentul Muri (138), Maitha (139), Jambani (140), Nayananandapur (193), Majdiha (194) & Balarampur (195) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Nikunjapur (Zone-B) Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000895/2021-2022 | 100/BSD | 28/01/2022 | 28/03/2022 | TAPAS DEY | 0.78 | 0.78 | 100 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bathan Tara (113), Elyati (114), Nikunjapur (115), Pingrui (116), Balatukri (117), Hira Dangar (137), Tentul Muri (138), Maitha (139), Jambani (140), Nayananandapur (193), Ma | SM/09534 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000039/2021-2022 | 579/BQA | 17/03/2022 | 17/03/2022 | Resource Division | 14.41 | 0 | 0 | 0
Total | [13 empty] | 137.37 | 115.73 | 84.25