## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ola (109) & Suklai (191) mouzas by retrofitting Ola & adjoining Mouzas Water Supply Scheme and Suklai & adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (B | SM/09536 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ola (109) and Suklai (191) mouzas by retrofitting Ola and adjoining Mouzas Water Supply Scheme and Suklai & adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total House Hold - 434 nos. |  | Junior Engineer | ORD/000320/2021-2022 | 3371/BQA | 31/12/2021 | 30/01/2022 | PRADIP CHAKRABORTY | 20.33 | 6.5 | 31.96 | 100
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ola (109) & Suklai (191) mouzas by retrofitting Ola & adjoining Mouzas Water Supply Scheme and Suklai & adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (B | SM/09536 | Retrofitting | Household survey in Ola (109) & Suklai (191) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Ola & adjoining Mouzas Water Supply Scheme and Suklai & adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000885/2021-2022 | 98/BSD | 28/01/2022 | 28/03/2022 | TAPAS DEY | 0.14 | 0.06 | 41.7 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ola (109) & Suklai (191) mouzas by retrofitting Ola & adjoining Mouzas Water Supply Scheme and Suklai & adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (B | SM/09536 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000041/2021-2022 | 580/BQA | 17/03/2022 | 17/03/2022 | Resource Division | 2.67 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ola (109) & Suklai (191) mouzas by retrofitting Ola & adjoining Mouzas Water Supply Scheme and Suklai & adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (B | SM/09536 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ola (109) and Suklai (191) mouzas by retrofitting Ola and adjoining Mouzas Water Supply Scheme and Suklai & adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total House Hold - 434 nos. |  |  | VCH/000234/2022-2023 | FHTC/11 | 11/04/2022 | 11/04/2022 | PRADIP CHAKRABORTY | 6.56 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ola (109) & Suklai (191) mouzas by retrofitting Ola & adjoining Mouzas Water Supply Scheme and Suklai & adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (B | SM/09536 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Ola (109) and Suklai (191) mouzas by retrofitting Ola and adjoining Mouzas Water Supply Scheme and Suklai & adjoining Mouzas Water Supply Scheme under Onda Water Supply Scheme (BRGF Ph-I) at Block- Onda, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. Total House Hold - 434 nos. |  |  | VCH/002886/2021-2022 |  | 16/03/2022 | 16/03/2022 | PRADIP CHAKRABORTY | 6.56 | 0 | 0 | 0
Total | [13 empty] | 36.27 | 6.56 | 18.08