## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chatiasol (120), Barajamabedya (127), Goalbari (128), Sukhadali (129), Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175), Sindurpur (176), Chhotajamabedya (177) | SM/09549 | Retrofitting | Work Order for Household survey in Chatiasol (120), Barajamabedya (127), Goalbari (128), Sukhadali (129), Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175), Sindurpur (176), Chhotajamabedya (177), Kusumtikri (178), Betjhor (179), Botha (180), Bhangadali (181), Ghungia (182), Benasuli (183) & Baraamjhor (184) mouzas to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 25) |  | Junior Engineer | ORD/000688/2021-2022 | 864/KSD | 31/12/2021 | 31/03/2022 | TAPAS DEY | 0.83 | 0.43 | 52.54 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chatiasol (120), Barajamabedya (127), Goalbari (128), Sukhadali (129), Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175), Sindurpur (176), Chhotajamabedya (177) | SM/09549 | Retrofitting | Supplying, laying, fiting, fixing and jointing by HDPE pipe for Distribution Main along with ancillary works from Kuldiha Over Head Reservoir site to Amjhor village due to Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. under Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000272/2021-2022 | 3181/BQA | 21/12/2021 | 20/01/2022 | SANJOY PATRA | 87.36 | 16.94 | 19.39 | 100
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chatiasol (120), Barajamabedya (127), Goalbari (128), Sukhadali (129), Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175), Sindurpur (176), Chhotajamabedya (177) | SM/09549 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chatiasol (120) & Barajamabedya (127) mouzas by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 2 Nos. Total Household:- 362 Nos. |  | Junior Engineer | ORD/000457/2021-2022 | 671/BQA | 25/03/2022 | 24/04/2022 | JAGADISH BANERJEE | 22.73 | 21.73 | 95.58 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chatiasol (120), Barajamabedya (127), Goalbari (128), Sukhadali (129), Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175), Sindurpur (176), Chhotajamabedya (177) | SM/09549 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Betjhor (179), Botha (180), Bhangadali (181), Ghungia (182) & Benasuli (183) mouzas by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 5 Nos. Total Household:- 377 Nos. | Assistant Engineer | Junior Engineer | ORD/000459/2021-2022 | 673/BQA | 25/03/2022 | 24/04/2022 | SAKTIPADA MANDAL | 23.32 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chatiasol (120), Barajamabedya (127), Goalbari (128), Sukhadali (129), Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175), Sindurpur (176), Chhotajamabedya (177) | SM/09549 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175) & Sindurpur (176) mouzas by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 5 Nos. Total Household:- 706 Nos. ( Part -A) | Assistant Engineer | Junior Engineer | ORD/000469/2021-2022 | 778/BQA | 31/03/2022 | 30/04/2022 | GANESH ROY | 25.3 | 0 | 0 | 30
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chatiasol (120), Barajamabedya (127), Goalbari (128), Sukhadali (129), Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175), Sindurpur (176), Chhotajamabedya (177) | SM/09549 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Goalbari (128) mouza by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 1 No. Total Household:- 420 Nos. |  | Junior Engineer | ORD/000456/2021-2022 | 670/BQA | 25/03/2022 | 24/04/2022 | SAIKAT CHOWDHURY | 26.23 | 25.51 | 97.26 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chatiasol (120), Barajamabedya (127), Goalbari (128), Sukhadali (129), Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175), Sindurpur (176), Chhotajamabedya (177) | SM/09549 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175) & Sindurpur (176) mouzas by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 5 Nos. Total Household:- 706 Nos. ( Part-B ) | Assistant Engineer | Junior Engineer | ORD/000477/2021-2022 | 779/BQA | 31/03/2022 | 01/01/2026 | SUBHADIP KOLEY | 25.3 | 4.65 | 18.37 | 30
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chatiasol (120), Barajamabedya (127), Goalbari (128), Sukhadali (129), Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175), Sindurpur (176), Chhotajamabedya (177) | SM/09549 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Baraamjhor (184) mouza by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 1 No. Total Household:- 365 Nos. |  | Junior Engineer | ORD/000458/2021-2022 | 672/BQA | 25/03/2022 | 24/04/2022 | BEAUTY CHATTERJEE | 23.03 | 21.58 | 93.7 | 0
9 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chatiasol (120), Barajamabedya (127), Goalbari (128), Sukhadali (129), Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175), Sindurpur (176), Chhotajamabedya (177) | SM/09549 | Retrofitting | Work Order for Balance work of supplying, laying, fiting, fixing and jointing by HDPE pipe for Distribution Main along with ancillary works from Kuldiha Over Head Reservoir site to Amjhor village due to Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. under Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) | Assistant Engineer |  | ORD/001076/2021-2022 | 737/BQA | 28/03/2022 | 07/04/2022 | SANJOY PATRA | 4.98 | 4.91 | 98.56 | 20
10 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chatiasol (120), Barajamabedya (127), Goalbari (128), Sukhadali (129), Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175), Sindurpur (176), Chhotajamabedya (177) | SM/09549 | Retrofitting | Work Order for Balance work of supplying, laying, fiting, fixing and jointing by HDPE pipe for Distribution Main along with ancillary works from Kuldiha Over Head Reservoir site to Amjhor village due to Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. under Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-C) | Assistant Engineer |  | ORD/001077/2021-2022 | 740/BQA | 28/03/2022 | 07/04/2022 | SANJOY PATRA | 4.99 | 4.92 | 98.68 | 20
11 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chatiasol (120), Barajamabedya (127), Goalbari (128), Sukhadali (129), Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175), Sindurpur (176), Chhotajamabedya (177) | SM/09549 | Retrofitting | Work Order for Balance work of supplying, laying, fiting, fixing and jointing by HDPE pipe for Distribution Main along with ancillary works from Kuldiha Over Head Reservoir site to Amjhor village due to Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. under Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer |  | ORD/001075/2021-2022 | 734/BQA | 28/03/2022 | 07/04/2022 | SANJOY PATRA | 4.99 | 4.97 | 99.63 | 25
12 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chatiasol (120), Barajamabedya (127), Goalbari (128), Sukhadali (129), Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175), Sindurpur (176), Chhotajamabedya (177) | SM/09549 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Sukhadali (129), Chhotajamabedya (177) & Kusumtikri (178) mouzas by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 3 Nos. Total Household:- 250 Nos. | Assistant Engineer | Junior Engineer | ORD/000003/2022-2023 | 886/BQA | 13/04/2022 | 13/05/2022 | UTTAM KUMAR SINHAMAHAPATRA | 16.38 | 14.58 | 88.97 | 80
13 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chatiasol (120), Barajamabedya (127), Goalbari (128), Sukhadali (129), Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175), Sindurpur (176), Chhotajamabedya (177) | SM/09549 | Retrofitting | Work Order for Water supply arrangement at different Anganwadi Centre by laying pipeline and installation of stand post for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Under Jal Swapna & Jal Jeevan Mission Programme) (Sl. No. 16) |  | Junior Engineer | ORD/000475/2021-2022 | 108/KSD | 10/03/2022 | 25/03/2022 | UTTAM KUMAR SINHAMAHAPATRA | 4.6 | 3.11 | 67.56 | 20
14 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chatiasol (120), Barajamabedya (127), Goalbari (128), Sukhadali (129), Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175), Sindurpur (176), Chhotajamabedya (177) | SM/09549 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000005/2022-2023 | 1839/BQA | 29/08/2022 | 29/08/2022 | Resource Division | 8.91 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chatiasol (120), Barajamabedya (127), Goalbari (128), Sukhadali (129), Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175), Sindurpur (176), Chhotajamabedya (177) | SM/09549 | Retrofitting | Laying of distribution pipeline including different Dia. DI (K7) & UPVC pipe & Construction of RCC over head reservoir of 450 m3 capacities whose staging height is 20.00m for Rejuvenation of ONDA Pipe Water Supply Scheme, Vide No. PC-I/O.H.R./4/2012 Sheet 1 & 2) & Block- Onda under Bankura Sadar Sub- Division of Bankura Division, P.H.E. Dte (Zone-I) ( PART A & B) |  |  | VCH/001500/2022-2023 | FHTC/27 | 27/12/2022 | 27/12/2022 | GOPAL CHANDRA CHOWDHURY | 197.05 | 0 | 0 | 0
16 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chatiasol (120), Barajamabedya (127), Goalbari (128), Sukhadali (129), Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175), Sindurpur (176), Chhotajamabedya (177) | SM/09549 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) with laying of UPVC pipeline in Goalbari (128) mouza by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000483/2022-2023 | 333/BQA | 20/02/2023 | 06/04/2023 | SAIKAT CHOWDHURY | 11.97 | 11.92 | 99.53 | 0
17 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Chatiasol (120), Barajamabedya (127), Goalbari (128), Sukhadali (129), Gopalpur (138), Panchberia (173), Banpur (174), Tapaberia (175), Sindurpur (176), Chhotajamabedya (177) | SM/09549 | Retrofitting | Laying extra UPVC pipeline in Sukhadali (129) & Kusumtikri (178) mouzas for retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000639/2023-2024 | 2581/BQA | 15/09/2023 | 15/10/2023 | UTTAM KUMAR SINHAMAHAPATRA | 3.46 | 0 | 0 | 0
Total | [13 empty] | 491.41 | 135.23 | 27.52