## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Khamani (121), Tantibaria (122), Andharia (123), Habra (124), Saldahara (125), Jangalkhas (126), Chhotaamlatara (185), Baraamlatara (186), Kenduadangri (187), Telijant (188), | SM/09550 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Tantibaria (122), Andharia (123), Habra (124), Saldahara (125), Telijant (188) & Bhalukchira (189) mouzas by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 6 Nos. Total Household:- 729 Nos. ( PART B ) |  | Junior Engineer | ORD/000485/2021-2022 | 783/BQA | 31/03/2022 | 30/04/2022 | MRITYUNJOY HAZRA | 22.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Khamani (121), Tantibaria (122), Andharia (123), Habra (124), Saldahara (125), Jangalkhas (126), Chhotaamlatara (185), Baraamlatara (186), Kenduadangri (187), Telijant (188), | SM/09550 | Retrofitting | Supplying, laying, fiting, fixing and jointing by HDPE pipe for Distribution Main along with ancillary works from Kuldiha Over Head Reservoir site to Amjhor village due to Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. under Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte |  |  | VCH/002961/2021-2022 | FHTC/26 | 25/03/2022 | 25/03/2022 | SANJOY PATRA | 69.45 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Khamani (121), Tantibaria (122), Andharia (123), Habra (124), Saldahara (125), Jangalkhas (126), Chhotaamlatara (185), Baraamlatara (186), Kenduadangri (187), Telijant (188), | SM/09550 | Retrofitting | Supplying, laying, fiting, fixing and jointing by HDPE pipe for Distribution Main along with ancillary works from Amjhor village to Sarenga Netaji More due to Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. under Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte |  |  | VCH/002954/2021-2022 | FHTC/23 | 23/03/2022 | 23/03/2022 | EARTH MOVING (INDIA) | 24.89 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Khamani (121), Tantibaria (122), Andharia (123), Habra (124), Saldahara (125), Jangalkhas (126), Chhotaamlatara (185), Baraamlatara (186), Kenduadangri (187), Telijant (188), | SM/09550 | Retrofitting | Work Order for Household survey in Khamani (121), Tantibaria (122), Andharia (123), Habra (124), Saldahara (125), Jangalkhas (126), Chhotaamlatara (185), Baraamlatara (186), Kenduadangri (187), Telijant (188), Bhalukchira (189), Nekrapahari (192), Amdiha (193), Beruabaid (194) & Kuldiha (211) mouzas to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 26) |  | Junior Engineer | ORD/000689/2021-2022 | 865/KSD | 31/12/2021 | 31/03/2022 | TAPAS DEY | 0.76 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Khamani (121), Tantibaria (122), Andharia (123), Habra (124), Saldahara (125), Jangalkhas (126), Chhotaamlatara (185), Baraamlatara (186), Kenduadangri (187), Telijant (188), | SM/09550 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Jangalkhas (126), Chhotaamlatara (185), Baraamlatara (186) & Kenduadangri (187) mouzas by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte.Total Mouza:- 4 Nos. Total Household:- 295 Nos. |  | Junior Engineer | ORD/000004/2022-2023 | 887/BQA | 13/04/2022 | 13/05/2022 | TAPAN KUMAR UPADHYAY | 16.71 | 0 | 0 | 100
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Khamani (121), Tantibaria (122), Andharia (123), Habra (124), Saldahara (125), Jangalkhas (126), Chhotaamlatara (185), Baraamlatara (186), Kenduadangri (187), Telijant (188), | SM/09550 | Retrofitting | Work Order for Water supply arrangement at different School by laying pipeline and installation of stand post for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Under Jal Swapna & Jal Jeevan Mission Programme) (Sl. No. 18) |  | Junior Engineer | ORD/000476/2021-2022 | 110/KSD | 10/03/2022 | 25/03/2022 | UTTAM KUMAR SINHAMAHAPATRA | 4.66 | 0 | 0 | 20
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Khamani (121), Tantibaria (122), Andharia (123), Habra (124), Saldahara (125), Jangalkhas (126), Chhotaamlatara (185), Baraamlatara (186), Kenduadangri (187), Telijant (188), | SM/09550 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ with laying of UPVC pipeline in Jangalkhas (126), Chottaamlatara(185), Baraamlatara(186), & Kenduadangri (187) mouzas by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000660/2022-2023 | 505/BQA | 13/03/2023 | 27/04/2023 | TAPAN KUMAR UPADHYAY | 5.13 | 0 | 0 | 100
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Khamani (121), Tantibaria (122), Andharia (123), Habra (124), Saldahara (125), Jangalkhas (126), Chhotaamlatara (185), Baraamlatara (186), Kenduadangri (187), Telijant (188), | SM/09550 | Retrofitting | Supplying, laying, fiting, fixing and jointing by HDPE pipe for Distribution Main along with ancillary works from Kuldiha Over Head Reservoir site to Amjhor village due to Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. under Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000272/2021-2022 | 3181/BQA | 21/12/2021 | 20/01/2022 | SANJOY PATRA | 87.36 | 0 | 0 | 100
9 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Khamani (121), Tantibaria (122), Andharia (123), Habra (124), Saldahara (125), Jangalkhas (126), Chhotaamlatara (185), Baraamlatara (186), Kenduadangri (187), Telijant (188), | SM/09550 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Tantibaria (122), Andharia (123), Habra (124), Saldahara (125), Telijant (188) & Bhalukchira (189) mouzas by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 6 Nos. Total Household:- 729 Nos. ( PART - A ) |  | Junior Engineer | ORD/000484/2021-2022 | 782/BQA | 31/03/2022 | 30/04/2022 | DAUD ALI KHAN | 22.5 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Khamani (121), Tantibaria (122), Andharia (123), Habra (124), Saldahara (125), Jangalkhas (126), Chhotaamlatara (185), Baraamlatara (186), Kenduadangri (187), Telijant (188), | SM/09550 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000004/2022-2023 | 1840/BQA | 29/08/2022 | 29/08/2022 | Resource Division | 7.74 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Khamani (121), Tantibaria (122), Andharia (123), Habra (124), Saldahara (125), Jangalkhas (126), Chhotaamlatara (185), Baraamlatara (186), Kenduadangri (187), Telijant (188), | SM/09550 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Khamani (121) mouza by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 1 No. Total Household:- 381 Nos. | Assistant Engineer | Junior Engineer | ORD/000460/2021-2022 | 674/BQA | 25/03/2022 | 24/04/2022 | MAHARAJA CONSTRUCTION CO. | 23.78 | 0 | 0 | 95
12 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Khamani (121), Tantibaria (122), Andharia (123), Habra (124), Saldahara (125), Jangalkhas (126), Chhotaamlatara (185), Baraamlatara (186), Kenduadangri (187), Telijant (188), | SM/09550 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Nekrapahari (192), Amdiha (193) & Beruabaid (194) mouzas by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 3 Nos. Total Household:- 158 Nos. | Assistant Engineer | Junior Engineer | ORD/000461/2021-2022 | 675/BQA | 25/03/2022 | 01/04/2025 | SHYAMAPADA DEY | 10.13 | 0 | 0 | 20
13 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Khamani (121), Tantibaria (122), Andharia (123), Habra (124), Saldahara (125), Jangalkhas (126), Chhotaamlatara (185), Baraamlatara (186), Kenduadangri (187), Telijant (188), | SM/09550 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kuldiha (211) mouza by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 1 No. Total Household:- 717 Nos. ( PART - B) | Assistant Engineer | Junior Engineer | ORD/000483/2021-2022 | 781/BQA | 31/03/2022 | 02/04/2026 | SHYAMAL KUMAR DAS | 22.12 | 0 | 0 | 40
14 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Khamani (121), Tantibaria (122), Andharia (123), Habra (124), Saldahara (125), Jangalkhas (126), Chhotaamlatara (185), Baraamlatara (186), Kenduadangri (187), Telijant (188), | SM/09550 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Kuldiha (211) mouza by retrofitting of Water Supply Scheme for Kuldiha and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 1 No. Total Household:- 717 Nos. ( PART-A) | Assistant Engineer | Junior Engineer | ORD/000482/2021-2022 | 780/BQA | 31/03/2022 | 02/04/2026 | BISWARUP BOSE | 22.12 | 0 | 0 | 40
Total | [13 empty] | 339.85 | 0 | 0