## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhudrubad (69), Baramakarkol (70), Chhota Makarkol (71), Asna (72), Kaliam (73), Dhanisukni (74), Ambakra (75), Kadambandh (76), Kantasola (77), Bhangabandh (78), Kalabati (7 | SM/09552 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhudrubad (69), Baramakarkol (70), Chhota Makarkol (71), Asna (72), Kaliam (73), Dhanisukni (74), Ambakra (75), Kadambandh (76), Kantasola (77), Bhangabandh (78), Kalabati (79), Nimaipur (80), Sirsha (81), Kumardoba (82), Dhabani (83), Kallaicha (84) & Manipur (85) mouzas by retrofitting of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 1926 nos. |  | Junior Engineer | ORD/000417/2021-2022 | 437/BQA | 03/03/2022 | 17/04/2022 | PRINCE INDUTRIES (INDIA) | 97.43 | 96.57 | 99.12 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhudrubad (69), Baramakarkol (70), Chhota Makarkol (71), Asna (72), Kaliam (73), Dhanisukni (74), Ambakra (75), Kadambandh (76), Kantasola (77), Bhangabandh (78), Kalabati (7 | SM/09552 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Asna (72), Dhanisukni (74) & Nimaipur (80) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 13) |  | Junior Engineer | ORD/000282/2022-2023 | 1292/BQA | 15/06/2022 | 25/06/2022 | PRINCE INDUTRIES (INDIA) | 4.86 | 4.79 | 98.57 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhudrubad (69), Baramakarkol (70), Chhota Makarkol (71), Asna (72), Kaliam (73), Dhanisukni (74), Ambakra (75), Kadambandh (76), Kantasola (77), Bhangabandh (78), Kalabati (7 | SM/09552 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Baramakarkol (70), Kalabati (79), Sirsha (81) & Kallaicha (84) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 18) |  | Junior Engineer | ORD/000283/2022-2023 | 1297/BQA | 15/06/2022 | 25/06/2022 | PRINCE INDUTRIES (INDIA) | 4.8 | 4.72 | 98.31 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhudrubad (69), Baramakarkol (70), Chhota Makarkol (71), Asna (72), Kaliam (73), Dhanisukni (74), Ambakra (75), Kadambandh (76), Kantasola (77), Bhangabandh (78), Kalabati (7 | SM/09552 | Retrofitting | Work Order for Construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? in Baramakarkol (70) mouzas by retrofitting of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 02) |  | Junior Engineer | ORD/000281/2022-2023 | 1281/BQA | 15/06/2022 | 25/06/2022 | PRINCE INDUTRIES (INDIA) | 1.58 | 1.54 | 97.6 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Bhudrubad (69), Baramakarkol (70), Chhota Makarkol (71), Asna (72), Kaliam (73), Dhanisukni (74), Ambakra (75), Kadambandh (76), Kantasola (77), Bhangabandh (78), Kalabati (7 | SM/09552 | Retrofitting | Work Order for Household survey in Bhudrubad (69), Baramakarkol (70), Chhota Makarkol (71), Asna (72), Kaliam (73), Dhanisukni (74), Ambakra (75), Kadambandh (76), Kantasola (77), Bhangabandh (78), Kalabati (79), Nimaipur (80), Sirsha (81), Kumardoba (82), Dhabani (83), Kallaicha (84) & Manipur (85) mouzas to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 22) |  | Junior Engineer | ORD/000623/2021-2022 | 861/KSD | 31/12/2021 | 31/03/2022 | TAPAS DEY | 0.64 | 0.64 | 100 | 0
Total | [13 empty] | 109.31 | 108.26 | 99.04