## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmipal (158), Dhanghari (159), Puipal (160), Khamardanga (161), Kustara (162), Khaergaria (163), Suknokhali (164), Sushinia (165), Hatibari (166), Raybandh (167) & Dubraj | SM/09553 | Retrofitting | Work Order for Water supply arrangement at different Anganwadi Centre by laying pipeline and installation of stand post under Dubrajpur Zone-A & B of Simlapal Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Under Jal Swapna & Jal Jeevan Mission Programme) [Part-B] (Sl. No. 12) |  | Junior Engineer | ORD/000336/2021-2022 | 820/KSD | 15/12/2021 | 30/12/2021 | SOURAV SINHA MAHAPATRA | 3.59 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmipal (158), Dhanghari (159), Puipal (160), Khamardanga (161), Kustara (162), Khaergaria (163), Suknokhali (164), Sushinia (165), Hatibari (166), Raybandh (167) & Dubraj | SM/09553 | Retrofitting | Work Order for Household survey in Lakshmipal (158), Dhanghari (159), Puipal (160), Khamardanga (161), Kustara (162), Khaergaria (163), Suknokhali (164), Sushinia (165), Hatibari (166), Raybandh (167) & Dubrajpur (168) mouzas to provide ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 23) |  | Junior Engineer | ORD/000686/2021-2022 | 862/KSD | 31/12/2021 | 31/03/2022 | TAPAS DEY | 1.12 | 0.88 | 78.79 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmipal (158), Dhanghari (159), Puipal (160), Khamardanga (161), Kustara (162), Khaergaria (163), Suknokhali (164), Sushinia (165), Hatibari (166), Raybandh (167) & Dubraj | SM/09553 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000007/2022-2023 | 1838/BQA | 29/08/2022 | 29/08/2022 | Resource Division | 9.23 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmipal (158), Dhanghari (159), Puipal (160), Khamardanga (161), Kustara (162), Khaergaria (163), Suknokhali (164), Sushinia (165), Hatibari (166), Raybandh (167) & Dubraj | SM/09553 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000017/2022-2023 | 2036/BQA | 29/09/2022 | 29/09/2022 | Resource Division | 11.44 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Lakshmipal (158), Dhanghari (159), Puipal (160), Khamardanga (161), Kustara (162), Khaergaria (163), Suknokhali (164), Sushinia (165), Hatibari (166), Raybandh (167) & Dubraj | SM/09553 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Lakshmipal (158), Dhanghari (159), Puipal (160), Khamardanga (161), Kustara (162), Khaergaria (163), Suknokhali (164), Sushinia (165), Hatibari (166), Raybandh (167) & Dubrajpur (168) mouzas by retrofitting of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Household :- 3357 nos. |  | Junior Engineer | ORD/000045/2022-2023 | 1648/BQA | 25/07/2022 | 07/11/2022 | M/S TARUN KUMAR PATRA | 144.56 | 123.04 | 85.12 | 95
Total | [13 empty] | 169.92 | 123.92 | 72.93