## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chakuparsole Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Chotobankadaha-148 & Bandrya-150) of | SM/09619 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuporsol Zone- A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Majuria, No. of Mouza :- 02 nos. i.e. Chotobankadaha-148 and Bandrya- 150, Total House Hold - 534 ( Out of 703) |  | Junior Engineer | ORD/000194/2021-2022 | 3028/BQA | 29/11/2021 | 29/12/2021 | SUBHENDU SEKHAR GORAI | 49.14 | 12.46 | 25.35 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chakuparsole Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Chotobankadaha-148 & Bandrya-150) of | SM/09619 | Retrofitting | Laying HDPE pipeline to increase pressure in Surulia (87) & Jalneja (88) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-O (Madandihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/001432/2022-2023 | FHTC/15 | 15/12/2022 | 15/12/2022 | SOURAV SINHA MAHAPATRA | 5.66 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chakuparsole Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Chotobankadaha-148 & Bandrya-150) of | SM/09619 | Retrofitting | Supplying, laying, fiting , fixing and jointing of UPVC pipes in connection with Jal Jeevan Mission Programme JJM AND Jal swapna of Andharthol zone V water supply scheme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. block - bankura - I Name of OHR - Andharthol name of village - Andharthol (school more) |  |  | VCH/001430/2022-2023 | FHTC/15 | 15/12/2022 | 15/12/2022 | TARINI CHARAN UPADHYAY | 4.21 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chakuparsole Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Chotobankadaha-148 & Bandrya-150) of | SM/09619 | Retrofitting | 'Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 02 nos (Chapatara & Sendra) Total House Hold - 604' |  |  | VCH/001171/2022-2023 | FHTC/14 | 14/09/2022 | 14/09/2022 | GOPAL CHANDRA CHOWDHURY | 44.27 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chakuparsole Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Chotobankadaha-148 & Bandrya-150) of | SM/09619 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KHYERKANALI (Zone - J) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph. - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Kherkanali No.of Mouza :- 01 nos. ( Kaljuri)Total House Hold -120 nos. |  |  | VCH/001433/2022-2023 | FHTC/15 | 15/12/2022 | 15/12/2022 | MOHAN KUMAR ROY | 14.32 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chakuparsole Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Chotobankadaha-148 & Bandrya-150) of | SM/09619 | Retrofitting | Supplying, laying, fiting , fixing and jointing of UPVC pipes in connection with Jal Jeevan Mission Programme JJM AND Jal swapna of Andharthol zone V water supply scheme under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. block - bankura - I Name of OHR - Andharthol name of village - Andharthol (school more) |  |  | VCH/001431/2022-2023 | FHTC/15 | 15/12/2022 | 15/12/2022 | TARINI CHARAN UPADHYAY | 4.6 | 0 | 0 | 0
Total | [13 empty] | 122.2 | 12.46 | 10.19