## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Maulakanda (129), Rambandh (130), Ghagra (131), Runiara (132), Rangamatia (133), Madhupur (134) & Bhedua (181) mouzas by retrofitting of Water Supply Scheme for Baricha, Zone | SM/09620 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Maulakanda (129), Rambandh (130), Ghagra (131), Runiara (132), Rangamatia (133), Madhupur (134) & Bhedua (181) mouzas under Baricha, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 7 Nos. Total Household:- 882 Nos. |  | Junior Engineer | ORD/000196/2021-2022 | 3030/BQA | 29/11/2021 | 29/12/2021 | EARTH MOVING (INDIA) | 51.76 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Maulakanda (129), Rambandh (130), Ghagra (131), Runiara (132), Rangamatia (133), Madhupur (134) & Bhedua (181) mouzas by retrofitting of Water Supply Scheme for Baricha, Zone | SM/09620 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Jamsol (285), Baligura (286), Asna (287), Chhotagarra (288), Dakharang (290), Kadma (291) & Chingra (292) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-B and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/002542/2021-2022 | FHTC/23 | 23/02/2022 | 23/02/2022 | SUBHADIP KOLEY | 42.16 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Maulakanda (129), Rambandh (130), Ghagra (131), Runiara (132), Rangamatia (133), Madhupur (134) & Bhedua (181) mouzas by retrofitting of Water Supply Scheme for Baricha, Zone | SM/09620 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Cherabasta. No.of Mouza :- 04 ( Vidyadharpur, Cherabasta, Aina gobindapur & Mukundapur.) Total House Hold - 604 |  |  | VCH/002750/2021-2022 | FHTC/3 | 03/03/2022 | 03/03/2022 | GOPAL CHANDRA CHOWDHURY | 2.07 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Maulakanda (129), Rambandh (130), Ghagra (131), Runiara (132), Rangamatia (133), Madhupur (134) & Bhedua (181) mouzas by retrofitting of Water Supply Scheme for Baricha, Zone | SM/09620 | Retrofitting | Work Order for Household survey in Maulakanda (129), Rambandh (130), Ghagra (131), Runiara (132), Rangamatia (133), Madhupur (134) & Bhedua (181) mouzas under Baricha, Zone-A to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 13) |  | Junior Engineer | ORD/000599/2021-2022 | 799/KSD | 14/12/2021 | 14/03/2022 | TAPAS DEY | 0.29 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Maulakanda (129), Rambandh (130), Ghagra (131), Runiara (132), Rangamatia (133), Madhupur (134) & Bhedua (181) mouzas by retrofitting of Water Supply Scheme for Baricha, Zone | SM/09620 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Zone-L (Dhankura) by retrofitting of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Mouza under Zone-L (Dhankura) :- Ghagra (115), Garra (116), Bauripal (156), Kalabani (157), Katro (158), Huang Khana (160), Punshya (161), Sindriam (162), Kankri Jharna (172), Khejur Khanma (173), Chalkigara (174), Dhoba Kacha (175), Madankata (176), Dangarda (177), Jantadumur (178), Barikul (179) & Lep-Am (180) Total Mouza:- 17 Nos. Total Household - 2137 Nos. | Assistant Engineer | Junior Engineer | ORD/000078/2021-2022 | 2411/BQA | 16/09/2021 | 31/10/2021 | ALOK ENTERPRISE | 135.35 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Maulakanda (129), Rambandh (130), Ghagra (131), Runiara (132), Rangamatia (133), Madhupur (134) & Bhedua (181) mouzas by retrofitting of Water Supply Scheme for Baricha, Zone | SM/09620 | Retrofitting | Laying of extra UPVC pipe from Bhaghucha to Chuaberia to increase water pressure for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/001537/2022-2023 | FHTC/19 | 19/01/2023 | 19/01/2023 | TAPAN KUMAR MANDAL | 4.49 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Maulakanda (129), Rambandh (130), Ghagra (131), Runiara (132), Rangamatia (133), Madhupur (134) & Bhedua (181) mouzas by retrofitting of Water Supply Scheme for Baricha, Zone | SM/09620 | Retrofitting | Laying extra UPVC Pipe Line to Cover Majit mouza and dismantling, reconstruction of concrete for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -I W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/001542/2022-2023 | FHTC/19 | 19/01/2023 | 19/01/2023 | MD. AFSAR ALI | 3.22 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Maulakanda (129), Rambandh (130), Ghagra (131), Runiara (132), Rangamatia (133), Madhupur (134) & Bhedua (181) mouzas by retrofitting of Water Supply Scheme for Baricha, Zone | SM/09620 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SALMA ZONE -(I &II) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR- Salma Zone -II, Name of Mouza:-- 1 no., (Dahuka), Total House Hold - 277 nos. |  |  | VCH/001540/2022-2023 | FHTC/19 | 19/01/2023 | 19/01/2023 | GOURANGA CHATTERJEE | 4.44 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Maulakanda (129), Rambandh (130), Ghagra (131), Runiara (132), Rangamatia (133), Madhupur (134) & Bhedua (181) mouzas by retrofitting of Water Supply Scheme for Baricha, Zone | SM/09620 | Retrofitting | Laying of extra UPVC pipe from Pabra more to Sat-deuli village due to damage by PWD Road for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme SALMA ZONE-III W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/001541/2022-2023 | FHTC/19 | 19/01/2023 | 19/01/2023 | LABIR MIRSHAD KHAN | 2.09 | 0 | 0 | 0
Total | [13 empty] | 245.86 | 0 | 0